## Sheet1
Parent WBS Name | Activity Name | Activity Unit | EST AMT - MATERIAL | EST AMT - SERVICE | EST AMT - TOTAL | THEORITICAL AMT - MATERIAL | THEORITICAL AMT - SERVICE | THEORITICAL AMT - TOTAL | ACTUAL AMT - MATERIAL | ACTUAL AMT - SERVICE | ACTUAL AMT - TOTAL
ANTI TERMITE TREATMENT | Anti Termite Treatment | sqft | 0 | 720000 | 720000 | 0 | 0 | 0 | 0 | 0 | 0
BRICK BAT COBA | Brick Bat Coba on Terrace | sqft | 2028881.72 | 1730000 | 3758881.72 | 0 | 0 | 0 | 0 | 0 | 0
BRICK MASONRY WORK | Brick Masonry 4.5" | sqft | 10856516.74 | 5397600 | 16254116.74 | 0 | 0 | 0 | 0 | 0 | 0
BRICK MASONRY WORK | Brick Masonry 9" | sqft | 7516178.76 | 2283600 | 9799778.76 | 0 | 0 | 0 | 0 | 0 | 0
EARTH WORK | Back Filling | cuft | 0 | 66732 | 66732 | 0 | 0 | 0 | 0 | 0 | 0
EARTH WORK | Excavation | cuft | 0 | 3600000 | 3600000 | 0 | 0 | 0 | 0 | 808297 | 808297
GENERAL SITE WORKS | Barricading Work | lumpsum | 0 | 157500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Chipping, Grinding & Welding | lumpsum | 0 | 390000 | 390000 | 0 | 1300 | 1300 | 0 | 0 | 0
GENERAL SITE WORKS | Cleaning Work | lumpsum | 0 | 720000 | 720000 | 0 | 0 | 0 | 0 | 1620 | 1620
GENERAL SITE WORKS | Curing | lumpsum | 0 | 540000 | 540000 | 0 | 8400 | 8400 | 0 | 5280 | 5280
GENERAL SITE WORKS | Dismantling | lumpsum | 0 | 120000 | 120000 | 0 | 800 | 800 | 0 | 770 | 770
GENERAL SITE WORKS | Electrical, Plumbing,Mechanical Work | lumpsum | 0 | 270000 | 270000 | 0 | 14550 | 14550 | 0 | 11342 | 11342
GENERAL SITE WORKS | Housekeeping Work | lumpsum | 0 | 720000 | 720000 | 0 | 22900 | 22900 | 0 | 16753 | 16753
GENERAL SITE WORKS | Lab Work | lumpsum | 0 | 337500 | 337500 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Labour Supply to Client | lumpsum | 0 | 0.5 | 0.5 | 0 | 0.09 | 0.09 | 0 | 4730 | 4730
GENERAL SITE WORKS | Labour Supply to Other Site/Godown | lumpsum | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Level Marking & Layout | lumpsum | 0 | 869925 | 869925 | 0 | 39178.12 | 39178.12 | 0 | 33046 | 33046
GENERAL SITE WORKS | Leveling Dressing | lumpsum | 0 | 106000 | 106000 | 0 | 79952 | 79952 | 0 | 68968 | 68968
GENERAL SITE WORKS | Lift Operator | lumpsum | 0 | 292600 | 292600 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Material Shifting Loading Unloading | lumpsum | 0 | 1440000 | 1440000 | 0 | 62100 | 62100 | 0 | 52297 | 52297
GENERAL SITE WORKS | Mess Caretaker | lumpsum | 0 | 180000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Oiling Taping Cover Block Fixing | lumpsum | 0 | 648000 | 648000 | 0 | 0 | 0 | 0 | 2503 | 2503
GENERAL SITE WORKS | Rebarring Work | lumpsum | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Repairing | lumpsum | 0 | 315000 | 315000 | 0 | 30253.12 | 30253.12 | 0 | 25494 | 25494
GENERAL SITE WORKS | Slab Ponding Work | lumpsum | 0 | 39000 | 39000 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Starter Fixing | lumpsum | 0 | 283500 | 283500 | 0 | 1378.12 | 1378.12 | 0 | 1046 | 1046
GENERAL SITE WORKS | Sweeper & Office boy | lumpsum | 0 | 105000 | 105000 | 0 | 9100 | 9100 | 0 | 9100 | 9100
HIRE & RENT | Machine Hire charges | lumpsum | 0 | 533604 | 533604 | 0 | 0 | 0 | 0 | 79138 | 79138
HIRE & RENT | Shuttering Rent | lumpsum | 0 | 6920000 | 6920000 | 0 | 0 | 0 | 0 | 0 | 0
HIRE & RENT | Tools and Plant Rent | lumpsum | 0 | 8175000 | 8175000 | 0 | 0 | 0 | 0 | 0 | 0
PLAIN CEMENT CONCRETE | PCC M-10 (RMC) | cuft | 338952.6 | 11400 | 350352.6 | 0 | 0 | 0 | 136475 | 0 | 136475
PLAIN CEMENT CONCRETE | PCC M-10 (Site Plant Mix) | cuft | 6580441.8 | 1500000 | 8080441.8 | 0 | 0 | 0 | 0 | 0 | 0
PLASTER WORK | External Plaster Work | sqft | 3492890.76 | 6228000 | 9720890.76 | 0 | 0 | 0 | 0 | 0 | 0
PLASTER WORK | Internal Plaster Work | sqft | 5795551.9 | 9515000 | 15310551.9 | 0 | 0 | 0 | 0 | 0 | 0
REINFORCED CEMENT CONCRETE | RCC M-25 (RMC) | cuft | 2421090 | 68400 | 2489490 | 0 | 0 | 0 | 96562.5 | 0 | 96562.5
REINFORCED CEMENT CONCRETE | RCC M-25 (Site Plant Mix) | cuft | 43024413.94 | 1800000 | 44824413.94 | 0 | 0 | 0 | 0 | 0 | 0
SCAFFOLDING WORK | Scaffolding Work | sqft | 0 | 3460000 | 3460000 | 0 | 0 | 0 | 0 | 0 | 0
SHUTTERING WORK | Shuttering Making Work | sqft | 0 | 588120 | 588120 | 0 | 0 | 0 | 0 | 34707 | 34707
SHUTTERING WORK | Shuttering Work | sqft | 12974665.6 | 15224000 | 28198665.6 | 0 | 0 | 0 | 509716.68 | 73166 | 582882.68
SITE ADMINISTRATIVE EXPENSES | Diesel | lumpsum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Electrical Charges | lumpsum | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Head Office Overhead | lumpsum | 0 | 12715500 | 12715500 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Installation Charges | lumpsum | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Lab Material | lumpsum | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Machine & Vehicle Service Charges | lumpsum | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Office Goods | lumpsum | 0 | 192300 | 192300 | 0 | 0 | 0 | 0 | 129738 | 129738
SITE ADMINISTRATIVE EXPENSES | Property Rent Charges | lumpsum | 0 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Safety Items | lumpsum | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 880 | 880
SITE ADMINISTRATIVE EXPENSES | Security Guard | lumpsum | 0 | 900000 | 900000 | 0 | 0 | 0 | 0 | 108064 | 108064
SITE ADMINISTRATIVE EXPENSES | Site Office | lumpsum | 0 | 135000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Salary | lumpsum | 0 | 7875000 | 7875000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Welfare &medicne | lumpsum | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Stationary | lumpsum | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Toilets | lumpsum | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Tools and Plant Material | lumpsum | 0 | 170000 | 170000 | 0 | 0 | 0 | 0 | 482 | 482
SITE ADMINISTRATIVE EXPENSES | Transportation & Courier Charges | lumpsum | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Travel & Conveyance | lumpsum | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Water Charges | lumpsum | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 55 | 55
SITE INFRA WORK | Infra - Backfilling | cuft | 0 | 1.2 | 1.2 | 0 | 1.2 | 1.2 | 0 | 1030 | 1030
SITE INFRA WORK | Infra - Brick Masonry 4.5 | sqft | 65430.37 | 30000 | 95430.37 | 41032.85 | 19999.34 | 61032.19 | 25707.72 | 26809 | 52516.72
SITE INFRA WORK | Infra - Brick Masonry 9 | sqft | 903559.97 | 231000 | 1134559.97 | 308321.49 | 84821.07 | 393142.56 | 316045.94 | 124107 | 440152.94
SITE INFRA WORK | Infra - Brick Masonry 9 (Plus) | cuft | 35582 | 12000 | 47582 | 28487.84 | 9607.5 | 38095.34 | 0 | 1351 | 1351
SITE INFRA WORK | Infra - Door/Window Fixing Work | nos | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Electrical Work | nos | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Excavation | cuft | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - External Plaster | sqft | 459223.8 | 189000 | 648223.8 | 62408.73 | 26990.8 | 89399.53 | 5961.75 | 15615 | 21576.75
SITE INFRA WORK | Infra - Fabrication Work | sqft | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 1100 | 1100
SITE INFRA WORK | Infra - Flooring Work | sqft | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Hutment Dismantling Work | nos | 0 | 29000 | 29000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Hutment Fabrication Work | nos | 613640 | 69600 | 683240 | 550160 | 62400 | 612560 | 467724.6 | 0 | 467724.6
SITE INFRA WORK | Infra - Internal Plaster | sqft | 82463.04 | 115000 | 197463.04 | 28117.36 | 44237.5 | 72354.86 | 6391.05 | 48343 | 54734.05
SITE INFRA WORK | Infra - PCC (RMC 10) | cuft | 32150 | 706.28 | 32856.28 | 32148.43 | 706.28 | 32854.71 | 25750 | 1850 | 27600
SITE INFRA WORK | Infra - PCC (RMC 7.5) | cuft | 12328.04 | 280 | 12608.04 | 3677.37 | 83.52 | 3760.89 | 0 | 0 | 0
SITE INFRA WORK | Infra - PCC Work | cuft | 275783.1 | 48000 | 323783.1 | 176916.71 | 32694.24 | 209610.95 | 47650.58 | 77593 | 125243.58
SITE INFRA WORK | Infra - Paint Work | sqft | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Plumbing Work | nos | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - RCC (RMC 30) | cuft | 113973.4 | 15891.62 | 129865.02 | 86852.02 | 12110.1 | 98962.12 | 59225 | 6661 | 65886
SITE INFRA WORK | Infra - RCC (RMC 35) | cuft | 122413.26 | 14302.17 | 136715.43 | 120441.33 | 14071.8 | 134513.13 | 69525 | 11930 | 81455
SITE INFRA WORK | Infra - RCC Work | cuft | 478664.66 | 125000 | 603664.66 | 16488.43 | 4680.5 | 21168.93 | 56695.95 | 5358 | 62053.95
SITE INFRA WORK | Infra - Reinforcement Work | MT | 122018.5 | 15000 | 137018.5 | 27362.73 | 12900 | 40262.73 | 114792.06 | 10990 | 125782.06
SITE INFRA WORK | Infra - Shuttering Work | sqft | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 0 | 0
SITE INFRA WORK | Infra - Stone Masonry Work | cuft | 109950 | 40000 | 149950 | 91789.01 | 33393 | 125182.01 | 108842.67 | 57737 | 166579.67
SITE INFRA WORK | Infra -Wall Tile Work | sqft | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SLAB PONDING | Slab Ponding Work | sqft | 147396 | 0 | 147396 | 0 | 0 | 0 | 0 | 0 | 0
STEEL BINDING WORK | Steel Binding Work | kg | 99163686.5 | 12110000 | 111273686.5 | 0 | 0 | 0 | 4260751.72 | 92469 | 4353220.72
Total |  |  | 197767846.46 | 112761098.79 | 310528945.25 | 1574204.3 | 628618.31 | 2202822.61 | 6307818.22 | 1950419 | 8258237.22