## Detailed Data
Report Type : Labour Costing Report
Project Name : Radisson Collection Hotel
Generated on: 2026-04-02 06:23:54
Parent WBS Name | Activity Name | Item Group | Item Desc | Resource Unit | Est Qty | Est Rate | Est Amt | DPR Work Qty | SRN Billed Qty | Difference Qty | Theoritical Work Amt | SRN Amt | Difference Amt | Act Rate | Balance Work Amt [Est - Th] | Percentage Work Completed [DPR/Est]*100 | Work Amt
ANTI TERMITE TREATMENT | Anti Termite Treatment | Labour-Civil-Earth Work | Anti Termite Treatment | sqft | 60000 | 12 | 720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0
BRICK BAT COBA | Brick Bat Coba on Terrace | Labour-Civil-Brick Bat Coba Work | Brick Bat Coba Work | sqft | 69200 | 25 | 1730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730000 | 0 | 0
BRICK MASONRY WORK | Brick Masonry 9" | Labour-Civil-Masonry Work | Masonry Work Brick 9" Thick | sqft | 103800 | 22 | 2283600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2283600 | 0 | 0
BRICK MASONRY WORK | Brick Masonry 4.5" | Labour-Civil-Masonry Work | Masonry Work Brick 4.5" Thick | sqft | 269880 | 20 | 5397600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5397600 | 0 | 0
EARTH WORK | Back Filling | Labour-Civil-Earth Work | Back Filling Work | cuft | 22244 | 3 | 66732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66732 | 0 | 0
EARTH WORK | Excavation | Labour-Civil-Earth Work | Excavation Work | cuft | 1200000 | 3 | 3600000 | 0 | 439291.71 | -439291.71 | 0 | 808297 | -808297 | 1.84 | 3600000 | 0 | 0
GENERAL SITE WORKS | Barricading Work | Labour-General Works | Barricading Work | lumpsum | 450 | 350 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157500 | 0 | 0
GENERAL SITE WORKS | Slab Ponding Work | Labour-General Works | Slab Ponding Work | lumpsum | 78 | 500 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 0 | 0
GENERAL SITE WORKS | Sweeper & Office boy | Labour-General Works | Sweeper & Office boy | lumpsum | 300 | 350 | 105000 | 26 | 26 | 0 | 9100 | 9100 | 0 | 350 | 95900 | 8.6667 | 9100
GENERAL SITE WORKS | Starter Fixing | Labour-General Works | Starter fixing | lumpsum | 540 | 525 | 283500 | 2.625 | 2.63 | -0.005 | 1378.125 | 1046 | 332.125 | 397.7186 | 282121.875 | 0.48611 | 1044.0114
GENERAL SITE WORKS | Repairing | Labour-General Works | Repairing | lumpsum | 600 | 525 | 315000 | 57.625 | 58.63 | -1.005 | 30253.125 | 25494 | 4759.125 | 434.8286 | 284746.875 | 9.6042 | 25056.9973
GENERAL SITE WORKS | Rebarring Work | Labour-General Works | Rebarring Work | lumpsum | 1 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0
GENERAL SITE WORKS | Oiling Taping Cover Block Fixing | Labour-General Works | Oiling Taping Cover Block Fixing | lumpsum | 1620 | 400 | 648000 | 0 | 6.75 | -6.75 | 0 | 2503 | -2503 | 370.8148 | 648000 | 0 | 0
GENERAL SITE WORKS | Mess Caretaker | Site Expenses | Mess Caretaker | lumpsum | 450 | 400 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0
GENERAL SITE WORKS | Material Shifting Loading Unloading | Site Expenses | Material Shifting Loading Unloading | lumpsum | 3600 | 400 | 1440000 | 155.25 | 151.26 | 3.99 | 62100 | 52297 | 9803 | 345.7424 | 1377900 | 4.3125 | 53676.5123
GENERAL SITE WORKS | Leveling Dressing | Labour-General Works | Leveling and Dressing | lumpsum | 265 | 400 | 106000 | 199.88 | 193.13 | 6.75 | 79952 | 68968 | 10984 | 357.1066 | 26048 | 75.4264 | 71378.4696
GENERAL SITE WORKS | Labour Supply to Client | Labour-General Works | Labour Supply to Client | lumpsum | 50 | 0.01 | 0.5 | 9 | 9 | 0 | 0.09 | 4730 | -4729.91 | 525.5556 | 0.41 | 18 | 4730
GENERAL SITE WORKS | Labour Supply to Other Site/Godown | Labour-General Works | Labour Supply to Other Site/Godown | lumpsum | 600 | 0.01 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
GENERAL SITE WORKS | Lift Operator | Labour-General Works | Lift Operator | lumpsum | 836 | 350 | 292600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292600 | 0 | 0
GENERAL SITE WORKS | Lab Work | Labour-General Works | Lab Work | lumpsum | 675 | 500 | 337500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 337500 | 0 | 0
GENERAL SITE WORKS | Housekeeping Work | Labour-General Works | Housekeeping Work | lumpsum | 1800 | 400 | 720000 | 57.25 | 55.25 | 2 | 22900 | 16753 | 6147 | 303.2217 | 697100 | 3.1806 | 17359.4434
GENERAL SITE WORKS | Electrical, Plumbing,Mechanical Work | Labour-General Works | Electrical-Plumbing-Mechanical Work | lumpsum | 450 | 600 | 270000 | 24.25 | 24.26 | -0.01 | 14550 | 11342 | 3208 | 467.5185 | 255450 | 5.3889 | 11337.3248
GENERAL SITE WORKS | Dismantling | Labour-General Works | Dismantling | lumpsum | 300 | 400 | 120000 | 2 | 2 | 0 | 800 | 770 | 30 | 385 | 119200 | 0.66667 | 770
GENERAL SITE WORKS | Curing | Labour-General Works | Curing | lumpsum | 1350 | 400 | 540000 | 21 | 16 | 5 | 8400 | 5280 | 3120 | 330 | 531600 | 1.5556 | 6930
GENERAL SITE WORKS | Cleaning Work | Labour-General Works | Cleaning Work | lumpsum | 1800 | 400 | 720000 | 0 | 5 | -5 | 0 | 1620 | -1620 | 324 | 720000 | 0 | 0
GENERAL SITE WORKS | Chipping, Grinding & Welding | Labour-General Works | Chipping / Grinding & Welding | lumpsum | 600 | 650 | 390000 | 2 | 0 | 2 | 1300 | 0 | 1300 | 0 | 388700 | 0.33333 | 0
GENERAL SITE WORKS | Level Marking & Layout | Labour-General Works | Level Marking & Layout | lumpsum | 1657 | 525 | 869925 | 74.625 | 74.63 | -0.005 | 39178.125 | 33046 | 6132.125 | 442.7978 | 830746.875 | 4.5036 | 33043.786
HIRE & RENT | Tools and Plant Rent | Hire & Rent | Tools Rent | lumpsum | 8175000 | 1 | 8175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8175000 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | JCB HIRE CHARGE | hours | 72 | 800 | 57600 | 0 | 64.28 | -64.28 | 0 | 54638 | -54638 | 850 | 57600 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | Vehicle Hire Charges | lumpsum | 50000 | 1 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | JCB & Dumper Hire Charges for Debris Removal (Per Trip) | per trip | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | JCB Excavator (Poclain) Hire Charges 140 for Excavation 9 (Hours) | perhour | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | JCB Hydraulic Rock Breaker (Hours) | perhour | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
HIRE & RENT | Shuttering Rent | Hire & Rent | Shuttering Material on Rent | lumpsum | 6920000 | 1 | 6920000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6920000 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | Tractor Hire Charges (Hours) | hours | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | Machinery Hire Charges | lumpsum | 30 | 1700 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | Tractor Hire Charges (Monthly) | per month | 15 | 25000 | 375000 | 0 | 1 | -1 | 0 | 24500 | -24500 | 24500 | 375000 | 0 | 0
PLAIN CEMENT CONCRETE | PCC M-10 (Site Plant Mix) | Labour-Civil-Concreting Work | Concreting Work PCC | cuft | 100000 | 15 | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 0
PLAIN CEMENT CONCRETE | PCC M-10 (RMC) | Labour-Civil-Concreting Work | Concreting Work with RMC M-10 | cuft | 3800 | 3 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11400 | 0 | 0
PLASTER WORK | Internal Plaster Work | Labour-Civil-Plaster Work | Plaster Work Internal | sqft | 865000 | 11 | 9515000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9515000 | 0 | 0
PLASTER WORK | External Plaster Work | Labour-Civil-Plaster Work | Plaster Work External | sqft | 346000 | 18 | 6228000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6228000 | 0 | 0
REINFORCED CEMENT CONCRETE | RCC M-25 (Site Plant Mix) | Labour-Civil-Concreting Work | Concreting Work RCC | cuft | 500000 | 3.6 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800000 | 0 | 0
REINFORCED CEMENT CONCRETE | RCC M-25 (RMC) | Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | 19000 | 3.6 | 68400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68400 | 0 | 0
SCAFFOLDING WORK | Scaffolding Work | Labour-Civil-Scaffolding | De-Scaffolding | sqft | 346000 | 5 | 1730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730000 | 0 | 0
SCAFFOLDING WORK | Scaffolding Work | Labour-Civil-Scaffolding | Scaffolding | sqft | 346000 | 5 | 1730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730000 | 0 | 0
SHUTTERING WORK | Shuttering Making Work | Labour-Civil-Shuttering Work | Shuttering Making Work | sqft | 73515 | 8 | 588120 | 0 | 4338.43 | -4338.43 | 0 | 34707 | -34707 | 7.9999 | 588120 | 0 | 0
SHUTTERING WORK | Shuttering Work | Labour-Civil-Shuttering Work | Shuttering Work | sqft | 692000 | 22 | 15224000 | 0 | 4877.74 | -4877.74 | 0 | 73166 | -73166 | 15 | 15224000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Safety Items | Site Expenses | Safety Items | lumpsum | 500000 | 1 | 500000 | 0 | 880 | -880 | 0 | 880 | -880 | 1 | 500000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Transportation & Courier Charges | Site Expenses | Transportation and Courier Charges | lumpsum | 150000 | 1 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Travel & Conveyance | Site Expenses | Travel & Conveyance | lumpsum | 150000 | 1 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Welfare &medicne | Site Expenses | Staff Welfare and Medicines | lumpsum | 75000 | 1 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Salary | Site Expenses | Staff Salary | lumpsum | 7875000 | 1 | 7875000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Site Office | Site Expenses | Site Office | lumpsum | 135000 | 1 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Water Charges | Site Expenses | Water Charges | lumpsum | 75000 | 1 | 75000 | 0 | 55.22 | -55.22 | 0 | 55 | -55 | 0.99602 | 75000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Security Guard | Site Expenses | Security Guard | lumpsum | 900000 | 1 | 900000 | 0 | 22405.354 | -22405.354 | 0 | 108064 | -108064 | 4.8231 | 900000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Stationary | Site Expenses | STATIONARY | Rs. | 75000 | 1 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Property Rent Charges | Site Expenses | Property Rent Charges | lumpsum | 300000 | 1 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Office Goods | Site Expenses | Office Goods | lumpsum | 192300 | 1 | 192300 | 0 | 129738.36 | -129738.36 | 0 | 129738 | -129738 | 1 | 192300 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Machine & Vehicle Service Charges | Site Expenses | Machine & Vehicle Service Charges | lumpsum | 200000 | 1 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Lab Material | Site Expenses | Lab Material | lumpsum | 500000 | 1 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Installation Charges | Site Expenses | Installation Charges | lumpsum | 200000 | 1 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Head Office Overhead | Overheads | Head Office Overhead | lumpsum | 12715500 | 1 | 12715500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12715500 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Electrical Charges | Site Expenses | Electricity Charges | lumpsum | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Diesel | Site Expenses | Diesel Expenses | lumpsum | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Toilets | Labour-General Works | Toilets Construction Work | lumpsum | 100000 | 1 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Tools and Plant Material | Site Expenses | Tools and Plant Material | Rs. | 170000 | 1 | 170000 | 0 | 482.02 | -482.02 | 0 | 482 | -482 | 0.99996 | 170000 | 0 | 0
SITE INFRA WORK | Infra - Hutment Dismantling Work | Labour-Site Infra Work | Infra - Hutment Dismantling Work | nos | 58 | 500 | 29000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29000 | 0 | 0
SITE INFRA WORK | Infra - Flooring Work | Labour-Site Infra Work | Infra - Flooring Work | sqft | 1 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
SITE INFRA WORK | Infra - Fabrication Work | Labour-Site Infra Work | Infra - Fabrication Work | sqft | 100 | 15 | 1500 | 0 | 74 | -74 | 0 | 1100 | -1100 | 14.8649 | 1500 | 0 | 0
SITE INFRA WORK | Infra - Excavation | Labour-Site Infra Work | Infra - Excavation | cuft | 500 | 4 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0
SITE INFRA WORK | Infra - External Plaster | Labour-Site Infra Work | Infra - External Plaster | sqft | 10500 | 18 | 189000 | 1499.489 | 1843.49 | -344.001 | 26990.802 | 15615 | 11375.802 | 8.4703 | 162009.198 | 14.2808 | 12701.1922
SITE INFRA WORK | Infra - Electrical Work | Labour-Site Infra Work | Infra - Electrical Work | nos | 1 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0
SITE INFRA WORK | Infra - Door/Window Fixing Work | Labour-Site Infra Work | Infra - Door/Window Fixing | nos | 5 | 500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0
SITE INFRA WORK | Infra - Brick Masonry 9 (Plus) | Labour-Site Infra Work | Infra - Brick Masonry 9" Plus | cuft | 400 | 30 | 12000 | 320.25 | 320.25 | 0 | 9607.5 | 1351 | 8256.5 | 4.2186 | 2392.5 | 80.0625 | 1351
SITE INFRA WORK | Infra - Brick Masonry 9 | Labour-Site Infra Work | Infra - Brick Masonry 9" | sqft | 10500 | 22 | 231000 | 3855.503 | 5158.72 | -1303.217 | 84821.066 | 124107 | -39285.934 | 24.0577 | 146178.934 | 36.7191 | 92754.5808
SITE INFRA WORK | Infra - Brick Masonry 4.5 | Labour-Site Infra Work | Infra - Brick Masonry 4.5" | sqft | 1500 | 20 | 30000 | 999.967 | 1289.84 | -289.873 | 19999.34 | 26809 | -6809.66 | 20.7847 | 10000.66 | 66.6645 | 20784.0626
SITE INFRA WORK | Infra - Backfilling | Labour-Site Infra Work | Infra - Backfilling | cuft | 120 | 0.01 | 1.2 | 120 | 120 | 0 | 1.2 | 1030 | -1028.8 | 8.5833 | 0 | 100 | 1030
SITE INFRA WORK | Infra - Paint Work | Labour-Site Infra Work | Infra - Paint Work | sqft | 5000 | 6 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0
SITE INFRA WORK | Infra - Hutment Fabrication Work | Labour-Site Infra Work | Infra-Hutment Fabrication Work | nos | 58 | 1200 | 69600 | 52 | 0 | 52 | 62400 | 0 | 62400 | 0 | 7200 | 89.6552 | 0
SITE INFRA WORK | Infra - Internal Plaster | Labour-Site Infra Work | Infra - Internal Plaster | sqft | 11500 | 10 | 115000 | 4423.75 | 4521.18 | -97.43 | 44237.5 | 48343 | -4105.5 | 10.6926 | 70762.5 | 38.4674 | 47301.2236
SITE INFRA WORK | Infra - PCC Work | Labour-Site Infra Work | Infra - PCC Work | cuft | 4000 | 12 | 48000 | 2724.52 | 3263.82 | -539.3 | 32694.24 | 77593 | -44898.76 | 23.7737 | 15305.76 | 68.113 | 64771.8564
SITE INFRA WORK | Infra - PCC (RMC 10) | Labour-Civil-Concreting Work | Concreting Work with RMC M-10 | cuft | 353.14 | 2 | 706.28 | 353.14 | 353.14 | 0 | 706.28 | 1850 | -1143.72 | 5.2387 | 0 | 100 | 1850
SITE INFRA WORK | Infra -Wall Tile Work | Labour-Site Infra Work | Infra -Wall Tile Work | sqft | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
SITE INFRA WORK | Infra - Stone Masonry Work | Labour-Site Infra Work | Infra - Stone Masonry Work | cuft | 2000 | 20 | 40000 | 1669.65 | 1823.29 | -153.64 | 33393 | 57737 | -24344 | 31.6664 | 6607 | 83.4825 | 52871.7769
SITE INFRA WORK | Infra - Shuttering Work | Labour-Site Infra Work | Infra - Shuttering | sqft | 1000 | 0.01 | 10 | 1000 | 0 | 1000 | 10 | 0 | 10 | 0 | 0 | 100 | 0
SITE INFRA WORK | Infra - Reinforcement Work | Labour-Site Infra Work | Infra - Reinforcement | MT | 2.5 | 6000 | 15000 | 2.15 | 2.198 | -0.048 | 12900 | 10990 | 1910 | 5000 | 2100 | 86 | 10750
SITE INFRA WORK | Infra - RCC Work | Labour-Site Infra Work | Infra - RCC Work | cuft | 5000 | 25 | 125000 | 187.22 | 187.16 | 0.06 | 4680.5 | 5358 | -677.5 | 28.6279 | 120319.5 | 3.7444 | 5359.7177
SITE INFRA WORK | Infra - RCC (RMC 35) | Labour-Site Infra Work | Infra - RCC Work (RMC) | cuft | 953.478 | 15 | 14302.17 | 938.12 | 938.15 | -0.03 | 14071.8 | 11930 | 2141.8 | 12.7165 | 230.37 | 98.3893 | 11929.6185
SITE INFRA WORK | Infra - RCC (RMC 30) | Labour-Site Infra Work | Infra - RCC Work (RMC) | cuft | 1059.441 | 15 | 15891.62 | 807.34 | 807.35 | -0.01 | 12110.1 | 6661 | 5449.1 | 8.2504 | 3781.52 | 76.2043 | 6660.9175
SITE INFRA WORK | Infra - Plumbing Work | Labour-Site Infra Work | Infra - Plumbing Work | nos | 1 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0
SITE INFRA WORK | Infra - PCC (RMC 7.5) | Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | 140 | 2 | 280 | 41.76 | 0 | 41.76 | 83.52 | 0 | 83.52 | 0 | 196.48 | 29.8286 | 0
STEEL BINDING WORK | Steel Binding Work | Labour-Civil-Reinforcement Work | Reinforcement Work Steel Binding | kg | 1730000 | 7 | 12110000 | 0 | 14226 | -14226 | 0 | 92469 | -92469 | 6.5 | 12110000 | 0 | 0

## Summary
Report Type : Labour Costing Summary
Project Name : Radisson Collection Hotel
Generated on: 2026-04-02 06:23:54
Labour Costing Summary | Estimated Amount | Theoritical Amount | Actual Amount
Productive Labour | 64302852 | -1.1642e-10 | 1008639
Site Infra Work | 982810.28 | 358706.848 | 390474
General Site Work | 7534031.51 | 269911.465 | 232949
Hire & Rent | 15628604 | 0 | 79138
Site Admin Expenses | 24312801 | 0 | 239219