## Sheet1
Parent WBS Name | Activity Name | Activity Unit | EST AMT - MATERIAL | EST AMT - SERVICE | EST AMT - TOTAL | THEORITICAL AMT - MATERIAL | THEORITICAL AMT - SERVICE | THEORITICAL AMT - TOTAL | ACTUAL AMT - MATERIAL | ACTUAL AMT - SERVICE | ACTUAL AMT - TOTAL
ANTI TERMITE TREATMENT | Anti Termite Treatment | sqft | 0 | 720000 | 720000 | 0 | 0 | 0 | 0 | 0 | 0
BRICK BAT COBA | Brick Bat Coba on Terrace | sqft | 2028881.72 | 1730000 | 3758881.72 | 0 | 0 | 0 | 0 | 0 | 0
BRICK MASONRY WORK | Brick Masonry 4.5" | sqft | 10856516.74 | 5397600 | 16254116.74 | 0 | 0 | 0 | 0 | 0 | 0
BRICK MASONRY WORK | Brick Masonry 9" | sqft | 7516178.76 | 2283600 | 9799778.76 | 27427.82 | 8333.25 | 35761.07 | 0 | 4980 | 4980
EARTH WORK | Back Filling | cuft | 0 | 66732 | 66732 | 0 | 0 | 0 | 0 | 0 | 0
EARTH WORK | Excavation | cuft | 0 | 3600000 | 3600000 | 0 | 2189243.01 | 2189243.01 | 0 | 1342736 | 1342736
GENERAL SITE WORKS | Barricading Work | lumpsum | 0 | 157500 | 157500 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Chipping, Grinding & Welding | lumpsum | 0 | 390000 | 390000 | 0 | 6500 | 6500 | 0 | 2805 | 2805
GENERAL SITE WORKS | Cleaning Work | lumpsum | 0 | 720000 | 720000 | 0 | 3352 | 3352 | 0 | 1622 | 1622
GENERAL SITE WORKS | Curing | lumpsum | 0 | 540000 | 540000 | 0 | 49760 | 49760 | 0 | 18735 | 18735
GENERAL SITE WORKS | Dismantling | lumpsum | 0 | 120000 | 120000 | 0 | 800 | 800 | 0 | 770 | 770
GENERAL SITE WORKS | Electrical, Plumbing,Mechanical Work | lumpsum | 0 | 270000 | 270000 | 0 | 17550 | 17550 | 0 | 13092 | 13092
GENERAL SITE WORKS | Housekeeping Work | lumpsum | 0 | 720000 | 720000 | 0 | 27000 | 27000 | 0 | 18609 | 18609
GENERAL SITE WORKS | Lab Work | lumpsum | 0 | 337500 | 337500 | 0 | 26385 | 26385 | 0 | 12785 | 12785
GENERAL SITE WORKS | Labour Supply to Client | lumpsum | 0 | 0.5 | 0.5 | 0 | 0.09 | 0.09 | 0 | 4730 | 4730
GENERAL SITE WORKS | Labour Supply to Other Site/Godown | lumpsum | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Level Marking & Layout | lumpsum | 0 | 869925 | 869925 | 0 | 119980.88 | 119980.88 | 0 | 70631 | 70631
GENERAL SITE WORKS | Leveling Dressing | lumpsum | 0 | 200000 | 200000 | 0 | 175784 | 175784 | 0 | 121297 | 121297
GENERAL SITE WORKS | Lift Operator | lumpsum | 0 | 292600 | 292600 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Material Shifting Loading Unloading | lumpsum | 0 | 1440000 | 1440000 | 0 | 83510 | 83510 | 0 | 60837 | 60837
GENERAL SITE WORKS | Mess Caretaker | lumpsum | 0 | 180000 | 180000 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Oiling Taping Cover Block Fixing | lumpsum | 0 | 648000 | 648000 | 0 | 2700 | 2700 | 0 | 2503 | 2503
GENERAL SITE WORKS | Rebarring Work | lumpsum | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Repairing | lumpsum | 0 | 315000 | 315000 | 0 | 48767.25 | 48767.25 | 0 | 31813 | 31813
GENERAL SITE WORKS | Slab Ponding Work | lumpsum | 0 | 39000 | 39000 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORKS | Starter Fixing | lumpsum | 0 | 283500 | 283500 | 0 | 45215.62 | 45215.62 | 0 | 22885 | 22885
GENERAL SITE WORKS | Sweeper & Office boy | lumpsum | 0 | 105000 | 105000 | 0 | 27650 | 27650 | 0 | 18550 | 18550
HIRE & RENT | Machine Hire charges | lumpsum | 0 | 2513604 | 2513604 | 0 | 0 | 0 | 0 | 234868 | 234868
HIRE & RENT | Shuttering Rent | lumpsum | 0 | 6920000 | 6920000 | 0 | 0 | 0 | 0 | 0 | 0
HIRE & RENT | Tools and Plant Rent | lumpsum | 0 | 8175000 | 8175000 | 0 | 0 | 0 | 0 | 0 | 0
PLAIN CEMENT CONCRETE | PCC M-10 (RMC) | cuft | 338952.6 | 11400 | 350352.6 | 0 | 0 | 0 | 203221.08 | 0 | 203221.08
PLAIN CEMENT CONCRETE | PCC M-10 (Site Plant Mix) | cuft | 7079205 | 1500000 | 8579205 | 619929.17 | 131355.67 | 751284.84 | 524073.04 | 79278 | 603351.03
PLASTER WORK | External Plaster Work | sqft | 3492890.76 | 6228000 | 9720890.76 | 5339.39 | 10152 | 15491.39 | 0 | 0 | 0
PLASTER WORK | Internal Plaster Work | sqft | 5795551.9 | 9515000 | 15310551.9 | 0 | 0 | 0 | 0 | 0 | 0
REINFORCED CEMENT CONCRETE | RCC M-25 (RMC) | cuft | 2421090 | 68400 | 2489490 | 0 | 0 | 0 | 1911277 | 0 | 1911277
REINFORCED CEMENT CONCRETE | RCC M-25 (Site Plant Mix) | cuft | 88331325.94 | 1800000 | 90131325.94 | 5696266.38 | 116077.5 | 5812343.88 | 1641025.53 | 250169 | 1891194.53
SCAFFOLDING WORK | Scaffolding Work | sqft | 0 | 3460000 | 3460000 | 0 | 0 | 0 | 0 | 0 | 0
SHUTTERING WORK | Shuttering Making Work | sqft | 0 | 588120 | 588120 | 0 | 42387.44 | 42387.44 | 0 | 128915 | 128915
SHUTTERING WORK | Shuttering Work | sqft | 12974665.6 | 15224000 | 28198665.6 | 263873.01 | 309618.98 | 573491.99 | 1924342.29 | 572681 | 2497023.29
SITE ADMINISTRATIVE EXPENSES | Diesel | lumpsum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Electrical Charges | lumpsum | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Head Office Overhead | lumpsum | 0 | 12715500 | 12715500 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Installation Charges | lumpsum | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Lab Material | lumpsum | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Machine & Vehicle Service Charges | lumpsum | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Office Goods | lumpsum | 0 | 192300 | 192300 | 0 | 0 | 0 | 0 | 129738 | 129738
SITE ADMINISTRATIVE EXPENSES | Property Rent Charges | lumpsum | 0 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Safety Items | lumpsum | 0 | 500000 | 500000 | 0 | 0 | 0 | 0 | 880 | 880
SITE ADMINISTRATIVE EXPENSES | Security Guard | lumpsum | 0 | 900000 | 900000 | 0 | 0 | 0 | 0 | 270640 | 270640
SITE ADMINISTRATIVE EXPENSES | Site Office | lumpsum | 0 | 135000 | 135000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Salary | lumpsum | 0 | 7875000 | 7875000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Welfare &medicne | lumpsum | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Stationary | lumpsum | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Toilets | lumpsum | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Tools and Plant Material | lumpsum | 0 | 170000 | 170000 | 0 | 0 | 0 | 0 | 482 | 482
SITE ADMINISTRATIVE EXPENSES | Transportation & Courier Charges | lumpsum | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Travel & Conveyance | lumpsum | 0 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Water Charges | lumpsum | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 55 | 55
SITE INFRA WORK | Dismantling Work (Sqft) | sqft | 31740000 | 3602500 | 35342500 | 0 | 0 | 0 | 0 | 7760 | 7760
SITE INFRA WORK | Infra - Backfilling | cuft | 0 | 1.2 | 1.2 | 0 | 1.2 | 1.2 | 0 | 1030 | 1030
SITE INFRA WORK | Infra - Brick Masonry 4.5 | sqft | 65430.37 | 200000 | 265430.37 | 104154.53 | 50764.74 | 154919.27 | 74832.42 | 30826 | 105658.42
SITE INFRA WORK | Infra - Brick Masonry 9 | sqft | 903559.97 | 231000 | 1134559.97 | 463601.36 | 127539.48 | 591140.84 | 393557.69 | 127408 | 520965.69
SITE INFRA WORK | Infra - Brick Masonry 9 (Plus) | cuft | 35582 | 12000 | 47582 | 28487.84 | 9607.5 | 38095.34 | 0 | 1351 | 1351
SITE INFRA WORK | Infra - Door/Window Fixing Work | nos | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Electrical Work | nos | 0 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Excavation | cuft | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - External Plaster | sqft | 459223.8 | 189000 | 648223.8 | 76726.01 | 33182.8 | 109908.81 | 5961.75 | 15615 | 21576.75
SITE INFRA WORK | Infra - Fabrication Work | sqft | 0 | 450000 | 450000 | 0 | 1110 | 1110 | 0 | 110560 | 110560
SITE INFRA WORK | Infra - Flooring Work | sqft | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Hutment Dismantling Work | nos | 0 | 29000 | 29000 | 0 | 0 | 0 | 0 | 2500 | 2500
SITE INFRA WORK | Infra - Hutment Fabrication Work | nos | 1058000 | 120000 | 1178000 | 550160 | 62400 | 612560 | 467724.6 | 101101 | 568825.6
SITE INFRA WORK | Infra - Internal Plaster | sqft | 82463.04 | 115000 | 197463.04 | 36659.25 | 57676.6 | 94335.85 | 6391.05 | 57470 | 63861.05
SITE INFRA WORK | Infra - PCC (RMC 10) | cuft | 32150 | 706.28 | 32856.28 | 32148.43 | 706.28 | 32854.71 | 25750 | 1850 | 27600
SITE INFRA WORK | Infra - PCC (RMC 7.5) | cuft | 12328.04 | 280 | 12608.04 | 3677.37 | 83.52 | 3760.89 | 0 | 452 | 452
SITE INFRA WORK | Infra - PCC Work | cuft | 275783.1 | 48000 | 323783.1 | 246840.01 | 45616.08 | 292456.09 | 193194.03 | 80602 | 273796.03
SITE INFRA WORK | Infra - Paint Work | sqft | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Plumbing Work | nos | 0 | 12000 | 12000 | 0 | 12000 | 12000 | 0 | 33984 | 33984
SITE INFRA WORK | Infra - RCC (RMC 30) | cuft | 113973.4 | 15891.62 | 129865.02 | 86852.02 | 12110.1 | 98962.12 | 59225 | 6661 | 65886
SITE INFRA WORK | Infra - RCC (RMC 35) | cuft | 122413.26 | 14302.17 | 136715.43 | 120441.33 | 14071.8 | 134513.13 | 69525 | 11930 | 81455
SITE INFRA WORK | Infra - RCC Work | cuft | 478664.66 | 125000 | 603664.66 | 22890.13 | 6497.72 | 29387.86 | 56695.95 | 5358 | 62053.95
SITE INFRA WORK | Infra - Reinforcement Work | MT | 122018.5 | 15000 | 137018.5 | 27362.73 | 12900 | 40262.73 | 114792.06 | 10990 | 125782.06
SITE INFRA WORK | Infra - Shuttering Work | sqft | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 15000 | 15000
SITE INFRA WORK | Infra - Stone Masonry Work | cuft | 109950 | 40000 | 149950 | 100235.37 | 36465.8 | 136701.17 | 108842.67 | 57737 | 166579.67
SITE INFRA WORK | Infra -Wall Tile Work | sqft | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra-MS Gate Fixing | nos | 0 | 70000 | 70000 | 0 | 0 | 0 | 0 | 19000 | 19000
SLAB PONDING | Slab Ponding Work | sqft | 147396 | 0 | 147396 | 0 | 0 | 0 | 0 | 0 | 0
STEEL BINDING WORK | Steel Binding Work | kg | 99163686.5 | 12110000 | 111273686.5 | 3907941.9 | 491560.16 | 4399502.06 | 12527235.37 | 456449 | 12983684.37
Total |  |  | 275757881.66 | 119176498.79 | 394934380.45 | 12421014.06 | 4416426.47 | 16837440.53 | 20307666.53 | 4572720 | 24880386.53