## Theoretical Consumption
Report Type : Theoretical Consumption Report
Project Name : WTC Commercial
Generated on: 2026-06-11 16:11:56
Activity Name | Activity Unit | Total Qty | Item Group | Item Desc | Resource Coefficient | Resource Unit | Est Qty | Theoritical Qty
ATT Work - Below Footing | sqft | 9687.01 | Civil Raw Material-Chemical | Anti Termite Chemical | 10.76 | ltr | 104232.2 | 0
Below Floor PCC M7.5 | cuft | 24599 | Civil Raw Material-RMC | RMC M-7.5 | 0.028321 | cum | 696.66 | 556.01
Below Footing PCC M7.5 | cuft | 29000 | Civil Raw Material-RMC | RMC M-7.5 | 0.028321 | cum | 821.3 | 819
Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Bricks | Bricks Bat | 0.3333 | cuft | 15964.4 | 0
Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Sand | M-Sand | 0.34836 | cuft | 16685.75 | 0
Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Cement | Cement PPC | 0.038831 | bags | 1859.93 | 0
Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Chemical | Waterproofing Chemical | 0.01 | kg | 478.98 | 0
Brick Masonry 4.5" Thick | sqft | 40343 | Civil Raw Material-Bricks | Earthen Bricks | 5.855 | nos | 236208.67 | 148915.8
Brick Masonry 4.5" Thick | sqft | 40343 | Civil Raw Material-Sand | Silica Sand | 0.09684 | cuft | 3906.82 | 2155.14
Brick Masonry 4.5" Thick | sqft | 40343 | Civil Raw Material-Cement | Cement PPC | 0.016995 | bags | 685.63 | 440.64
Brick Masonry 4.5" Thick | sqft | 40343 | Civil Raw Material-Bricks | Flyash Bricks | 5.855 | nos | 236208.67 | 148915.8
Brick Masonry 4.5" Thick | sqft | 40343 | Civil Raw Material-Sand | M-Sand | 0.10746 | cuft | 4335.26 | 2391.49
Brick Masonry 9" Thick | sqft | 102392.04 | Civil Raw Material-Sand | M-Sand | 0.10506 | cuft | 10757.31 | 7576.1
Brick Masonry 9" Thick | sqft | 102392.04 | Civil Raw Material-Cement | Cement PPC | 0.023999 | bags | 2457.31 | 2016.26
Brick Masonry 9" Thick | sqft | 102392.04 | Civil Raw Material-Sand | Silica Sand | 0.10506 | cuft | 10757.31 | 7576.1
Brick Masonry 9" Thick | sqft | 102392.04 | Civil Raw Material-Bricks | Earthen Bricks | 5.25 | nos | 537558.21 | 432672.64
Brick Masonry 9" Thick | sqft | 102392.04 | Civil Raw Material-Bricks | Flyash Bricks | 10.549 | nos | 1080137.21 | 869386.45
Coupler Fixing 16mm Dia | nos | 7000 | Civil Raw Material-Coupler | Coupler 16 16 MM | 1 | nos | 7000 | 0
Coupler Fixing 20mm Dia | nos | 4600 | Civil Raw Material-Coupler | Coupler 20 20 MM | 1 | nos | 4600 | 4165
Coupler Fixing 25mm Dia | nos | 7000 | Civil Raw Material-Coupler | Coupler 25 25 MM | 1 | nos | 7000 | 5567
Coupler Fixing 25mm X 20mm Dia | nos | 3650 | Civil Raw Material-Coupler | Coupler 25 20 MM | 1 | nos | 3650 | 3586
Coupler Fixing 32mm Dia | nos | 7000 | Civil Raw Material-Coupler | Coupler 32 32 MM | 1 | nos | 7000 | 4859
Coupler Fixing 32mm X 20mm Dia | nos | 500 | Civil Raw Material-Coupler | Coupler 32 20 MM | 1 | nos | 500 | 26
Coupler Fixing 32mm X 25mm Dia | nos | 2350 | Civil Raw Material-Coupler | Coupler 32 25 MM | 1 | nos | 2350 | 2225
Coupler Fixing 40mm Dia | nos | 2200 | Civil Raw Material-Coupler | Coupler 40 40 MM | 1 | nos | 2200 | 1348
Coupler Fixing 40mm X 25mm Dia | nos | 500 | Civil Raw Material-Coupler | Coupler 40 25 MM | 1 | nos | 500 | 44
Coupler Fixing 40mm X 32mm Dia | nos | 1500 | Civil Raw Material-Coupler | Coupler 40 32 MM | 1 | nos | 1500 | 722
Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Bricks | Earthen Bricks | 28.35 | nos | 28350 | 24648.7
Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Cement | Cement PPC | 0.07004 | bags | 70.04 | 62.08
Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Sand | M-Sand | 0.6096 | cuft | 609.6 | 463.76
Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Sand | Silica Sand | 0.9696 | cuft | 969.6 | 737.64
Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Sand | Stone Dust | 0.2496 | cuft | 249.6 | 189.89
Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Sand | Silica Sand | 0.029052 | cuft | 145.26 | 26.22
Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Bricks | Earthen Bricks | 5.855 | nos | 29275.05 | 6038.19
Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Cement | Cement PPC | 0.016583 | bags | 82.92 | 17.43
Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Sand | M-Sand | 0.10506 | cuft | 525.3 | 94.8
Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Sand | Stone Dust | 0.067788 | cuft | 338.94 | 61.17
Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Bricks | Earthen Bricks | 10.549 | nos | 52745.18 | 44008.91
Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Cement | Cement PPC | 0.023999 | bags | 120 | 102.06
Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Sand | M-Sand | 0.21012 | cuft | 1050.6 | 767.01
Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Sand | Silica Sand | 0.1681 | cuft | 840.48 | 613.61
Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Sand | Stone Dust | 0.042024 | cuft | 210.12 | 153.4
Infra - External Plaster | sqft | 10000 | Civil Raw Material-Sand | M-Sand | 0.1248 | cuft | 1248 | 198.52
Infra - External Plaster | sqft | 10000 | Civil Raw Material-Cement | Cement PPC | 0.017098 | bags | 170.98 | 31.69
Infra - External Plaster | sqft | 10000 | Civil Raw Material-Sand | Silica Sand | 0.12444 | cuft | 1244.4 | 197.94
Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Cement | Cement PPC | 0.010094 | bags | 100.94 | 41.44
Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Misc | Fibre Mesh | 0.1 | mtr | 1000 | 422.91
Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Sand | Silica Sand | 0.0882 | cuft | 882 | 310.84
Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Sand | M-Sand | 0.0882 | cuft | 882 | 310.84
Infra - Labour Hutment Fabrication | nos | 150 | Site Infra Items-GI Sheet | GI Sheet 10x4 | 4 | nos | 600 | 480
Infra - Labour Hutment Fabrication | nos | 150 | Site Infra Items-GI Sheet | GI Sheet 8x4 | 5 | nos | 750 | 600
Infra - M7.5 PCC Work | cuft | 1000 | Civil Raw Material-RMC | RMC M-7.5 | 0.02831 | cum | 28.31 | 6.5
Infra - PCC Work | cuft | 5000 | Civil Raw Material-Sand | Stone Dust | 0.486 | cuft | 2430 | 1947.73
Infra - PCC Work | cuft | 5000 | Civil Raw Material-Cement | Cement PPC | 0.093318 | bags | 466.59 | 435.71
Infra - PCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 10 MM | 0.495 | cuft | 2475 | 2164.14
Infra - PCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 20 MM | 0.495 | cuft | 2475 | 2164.14
Infra - PCC Work | cuft | 5000 | Civil Raw Material-Sand | Silica Sand | 0.045 | cuft | 225 | 216.41
Infra - RCC Work | cuft | 5000 | Civil Raw Material-Sand | M-Sand | 0.455 | cuft | 2275 | 0
Infra - RCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 20 MM | 0.50864 | cuft | 2543.2 | 0
Infra - RCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 10 MM | 0.4268 | cuft | 2134 | 0
Infra - RCC Work | cuft | 5000 | Civil Raw Material-Cement | Cement PPC | 0.20085 | bags | 1004.25 | 0
Infra - RCC Work | cuft | 5000 | Civil Raw Material-Chemical | Admixture PC Based | 0.04 | kg | 200 | 0
Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 16 MM | 0.2 | MT | 5 | 1.85
Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 20 MM | 0.2 | MT | 5 | 1.85
Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 12 MM | 0.2 | MT | 5 | 1.85
Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 10 MM | 0.2 | MT | 5 | 1.85
Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 08 MM | 0.2 | MT | 5 | 1.85
Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Misc | Binding Wire | 10 | kg | 250 | 92.71
Plaster - External | sqft | 143253.07 | Civil Raw Material-Sand | M-Sand | 0.1248 | cuft | 17877.98 | 3411.04
Plaster - External | sqft | 143253.07 | Civil Raw Material-Sand | Silica Sand | 0.12444 | cuft | 17826.41 | 3401.2
Plaster - External | sqft | 143253.07 | Civil Raw Material-Cement | Cement PPC | 0.017098 | bags | 2449.34 | 544.46
Plaster - External | sqft | 143253.07 | Civil Raw Material-Misc | Fibre Mesh | 0.1 | mtr | 14325.31 | 3279.85
Plaster - External | sqft | 143253.07 | Civil Raw Material-Chemical | Waterproofing Chemical | 0.003 | kg | 429.76 | 98.4
Plaster - Internal | sqft | 376600 | Civil Raw Material-Cement | Cement PPC | 0.017098 | bags | 6439.11 | 5609.67
Plaster - Internal | sqft | 376600 | Civil Raw Material-Misc | Fibre Mesh | 0.1 | mtr | 37660 | 33793.18
Plaster - Internal | sqft | 376600 | Civil Raw Material-Sand | M-Sand | 0.04404 | cuft | 16585.46 | 12402.1
Plaster - Internal | sqft | 376600 | Civil Raw Material-Sand | Silica Sand | 0.0882 | cuft | 33216.12 | 24837.99
RCC - Column & Wall - M-25 | cuft | 18530 | Civil Raw Material-RMC | RMC M-25 | 0.028317 | cum | 524.71 | 31
RCC - Column & Wall - M-50 | cuft | 141.26 | Civil Raw Material-RMC | RMC M-50 | 0.024778 | cum | 3.5 | 3.5
RCC - Column - M45 | cuft | 335.45 | Civil Raw Material-RMC | RMC M-45 | 0.02832 | cum | 9.5 | 9.5
RCC - Column,Walls- M35 | cuft | 1695000 | Civil Raw Material-RMC | RMC M-35 | 0.028321 | cum | 48003.4 | 4775.51
RCC - Ramp - M-35 | cuft | 9646.94 | Civil Raw Material-RMC | RMC M-35 | 0.028 | cum | 270.11 | 0
RCC - Slab & beam | cuft | 746725.91 | Civil Raw Material-RMC | RMC M-35 | 0.028321 | cum | 21147.72 | 20425.5
RCC - Slab & beam M-40 | cuft | 353.15 | Civil Raw Material-RMC | RMC M-40 | 0.02832 | cum | 10 | 6.5
RCC - Stiching Slab - M25 | cuft | 11800 | Civil Raw Material-RMC | RMC M-25 | 0.028321 | cum | 334.18 | 331.5
RCC Footing - M25 | cuft | 520 | Civil Raw Material-RMC | RMC M-25 | 0.028319 | cum | 14.73 | 10.5
RCC Footing - M30 | cuft | 300600 | Civil Raw Material-RMC | RMC M-30 | 0.028321 | cum | 8513.17 | 8407.55
RCC M-15 Podium Slab | cuft | 11608 | Civil Raw Material-RMC | RMC M-15 | 0.0283 | cum | 328.51 | 171.88
RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Civil Raw Material-Sand | M-Sand | 0.432 | cuft | 556.58 | 0
RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Civil Raw Material-Cement | Cement PPC | 0.232 | bags | 298.91 | 0
RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Civil Raw Material-Grit | Grit 10 MM | 0.387 | cuft | 498.61 | 0
RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Civil Raw Material-Grit | Grit 20 MM | 0.465 | cuft | 599.1 | 0
Shuttering Work | sqft | 1181614 | Consumable Material-Nails | Nails 2 | 0.006 | kg | 7089.68 | 6968.65
Shuttering Work | sqft | 1181614 | Consumable Material-Nails | Nails 4 | 0.007 | kg | 8271.3 | 8130.09
Shuttering Work | sqft | 1181614 | Consumable Material-Nails | Nails 3 | 0.007 | kg | 8271.3 | 8130.09
Shuttering Work | sqft | 1181614 | Civil Shuttering-Ply | Shuttering Ply 8x4x12 MM | 0.00332 | nos | 3922.96 | 3855.99
Shuttering Work | sqft | 1181614 | Civil Shuttering-Ply | Old Ply Scrap All Size | 0.00332 | nos | 3922.96 | 3855.99
Shuttering Work | sqft | 1181614 | Civil Shuttering-Misc | Shuttering Tape White | 0.0001 | nos | 118.16 | 116.14
Shuttering Work | sqft | 1181614 | Civil Shuttering-Misc | Shuttering Tape Brown | 0.0012 | nos | 1417.94 | 1393.73
Shuttering Work | sqft | 1181614 | Civil Shuttering-Batten (Pine) | Batten 2x2.5x8 (Pine) | 0.02656 | nos | 31383.67 | 30847.89
Shuttering Work | sqft | 1181614 | Civil Shuttering-Batten (Mirandi) | Batten 3x2.5x10 (Mirandi) | 0.003 | nos | 3544.84 | 3484.32
Shuttering Work | sqft | 1181614 | Civil Raw Material-Misc | Shuttering Oil | 0.0035 | ltr | 4135.65 | 4065.05
Shuttering Work | sqft | 1181614 | Civil Raw Material-Cover Block | Cover Block L Shape 40 MM | 0.0678 | nos | 80113.43 | 78745.74
Shuttering Work | sqft | 1181614 | Civil Raw Material-Cover Block | Cover Block 50 MM | 0.0678 | nos | 80113.43 | 78745.74
Shuttering Work | sqft | 1181614 | Civil Raw Material-Cover Block | Cover Block 25 MM | 0.0677 | nos | 79995.27 | 78629.6
Shuttering Work | sqft | 1181614 | Civil Raw Material-Cover Block | Cover Block 20 MM | 0.07422 | nos | 87698.9 | 86201.71
Shuttering Work | sqft | 1181614 | Civil Shuttering-Batten (Pine) | Batten 2.25x1.5x8 (Pine) | 0.009 | nos | 10634.53 | 10452.98
Site Office | lumpsum | 1 | Site Infra Items-Porta Cabin | Office Container Cabin | 1 | nos | 1 | 0
Slab Ponding Work | sqft | 800000 | Civil Raw Material-Cement | Cement PPC | 0.000618 | bags | 494.4 | 0.02
Slab Ponding Work | sqft | 800000 | Civil Raw Material-Sand | Silica Sand | 0.00912 | cuft | 7296 | 0.2
Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 40 MM | 0.103 | MT | 453.72 | 431.45
Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 32 MM | 0.103 | MT | 453.72 | 431.45
Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 25 MM | 0.206 | MT | 907.43 | 862.89
Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 20 MM | 0.103 | MT | 453.72 | 431.45
Steel Binding Work | MT | 4405 | Civil Raw Material-Misc | Binding Wire | 10 | kg | 44050 | 43144.68
Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 12 MM | 0.103 | MT | 453.72 | 431.45
Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 10 MM | 0.206 | MT | 907.43 | 862.89
Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 08 MM | 0.103 | MT | 453.72 | 431.45
Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 16 MM | 0.103 | MT | 453.72 | 431.45
Toilets | lumpsum | 1 | Site Infra Items-Porta Cabin | Container Portable Toilet | 1 | nos | 1 | 0
Material Wise Theoretical Consumption Summary
Item Desc | Resource Unit | Total Theoritical Qty
Admixture PC Based | kg
Anti Termite Chemical | ltr
Batten 2.25x1.5x8 (Pine) | nos
Batten 2x2.5x8 (Pine) | nos
Batten 3x2.5x10 (Mirandi) | nos
Binding Wire | kg
Bricks Bat | cuft
Cement PPC | bags
Container Portable Toilet | nos
Coupler 16 16 MM | nos
Coupler 20 20 MM | nos
Coupler 25 20 MM | nos
Coupler 25 25 MM | nos
Coupler 32 20 MM | nos
Coupler 32 25 MM | nos
Coupler 32 32 MM | nos
Coupler 40 25 MM | nos
Coupler 40 32 MM | nos
Coupler 40 40 MM | nos
Cover Block 20 MM | nos
Cover Block 25 MM | nos
Cover Block 50 MM | nos
Cover Block L Shape 40 MM | nos
Earthen Bricks | nos
Fibre Mesh | mtr
Flyash Bricks | nos
GI Sheet 10x4 | nos
GI Sheet 8x4 | nos
Grit 10 MM | cuft
Grit 20 MM | cuft
M-Sand | cuft
Nails 2 | kg
Nails 3 | kg
Nails 4 | kg
Office Container Cabin | nos
Old Ply Scrap All Size | nos
RMC M-15 | cum
RMC M-25 | cum
RMC M-30 | cum
RMC M-35 | cum
RMC M-40 | cum
RMC M-45 | cum
RMC M-50 | cum
RMC M-7.5 | cum
Shuttering Oil | ltr
Shuttering Ply 8x4x12 MM | nos
Shuttering Tape Brown | nos
Shuttering Tape White | nos
Silica Sand | cuft
Stone Dust | cuft
TMT Steel 08 MM | MT
TMT Steel 10 MM | MT
TMT Steel 12 MM | MT
TMT Steel 16 MM | MT
TMT Steel 20 MM | MT
TMT Steel 25 MM | MT
TMT Steel 32 MM | MT
TMT Steel 40 MM | MT
Waterproofing Chemical | kg