## Sheet1
Parent WBS Name | Activity Name | Activity Unit | EST AMT - MATERIAL | EST AMT - SERVICE | EST AMT - TOTAL | THEORITICAL AMT - MATERIAL | THEORITICAL AMT - SERVICE | THEORITICAL AMT - TOTAL | ACTUAL AMT - MATERIAL | ACTUAL AMT - SERVICE | ACTUAL AMT - TOTAL
ATT Work | ATT Work - Below Footing | sqft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BACKFILLING | Earth Work - Back Filling | cuft | 0 | 230556 | 230556 | 0 | 0 | 0 | 0 | 0 | 0
BRICK BAT COBA | Brick Bat Coba Work on Terrace | sqft | 1482821.96 | 1197450 | 2680271.96 | 0 | 0 | 0 | 0 | 0 | 0
BRICK MASONRY | Brick Masonry 4.5" Thick | sqft | 991012.96 | 227652.41 | 1218665.37 | 822475.45 | 200916.03 | 1023391.48 | 292841.12 | 183537 | 476378.12
BRICK MASONRY | Brick Masonry 9" Thick | sqft | 13200660.96 | 2615824 | 15816484.96 | 5461341.93 | 1147371.58 | 6608713.5 | 2135879.93 | 1054256 | 3190135.93
CORECUTTING WORK | Corecutting Work 250 MM | nos | 0 | 48000 | 48000 | 0 | 48000 | 48000 | 0 | 24000 | 24000
EXCAVATION | Earth Work - Excavation | cuft | 0 | 11221839.56 | 11221839.56 | 0 | 715.45 | 715.45 | 0 | 11371 | 11371
EXTERNAL PLASTER | Plaster - External | sqft | 2124954.73 | 2545061.4 | 4670016.13 | 0 | 0 | 0 | 3385.55 | 0 | 3385.55
GENERAL SITE WORK | Chipping, Grinding & Welding | lumpsum | 0 | 504000 | 504000 | 0 | 89337.5 | 89337.5 | 0 | 115663 | 115663
GENERAL SITE WORK | Cleaning Work | lumpsum | 0 | 1260000 | 1260000 | 0 | 581218.75 | 581218.75 | 0 | 552858 | 552858
GENERAL SITE WORK | Curing | lumpsum | 0 | 756000 | 756000 | 0 | 394451.75 | 394451.75 | 0 | 403749 | 403749
GENERAL SITE WORK | Dismantling | lumpsum | 0 | 300300 | 300300 | 0 | 43356.25 | 43356.25 | 0 | 60881 | 60881
GENERAL SITE WORK | Electrical, Plumbing,Mechanical Work | lumpsum | 0 | 300300 | 300300 | 0 | 64093.75 | 64093.75 | 0 | 56439 | 56439
GENERAL SITE WORK | Housekeeping Work | lumpsum | 0 | 1260000 | 1260000 | 0 | 198537.5 | 198537.5 | 0 | 186928 | 186928
GENERAL SITE WORK | Lab Work | lumpsum | 0 | 238000 | 238000 | 0 | 202256.25 | 202256.25 | 0 | 210023 | 210023
GENERAL SITE WORK | Labour Supply to Client | lumpsum | 0 | 1260000 | 1260000 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORK | Labour Supply to Other Site/Godown | lumpsum | 0 | 1260000 | 1260000 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORK | Level Marking & Layout | lumpsum | 0 | 648000 | 648000 | 0 | 521673.75 | 521673.75 | 0 | 518107 | 518107
GENERAL SITE WORK | Leveling Dressing | lumpsum | 0 | 500500 | 500500 | 0 | 499887.5 | 499887.5 | 0 | 486539 | 486539
GENERAL SITE WORK | Lift Operator | lumpsum | 0 | 504000 | 504000 | 0 | 0 | 0 | 0 | 0 | 0
GENERAL SITE WORK | Material Shifting Loading Unloading | lumpsum | 0 | 2520000 | 2520000 | 0 | 1681550.5 | 1681550.5 | 0 | 1629419 | 1629419
GENERAL SITE WORK | Oiling Taping Cover Block Fixing | lumpsum | 0 | 1979250 | 1979250 | 0 | 845643.75 | 845643.75 | 0 | 853931 | 853931
GENERAL SITE WORK | Repairing | lumpsum | 0 | 648000 | 648000 | 0 | 428512.5 | 428512.5 | 0 | 422131 | 422131
GENERAL SITE WORK | Slab Ponding Work | lumpsum | 0 | 252000 | 252000 | 0 | 1750 | 1750 | 0 | 13983 | 13983
GENERAL SITE WORK | Starter Fixing | lumpsum | 0 | 648000 | 648000 | 0 | 308083.5 | 308083.5 | 0 | 276088 | 276088
GENERAL SITE WORK | Sweeper & Office boy | lumpsum | 0 | 252000 | 252000 | 0 | 124162.5 | 124162.5 | 0 | 115814 | 115814
HIRE & RENT | Machine Hire charges | lumpsum | 0 | 997500.3 | 997500.3 | 0 | 0 | 0 | 0 | 750330 | 750330
HIRE & RENT | Shuttering Rent | lumpsum | 0 | 12126180 | 12126180 | 0 | 0 | 0 | 0 | 0 | 0
HIRE & RENT | Tools and Plant Rent | lumpsum | 0 | 4320000 | 4320000 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PLASTER | Plaster - Internal | sqft | 1630748.73 | 1524256.3 | 3155005.03 | 1320518.46 | 1391249 | 2711767.46 | 923409 | 1377149 | 2300558
MS COUPLER WORK | Coupler Fixing 16mm Dia | nos | 1540000 | 210000 | 1750000 | 0 | 0 | 0 | 618.2 | 0 | 618.2
MS COUPLER WORK | Coupler Fixing 20mm Dia | nos | 880000 | 80000 | 960000 | 801460 | 72860 | 874320 | 159856.5 | 100000 | 259856.5
MS COUPLER WORK | Coupler Fixing 25mm Dia | nos | 1540000 | 210000 | 1750000 | 1007380 | 137370 | 1144750 | 343209.6 | 128975 | 472184.6
MS COUPLER WORK | Coupler Fixing 25mm X 20mm Dia | nos | 742500 | 101250 | 843750 | 592240 | 80760 | 673000 | 281200 | 78150 | 359350
MS COUPLER WORK | Coupler Fixing 32mm Dia | nos | 1540000 | 210000 | 1750000 | 1053140 | 143610 | 1196750 | 470300.8 | 120875 | 591175.8
MS COUPLER WORK | Coupler Fixing 32mm X 20mm Dia | nos | 110000 | 15000 | 125000 | 5720 | 780 | 6500 | 750 | 650 | 1400
MS COUPLER WORK | Coupler Fixing 32mm X 25mm Dia | nos | 440000 | 60000 | 500000 | 390500 | 53250 | 443750 | 282625 | 49225 | 331850
MS COUPLER WORK | Coupler Fixing 40mm Dia | nos | 484000 | 66000 | 550000 | 296560 | 40440 | 337000 | 284970 | 33700 | 318670
MS COUPLER WORK | Coupler Fixing 40mm X 25mm Dia | nos | 110000 | 15000 | 125000 | 9680 | 1320 | 11000 | 11004 | 1100 | 12104
MS COUPLER WORK | Coupler Fixing 40mm X 32mm Dia | nos | 330000 | 45000 | 375000 | 154880 | 21120 | 176000 | 226368 | 18050 | 244418
PLAIN CEMENT CONCRETE | Below Floor PCC M7.5 | cuft | 2089974 | 122995 | 2212969 | 1525500.59 | 89775.68 | 1615276.26 | 991306.86 | 59843 | 1051149.86
PLAIN CEMENT CONCRETE | Below Footing PCC M7.5 | cuft | 2463891 | 145000 | 2608891 | 2457000.95 | 144594.45 | 2601595.4 | 2486735.68 | 89574 | 2576309.68
PONDING WORK | Slab Ponding Work | sqft | 469088.74 | 0 | 469088.74 | 13.23 | 0 | 13.23 | 10450.78 | 0 | 10450.78
REINFORCED CEMENT CONCRETE | RCC - Column & Wall - M-50 | cuft | 14000 | 1854 | 15854 | 14000 | 1853.78 | 15853.78 | 18033.89 | 292 | 18325.89
REINFORCED CEMENT CONCRETE | RCC - Column - M45 | cuft | 42000 | 5296.5 | 47296.5 | 39900 | 5031.68 | 44931.68 | 21850 | 352 | 22202
REINFORCED CEMENT CONCRETE | RCC - Column,Walls- M35 | cuft | 18125176 | 2400000 | 20525176 | 17342014.52 | 2296299.5 | 19638314.02 | 10576208.62 | 322077 | 10898285.62
REINFORCED CEMENT CONCRETE | RCC - Ramp - M-35 | cuft | 1080456 | 48234.7 | 1128690.7 | 0 | 0 | 0 | 0 | 0 | 0
REINFORCED CEMENT CONCRETE | RCC - Slab & beam | cuft | 81795540 | 3610250.7 | 85405790.7 | 75100010.01 | 3314726.7 | 78414736.71 | 48127311.07 | 1324141 | 49451452.07
REINFORCED CEMENT CONCRETE | RCC - Stiching Slab - M25 | cuft | 1203058.8 | 42480 | 1245538.8 | 1193402.04 | 42139.03 | 1235541.06 | 982662.9 | 18982 | 1001644.9
REINFORCED CEMENT CONCRETE | RCC Footing - M25 | cuft | 1872000 | 1040 | 1873040 | 1334718 | 741.51 | 1335459.51 | 24937.5 | 767 | 25704.5
REINFORCED CEMENT CONCRETE | RCC Footing - M30 | cuft | 31934850.4 | 593484 | 32528334.4 | 31948692.03 | 593741.22 | 32542433.24 | 25377612.7 | 616103 | 25993715.7
REINFORCED CEMENT CONCRETE | RCC M-15 Podium Slab | cuft | 1133345.7 | 58040 | 1191385.7 | 572283.65 | 29307.3 | 601590.95 | 391500 | 10888 | 402388
REINFORCED CEMENT CONCRETE | RCC M-35 (Manual) Ledge wall | cuft | 117760 | 0 | 117760 | 0 | 0 | 0 | 10416.24 | 0 | 10416.24
Rebaring work | Rebaring work | nos | 0 | 7856100 | 7856100 | 0 | 3043782 | 3043782 | 0 | 297835 | 297835
SCAFFOLDING | Scaffolding Work | sqft | 0 | 636265 | 636265 | 0 | 158172 | 158172 | 0 | 253821 | 253821
SHUTTERING | Shuttering Work | sqft | 19708912.55 | 23634387.15 | 43343299.7 | 17913064.98 | 21480855.58 | 39393920.55 | 9155871.98 | 17540696 | 26696567.98
SITE ADMINISTRATIVE EXPENSES | Diesel | lumpsum | 0 | 350000 | 350000 | 0 | 3157 | 3157 | 0 | 279608 | 279608
SITE ADMINISTRATIVE EXPENSES | Electrical Charges | lumpsum | 0 | 3600000 | 3600000 | 0 | 300000 | 300000 | 0 | 225578 | 225578
SITE ADMINISTRATIVE EXPENSES | Installation Charges | lumpsum | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 1105663 | 1105663
SITE ADMINISTRATIVE EXPENSES | Lab Material | lumpsum | 0 | 500000 | 500000 | 0 | 304929 | 304929 | 0 | 312709 | 312709
SITE ADMINISTRATIVE EXPENSES | Machine & Vehicle Service Charges | lumpsum | 0 | 240000 | 240000 | 0 | 0 | 0 | 0 | 1570 | 1570
SITE ADMINISTRATIVE EXPENSES | Office Goods | lumpsum | 0 | 500000 | 500000 | 0 | 157210 | 157210 | 0 | 443984 | 443984
SITE ADMINISTRATIVE EXPENSES | Property Rent Charges | lumpsum | 0 | 1200000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Safety Items | lumpsum | 0 | 500000 | 500000 | 0 | 26629 | 26629 | 0 | 483727 | 483727
SITE ADMINISTRATIVE EXPENSES | Security Guard | lumpsum | 0 | 1080000 | 1080000 | 0 | 10000 | 10000 | 0 | 836400 | 836400
SITE ADMINISTRATIVE EXPENSES | Site Office | lumpsum | 1000000 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Welfare &medicne | lumpsum | 0 | 600000 | 600000 | 0 | 0 | 0 | 0 | 108376 | 108376
SITE ADMINISTRATIVE EXPENSES | Stationary | lumpsum | 0 | 240000 | 240000 | 0 | 1017 | 1017 | 0 | 24340 | 24340
SITE ADMINISTRATIVE EXPENSES | Toilets | lumpsum | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Tools and Plant Material | lumpsum | 0 | 1500000 | 1500000 | 0 | 0 | 0 | 0 | 1153844 | 1153844
SITE ADMINISTRATIVE EXPENSES | Transportation & Courier Charges | lumpsum | 0 | 120000 | 120000 | 0 | 0 | 0 | 0 | 38335 | 38335
SITE ADMINISTRATIVE EXPENSES | Travel & Conveyance | lumpsum | 0 | 240000 | 240000 | 0 | 0 | 0 | 0 | 13078 | 13078
SITE ADMINISTRATIVE EXPENSES | Water Charges | lumpsum | 0 | 70000 | 70000 | 0 | 0 | 0 | 0 | 51300 | 51300
SITE INFRA WORK | Infra - Backfilling | cuft | 0 | 24600 | 24600 | 0 | 24028.35 | 24028.35 | 0 | 24029 | 24029
SITE INFRA WORK | Infra - Brick Masonry 18" | cuft | 276948.8 | 30000 | 306948.8 | 231113.56 | 27387.45 | 258501.01 | 107428.31 | 23923 | 131351.31
SITE INFRA WORK | Infra - Brick Masonry 4.5 | sqft | 240225.99 | 100000 | 340225.99 | 48404.41 | 21657 | 70061.41 | 47851.45 | 21890 | 69741.45
SITE INFRA WORK | Infra - Brick Masonry 9 | sqft | 474328.85 | 110000 | 584328.85 | 363208.94 | 96369.55 | 459578.49 | 266032.31 | 90220 | 356252.31
SITE INFRA WORK | Infra - Door/Window Fixing Work | nos | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Electrical Work | nos | 0 | 60000 | 60000 | 0 | 15000 | 15000 | 0 | 1788 | 1788
SITE INFRA WORK | Infra - Excavation | cuft | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - External Plaster | sqft | 160686.52 | 100000 | 260686.52 | 26506.75 | 19088 | 45594.75 | 26517.29 | 17179 | 43696.29
SITE INFRA WORK | Infra - Fabrication Work | sqft | 0 | 375000 | 375000 | 0 | 183320.85 | 183320.85 | 0 | 229228 | 229228
SITE INFRA WORK | Infra - Flooring Work | sqft | 0 | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Internal Plaster | sqft | 114292.28 | 100000 | 214292.28 | 41856.19 | 42290.89 | 84147.08 | 38639.78 | 38947 | 77586.78
SITE INFRA WORK | Infra - Labour Hutment Fabrication | nos | 1545000 | 225000 | 1770000 | 1236000 | 180000 | 1416000 | 0 | 147404 | 147404
SITE INFRA WORK | Infra - M7.5 PCC Work | cuft | 2445.42 | 5000 | 7445.42 | 561.26 | 1147.58 | 1708.84 | 17221.2 | 2608 | 19829.2
SITE INFRA WORK | Infra - PCC Work | cuft | 328147.49 | 125000 | 453147.49 | 286682.31 | 120230.12 | 406912.43 | 166196.59 | 123569 | 289765.59
SITE INFRA WORK | Infra - Paint Work | sqft | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Plumbing Work | nos | 0 | 480000 | 480000 | 0 | 336000 | 336000 | 0 | 55060 | 55060
SITE INFRA WORK | Infra - RCC Work | cuft | 428450.9 | 75000 | 503450.9 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra - Reinforcement Work | MT | 1392500 | 150000 | 1542500 | 257389.7 | 27726 | 285115.7 | 0 | 171702 | 171702
SITE INFRA WORK | Infra - Shuttering Work | sqft | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
SITE INFRA WORK | Infra -Wall Tile Work | sqft | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0
STEEL BINDING | Steel Binding Work | MT | 248395130 | 30275000 | 278670130 | 230658443.88 | 28946022 | 259604465.88 | 187658744.89 | 20726214 | 208384958.89
THREADING WORK | Threading work | nos | 0 | 2413901.61 | 2413901.61 | 0 | 2093257.06 | 2093257.06 | 0 | 1407809 | 1407809
Total |  |  | 443604908.78 | 139439848.63 | 583044757.41 | 394506662.82 | 73461765.06 | 467968427.88 | 291919947.74 | 58529374 | 350449321.74