## Detailed Data
Report Type : Labour Costing Report
Project Name : WTC Commercial
Generated on: 2026-04-02 06:23:53
Parent WBS Name | Activity Name | Item Group | Item Desc | Resource Unit | Est Qty | Est Rate | Est Amt | DPR Work Qty | SRN Billed Qty | Difference Qty | Theoritical Work Amt | SRN Amt | Difference Amt | Act Rate | Balance Work Amt [Est - Th] | Percentage Work Completed [DPR/Est]*100 | Work Amt
ATT Work | ATT Work - Below Footing | Labour-Civil-Earth Work | Anti Termite Treatment | sqft | 104232.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BACKFILLING | Earth Work - Back Filling | Labour-Civil-Earth Work | Back Filling Work | cuft | 115278 | 2 | 230556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230556 | 0 | 0
BRICK BAT COBA | Brick Bat Coba Work on Terrace | Labour-Civil-Water proofing Work | Water proofing Work Brick Bat Coba | sqft | 47898 | 25 | 1197450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197450 | 0 | 0
BRICK MASONRY | Brick Masonry 4.5" Thick | Labour-Civil-Masonry Work | Masonry Work Brick 4.5" Thick | sqft | 10347.837 | 22 | 227652.41 | 9132.547 | 8996.93 | 135.617 | 200916.034 | 183537 | 17379.034 | 20.4 | 26736.376 | 88.2556 | 186303.5812
BRICK MASONRY | Brick Masonry 9" Thick | Labour-Civil-Masonry Work | Masonry Work Brick 9" Thick | sqft | 104632.96 | 25 | 2615824 | 45894.863 | 47545.78 | -1650.917 | 1147371.575 | 1054256 | 93115.575 | 22.1735 | 1468452.425 | 43.8627 | 1017649.4042
CORECUTTING WORK | Corecutting Work 250 MM | Labour-Civil-Corecutting Work | Corecutting Work | nos | 12 | 4000 | 48000 | 12 | 12 | 0 | 48000 | 24000 | 24000 | 2000 | 0 | 100 | 24000
EXCAVATION | Earth Work - Excavation | Labour-Civil-Earth Work | Excavation Work | cuft | 3740613.188 | 3 | 11221839.56 | 238.484 | 238.48 | 0.004 | 715.452 | 11371 | -10655.548 | 47.6811 | 11221124.108 | 0.0063755 | 11371.1907
EXTERNAL PLASTER | Plaster - External | Labour-Civil-Plaster Work | Plaster Work External | sqft | 127253.07 | 20 | 2545061.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2545061.4 | 0 | 0
GENERAL SITE WORK | Oiling Taping Cover Block Fixing | Labour-General Works | Oiling Taping Cover Block Fixing | lumpsum | 5655 | 350 | 1979250 | 2416.125 | 2256.76 | 159.365 | 845643.75 | 799898 | 45745.75 | 354.4453 | 1133606.25 | 42.7255 | 856384.177
GENERAL SITE WORK | Oiling Taping Cover Block Fixing | Oiling Taping Cover Block Fixing | Oiling Taping Cover Block Fixing |  | 0 | 0 | 0 | 0 | 154.38 | -154.38 | 0 | 54033 | -54033 | 350 | 0 | 0 | 0
GENERAL SITE WORK | Repairing | Labour-General Works | Repairing | lumpsum | 1440 | 450 | 648000 | 952.25 | 850.25 | 102 | 428512.5 | 379206 | 49306.5 | 445.9935 | 219487.5 | 66.1285 | 424697.3402
GENERAL SITE WORK | Repairing | Repairing | Repairing |  | 0 | 0 | 0 | 0 | 101 | -101 | 0 | 42925 | -42925 | 425 | 0 | 0 | 0
GENERAL SITE WORK | Chipping, Grinding & Welding | Labour-General Works | Chipping / Grinding & Welding | lumpsum | 1440 | 350 | 504000 | 255.25 | 252.26 | 2.99 | 89337.5 | 115663 | -26325.5 | 458.5071 | 414662.5 | 17.7257 | 117033.9362
GENERAL SITE WORK | Sweeper & Office boy | Sweeper & Office boy | Sweeper & Office boy |  | 0 | 0 | 0 | 0 | 30 | -30 | 0 | 10500 | -10500 | 350 | 0 | 0 | 0
GENERAL SITE WORK | Slab Ponding Work | Labour-General Works | Slab Ponding Work | lumpsum | 720 | 350 | 252000 | 5 | 31.13 | -26.13 | 1750 | 13983 | -12233 | 449.1809 | 250250 | 0.69444 | 2245.9043
GENERAL SITE WORK | Material Shifting Loading Unloading | Site Expenses | Material Shifting Loading Unloading | lumpsum | 7200 | 350 | 2520000 | 4804.43 | 4534.66 | 269.77 | 1681550.5 | 1571325 | 110225.5 | 346.5144 | 838449.5 | 66.7282 | 1664804.1903
GENERAL SITE WORK | Sweeper & Office boy | Labour-General Works | Sweeper & Office boy | lumpsum | 720 | 350 | 252000 | 354.75 | 316.75 | 38 | 124162.5 | 105314 | 18848.5 | 332.483 | 127837.5 | 49.2708 | 117948.3552
GENERAL SITE WORK | Material Shifting Loading Unloading | Material Shifting Loading Unloading | Material Shifting Loading Unloading |  | 0 | 0 | 0 | 0 | 178.75 | -178.75 | 0 | 58094 | -58094 | 325.0014 | 0 | 0 | 0
GENERAL SITE WORK | Starter Fixing | Labour-General Works | Starter fixing | lumpsum | 1440 | 450 | 648000 | 684.63 | 620.63 | 64 | 308083.5 | 276088 | 31995.5 | 444.8512 | 339916.5 | 47.5438 | 304558.4768
GENERAL SITE WORK | Level Marking & Layout | Labour-General Works | Level Marking & Layout | lumpsum | 1440 | 450 | 648000 | 1159.275 | 1069.01 | 90.265 | 521673.75 | 492907 | 28766.75 | 461.0874 | 126326.25 | 80.5052 | 534527.0507
GENERAL SITE WORK | Cleaning Work | Cleaning Work | Cleaning Work |  | 0 | 0 | 0 | 0 | 226 | -226 | 0 | 73450 | -73450 | 325 | 0 | 0 | 0
GENERAL SITE WORK | Cleaning Work | Labour-General Works | Cleaning Work | lumpsum | 3600 | 350 | 1260000 | 1660.625 | 1435.51 | 225.115 | 581218.75 | 479408 | 101810.75 | 333.9635 | 678781.25 | 46.1285 | 554588.2021
GENERAL SITE WORK | Curing | Curing | Curing |  | 0 | 0 | 0 | 0 | 107.13 | -107.13 | 0 | 34817 | -34817 | 324.9977 | 0 | 0 | 0
GENERAL SITE WORK | Curing | Labour-General Works | Curing | lumpsum | 2160 | 350 | 756000 | 1127.005 | 1010.52 | 116.485 | 394451.75 | 368932 | 25519.75 | 365.0912 | 361548.25 | 52.1762 | 411459.6531
GENERAL SITE WORK | Dismantling | Dismantling | Dismantling |  | 0 | 0 | 0 | 0 | 17 | -17 | 0 | 7650 | -7650 | 450 | 0 | 0 | 0
GENERAL SITE WORK | Dismantling | Labour-General Works | Dismantling | lumpsum | 858 | 350 | 300300 | 123.875 | 106.88 | 16.995 | 43356.25 | 53231 | -9874.75 | 498.0445 | 256943.75 | 14.4376 | 61695.2669
GENERAL SITE WORK | Level Marking & Layout | Level Marking & Layout | Level Marking & Layout |  | 0 | 0 | 0 | 0 | 56 | -56 | 0 | 25200 | -25200 | 450 | 0 | 0 | 0
GENERAL SITE WORK | Housekeeping Work | Housekeeping Work | Housekeeping Work |  | 0 | 0 | 0 | 0 | 127 | -127 | 0 | 41275 | -41275 | 325 | 0 | 0 | 0
GENERAL SITE WORK | Electrical, Plumbing,Mechanical Work | Labour-General Works | Electrical-Plumbing-Mechanical Work | lumpsum | 858 | 350 | 300300 | 183.125 | 153.88 | 29.245 | 64093.75 | 56439 | 7654.75 | 366.7728 | 236206.25 | 21.3432 | 67165.2708
GENERAL SITE WORK | Labour Supply to Client | Labour-General Works | Labour Supply to Client | lumpsum | 3600 | 350 | 1260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260000 | 0 | 0
GENERAL SITE WORK | Leveling Dressing | Labour-General Works | Leveling and Dressing | lumpsum | 1430 | 350 | 500500 | 1428.25 | 1346.38 | 81.87 | 499887.5 | 486539 | 13348.5 | 361.3683 | 612.5 | 99.8776 | 516124.2196
GENERAL SITE WORK | Labour Supply to Other Site/Godown | Labour-General Works | Labour Supply to Other Site/Godown | lumpsum | 3600 | 350 | 1260000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260000 | 0 | 0
GENERAL SITE WORK | Housekeeping Work | Labour-General Works | Housekeeping Work | lumpsum | 3600 | 350 | 1260000 | 567.25 | 439.69 | 127.56 | 198537.5 | 145653 | 52884.5 | 331.2629 | 1061462.5 | 15.7569 | 187908.9
GENERAL SITE WORK | Lab Work | Lab Work | Lab Work |  | 0 | 0 | 0 | 0 | 55 | -55 | 0 | 19250 | -19250 | 350 | 0 | 0 | 0
GENERAL SITE WORK | Lab Work | Labour-General Works | Lab Work | lumpsum | 680 | 350 | 238000 | 577.875 | 521.89 | 55.985 | 202256.25 | 190773 | 11483.25 | 365.5425 | 35743.75 | 84.9816 | 211237.8995
GENERAL SITE WORK | Lift Operator | Labour-General Works | Lift Operator | lumpsum | 1440 | 350 | 504000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504000 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | JCB HIRE CHARGE | hours | 644.118 | 850 | 547500.3 | 0 | 610.27 | -610.27 | 0 | 518730 | -518730 | 850.0008 | 547500.3 | 0 | 0
HIRE & RENT | Machine Hire charges | Hire & Rent | Machinery Hire Charges | lumpsum | 18 | 25000 | 450000 | 0 | 9.83 | -9.83 | 0 | 231600 | -231600 | 23560.529 | 450000 | 0 | 0
HIRE & RENT | Tools and Plant Rent | Hire & Rent | Tools Rent | lumpsum | 12 | 360000 | 4320000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4320000 | 0 | 0
HIRE & RENT | Shuttering Rent | Hire & Rent | Shuttering Rent | lumpsum | 12 | 1010515 | 12126180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12126180 | 0 | 0
INTERNAL PLASTER | Plaster - Internal | Labour-Civil-Plaster Work | Plaster Work Internal | sqft | 152425.63 | 10 | 1524256.3 | 139124.9 | 136759.57 | 2365.33 | 1391249 | 1377149 | 14100 | 10.0699 | 133007.3 | 91.274 | 1400967.5294
MS COUPLER WORK | Coupler Fixing 40mm Dia | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 40 MM | nos | 2200 | 30 | 66000 | 1348 | 1348 | 0 | 40440 | 33700 | 6740 | 25 | 25560 | 61.2727 | 33700
MS COUPLER WORK | Coupler Fixing 40mm X 32mm Dia | Labour-Civil-Coupler Fixing Work | Coupler fixing work 40mm X 32mm | nos | 1500 | 30 | 45000 | 704 | 722 | -18 | 21120 | 18050 | 3070 | 25 | 23880 | 46.9333 | 17600
MS COUPLER WORK | Coupler Fixing 40mm X 25mm Dia | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 40mm X 25mm | nos | 500 | 30 | 15000 | 44 | 44 | 0 | 1320 | 1100 | 220 | 25 | 13680 | 8.8 | 1100
MS COUPLER WORK | Coupler Fixing 32mm Dia | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 32 MM | nos | 7000 | 30 | 210000 | 4787 | 4835 | -48 | 143610 | 120875 | 22735 | 25 | 66390 | 68.3857 | 119675
MS COUPLER WORK | Coupler Fixing 32mm X 20mm Dia | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 32mm X 20mm | nos | 500 | 30 | 15000 | 26 | 26 | 0 | 780 | 650 | 130 | 25 | 14220 | 5.2 | 650
MS COUPLER WORK | Coupler Fixing 25mm Dia | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 25 MM | nos | 7000 | 30 | 210000 | 4579 | 5159 | -580 | 137370 | 128975 | 8395 | 25 | 72630 | 65.4143 | 114475
MS COUPLER WORK | Coupler Fixing 25mm X 20mm Dia | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 25mm X 20mm | nos | 3375 | 30 | 101250 | 2692 | 3126 | -434 | 80760 | 78150 | 2610 | 25 | 20490 | 79.763 | 67300
MS COUPLER WORK | Coupler Fixing 20mm Dia | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 20 MM | nos | 4000 | 20 | 80000 | 3643 | 4000 | -357 | 72860 | 100000 | -27140 | 25 | 7140 | 91.075 | 91075
MS COUPLER WORK | Coupler Fixing 16mm Dia | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 16 MM | nos | 7000 | 30 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210000 | 0 | 0
MS COUPLER WORK | Coupler Fixing 32mm X 25mm Dia | Labour-Civil-Coupler Fixing Work | Coupler Fixing work 32mm X 25mm | nos | 2000 | 30 | 60000 | 1775 | 1969 | -194 | 53250 | 49225 | 4025 | 25 | 6750 | 88.75 | 44375
PLAIN CEMENT CONCRETE | Below Footing PCC M7.5 | Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | 29000 | 5 | 145000 | 28918.89 | 28426.68 | 492.21 | 144594.45 | 89574 | 55020.45 | 3.1511 | 405.55 | 99.7203 | 91124.9802
PLAIN CEMENT CONCRETE | Below Floor PCC M7.5 | Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | 24599 | 5 | 122995 | 17955.135 | 18449.59 | -494.455 | 89775.675 | 59843 | 29932.675 | 3.2436 | 33219.325 | 72.9913 | 58239.1882
REINFORCED CEMENT CONCRETE | RCC - Column,Walls- M35 | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 160000 | 15 | 2400000 | 153086.633 | 145282.56 | 7804.073 | 2296299.495 | 322077 | 1974222.495 | 2.2169 | 103700.505 | 95.6791 | 339377.8544
REINFORCED CEMENT CONCRETE | RCC - Column - M45 | Labour-Civil-Concreting Work | Concreting Work With RMC M-45 | cuft | 353.1 | 15 | 5296.5 | 335.445 | 335.45 | -0.005 | 5031.675 | 352 | 4679.675 | 1.0493 | 264.825 | 95 | 351.9948
REINFORCED CEMENT CONCRETE | RCC - Column & Wall - M-50 | Labour-Civil-Concreting Work | Concreting Work With RMC M-50 | cuft | 123.6 | 15 | 1854 | 123.585 | 123.59 | -0.005 | 1853.775 | 292 | 1561.775 | 2.3627 | 0.225 | 99.9879 | 291.9882
REINFORCED CEMENT CONCRETE | RCC Footing - M30 | Labour-Civil-Concreting Work | Concreting Work With RMC M-30 | cuft | 300600 | 2 | 593484 | 296870.609 | 296870.61 | -0.001 | 593741.218 | 616103 | -22361.782 | 2.0753 | -257.218 | 98.7594 | 616102.9979
REINFORCED CEMENT CONCRETE | RCC - Slab & beam | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 722050.14 | 5 | 3610250.7 | 662945.34 | 670113.19 | -7167.85 | 3314726.7 | 1324141 | 1990585.7 | 1.976 | 295524 | 91.8143 | 1309977.3569
REINFORCED CEMENT CONCRETE | RCC - Stiching Slab - M25 | Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | 11800 | 3.6 | 42480 | 11705.285 | 11705.29 | -0.005 | 42139.026 | 18982 | 23157.026 | 1.6217 | 340.974 | 99.1973 | 18981.9919
REINFORCED CEMENT CONCRETE | RCC - Ramp - M-35 | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 9646.94 | 5 | 48234.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48234.7 | 0 | 0
REINFORCED CEMENT CONCRETE | RCC Footing - M25 | Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | 520 | 2 | 1040 | 370.755 | 370.76 | -0.005 | 741.51 | 767 | -25.49 | 2.0687 | 298.49 | 71.299 | 766.9897
REINFORCED CEMENT CONCRETE | RCC M-15 Podium Slab | Labour-Civil-Concreting Work | Concreting Work with RMC M-15 | cuft | 11608 | 5 | 58040 | 5861.46 | 5861.46 | -9.0949e-13 | 29307.3 | 10888 | 18419.3 | 1.8576 | 28732.7 | 50.495 | 10888
Rebaring work | Rebaring work | Labour-Civil-Rebaring Work | Rebaring Work 16mm Dia | nos | 503.1 | 600 | 301860 | 194.922 | 416 | -221.078 | 116953.2 | 24960 | 91993.2 | 60 | 184906.8 | 38.7442 | 11695.32
Rebaring work | Rebaring work | Labour-Civil-Rebaring Work | Rebaring Work 10mm Dia | nos | 8010.9 | 600 | 4806540 | 3103.758 | 4436 | -1332.242 | 1862254.8 | 155260 | 1706994.8 | 35 | 2944285.2 | 38.7442 | 108631.53
Rebaring work | Rebaring work | Labour-Civil-Rebaring Work | Rebaring Work 20mm Dia | nos | 206.4 | 600 | 123840 | 79.968 | 213 | -133.032 | 47980.8 | 23430 | 24550.8 | 110 | 75859.2 | 38.7442 | 8796.48
Rebaring work | Rebaring work | Labour-Civil-Rebaring Work | Rebaring Work 25mm Dia | nos | 154.8 | 600 | 92880 | 59.976 | 88 | -28.024 | 35985.6 | 13200 | 22785.6 | 150 | 56894.4 | 38.7442 | 8996.4
Rebaring work | Rebaring work | Labour-Civil-Rebaring Work | Rebaring Work 08mm Dia | nos | 3005.7 | 600 | 1803420 | 1164.534 | 1577 | -412.466 | 698720.4 | 39425 | 659295.4 | 25 | 1104699.6 | 38.7442 | 29113.35
Rebaring work | Rebaring work | Labour-Civil-Rebaring Work | Rebaring Work 12mm Dia | nos | 1212.6 | 600 | 727560 | 469.812 | 1039 | -569.188 | 281887.2 | 41560 | 240327.2 | 40 | 445672.8 | 38.7442 | 18792.48
SCAFFOLDING | Scaffolding Work | Labour-Civil-Scaffolding | Scaffolding | sqft | 127253 | 2.5 | 318132.5 | 31634.4 | 31633.24 | 1.16 | 79086 | 253821 | -174735 | 8.0239 | 239046.5 | 24.8595 | 253830.3077
SCAFFOLDING | Scaffolding Work | Labour-Civil-Scaffolding | De-Scaffolding | sqft | 127253 | 2.5 | 318132.5 | 31634.4 | 0 | 31634.4 | 79086 | 0 | 79086 | 0 | 239046.5 | 24.8595 | 0
SHUTTERING | Shuttering Work | Labour-Civil-Shuttering Work | Shuttering Work | sqft | 1133548.29 | 20 | 22670965.8 | 1030260.99 | 1053569.34 | -23308.35 | 20605219.8 | 16738964 | 3866255.8 | 15.8879 | 2065746 | 90.8881 | 16368644.158
SHUTTERING | Shuttering Work | Labour-Civil-Shuttering Work | Shuttering Making Work | sqft | 120427.669 | 8 | 963421.35 | 109454.472 | 67808 | 41646.472 | 875635.775 | 542464 | 333171.775 | 8 | 87785.575 | 90.8881 | 875635.776
SHUTTERING | Shuttering Work | Labour-Civil-Shuttering Work | Extra Height Shuttering Work | sqft | 566774.145 | 0 | 0 | 515130.495 | 337632.18 | 177498.315 | 0 | 259268 | -259268 | 0.7679 | 0 | 90.8881 | 395569.087
SITE ADMINISTRATIVE EXPENSES | Water Charges | Site Expenses | Water Charges | lumpsum | 70000 | 1 | 70000 | 0 | 51300 | -51300 | 0 | 51300 | -51300 | 1 | 70000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Tools and Plant Material | Site Expenses | Tools and Plant Material | Rs. | 1500000 | 1 | 1500000 | 0 | 1153844 | -1153844 | 0 | 1153844 | -1153844 | 1 | 1500000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Transportation & Courier Charges | Site Expenses | Transportation and Courier Charges | lumpsum | 120000 | 1 | 120000 | 0 | 38335 | -38335 | 0 | 38335 | -38335 | 1 | 120000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Welfare &medicne | Site Expenses | Staff Welfare and Medicines | lumpsum | 600000 | 1 | 600000 | 0 | 108376 | -108376 | 0 | 108376 | -108376 | 1 | 600000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Safety Items | Site Expenses | Safety Items | lumpsum | 500000 | 1 | 500000 | 26629 | 483727 | -457098 | 26629 | 483727 | -457098 | 1 | 473371 | 5.3258 | 26629
SITE ADMINISTRATIVE EXPENSES | Security Guard | Site Expenses | Security Guard | lumpsum | 2160 | 500 | 1080000 | 20 | 1596 | -1576 | 10000 | 836400 | -826400 | 524.0602 | 1070000 | 0.92593 | 10481.203
SITE ADMINISTRATIVE EXPENSES | Stationary | Site Expenses | STATIONARY | Rs. | 240000 | 1 | 240000 | 1017 | 24340 | -23323 | 1017 | 24340 | -23323 | 1 | 238983 | 0.42375 | 1017
SITE ADMINISTRATIVE EXPENSES | Property Rent Charges | Site Expenses | Property Rent Charges | lumpsum | 12 | 100000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Machine & Vehicle Service Charges | Site Expenses | Machine & Vehicle Service Charges | lumpsum | 240000 | 1 | 240000 | 0 | 1570 | -1570 | 0 | 1570 | -1570 | 1 | 240000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Lab Material | Site Expenses | Lab Material | lumpsum | 500000 | 1 | 500000 | 304929 | 312709 | -7780 | 304929 | 312709 | -7780 | 1 | 195071 | 60.9858 | 304929
SITE ADMINISTRATIVE EXPENSES | Installation Charges | Site Expenses | Installation Charges | lumpsum | 1500000 | 1 | 1500000 | 0 | 1105663 | -1105663 | 0 | 1105663 | -1105663 | 1 | 1500000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Electrical Charges | Site Expenses | Electricity Charges | lumpsum | 12 | 300000 | 3600000 | 1 | 10 | -9 | 300000 | 225578 | 74422 | 22557.8 | 3300000 | 8.3333 | 22557.8
SITE ADMINISTRATIVE EXPENSES | Diesel | Site Expenses | Diesel Expenses | lumpsum | 350000 | 1 | 350000 | 3157 | 279608 | -276451 | 3157 | 279608 | -276451 | 1 | 346843 | 0.902 | 3157
SITE ADMINISTRATIVE EXPENSES | Travel & Conveyance | Site Expenses | Travel & Conveyance | lumpsum | 240000 | 1 | 240000 | 0 | 13078 | -13078 | 0 | 13078 | -13078 | 1 | 240000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Office Goods | Site Expenses | Office Goods | lumpsum | 500000 | 1 | 500000 | 157210 | 443984 | -286774 | 157210 | 443984 | -286774 | 1 | 342790 | 31.442 | 157210
SITE INFRA WORK | Infra - Shuttering Work | Labour-Site Infra Work | Infra - Shuttering | sqft | 1000 | 15 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0
SITE INFRA WORK | Infra - Brick Masonry 18" | Labour-Site Infra Work | infra - Brick Masonry 18" | cuft | 1000 | 30 | 30000 | 912.915 | 912.92 | -0.005 | 27387.45 | 23923 | 3464.45 | 26.2049 | 2612.55 | 91.2915 | 23922.869
SITE INFRA WORK | Infra - Reinforcement Work | Labour-Site Infra Work | Infra - Reinforcement | MT | 25 | 6000 | 150000 | 4.621 | 9.271 | -4.65 | 27726 | 171702 | -143976 | 18520.3322 | 122274 | 18.484 | 85582.4552
SITE INFRA WORK | Infra - RCC Work | Labour-Site Infra Work | Infra - RCC Work | cuft | 5000 | 15 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0
SITE INFRA WORK | Infra - Paint Work | Labour-Site Infra Work | Infra - Paint Work | sqft | 5000 | 6 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0
SITE INFRA WORK | Infra - Plumbing Work | Labour-Site Infra Work | Infra - Plumbing Work | nos | 40 | 12000 | 480000 | 28 | 32.86 | -4.86 | 336000 | 55060 | 280940 | 1675.5934 | 144000 | 70 | 46916.6159
SITE INFRA WORK | Infra - Backfilling | Labour-Site Infra Work | Infra - Backfilling | cuft | 8200 | 3 | 24600 | 8009.45 | 8009.45 | 0 | 24028.35 | 24029 | -0.65 | 3.0001 | 571.65 | 97.6762 | 24029
SITE INFRA WORK | Infra - Labour Hutment Fabrication | Labour-Site Infra Work | Infra-Hutment Fabrication Work | nos | 150 | 1500 | 225000 | 120 | 120 | 0 | 180000 | 147404 | 32596 | 1228.3667 | 45000 | 80 | 147404
SITE INFRA WORK | Infra - Internal Plaster | Labour-Site Infra Work | Infra - Internal Plaster | sqft | 10000 | 10 | 100000 | 4229.089 | 4229.05 | 0.039 | 42290.89 | 38947 | 3343.89 | 9.2094 | 57709.11 | 42.2909 | 38947.3592
SITE INFRA WORK | Infra - Flooring Work | Labour-Site Infra Work | Infra - Flooring Work | sqft | 5000 | 18 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0
SITE INFRA WORK | Infra - PCC Work | Labour-Site Infra Work | Infra - PCC Work | cuft | 5000 | 25 | 125000 | 4809.205 | 4809.22 | -0.015 | 120230.125 | 123569 | -3338.875 | 25.6942 | 4769.875 | 96.1841 | 123568.6146
SITE INFRA WORK | Infra - M7.5 PCC Work | Labour-Site Infra Work | Infra - PCC Work (RMC) | cuft | 1000 | 5 | 5000 | 229.515 | 229.52 | -0.005 | 1147.575 | 2608 | -1460.425 | 11.3628 | 3852.425 | 22.9515 | 2607.9432
SITE INFRA WORK | Infra - Excavation | Labour-Site Infra Work | Infra - Excavation | cuft | 5000 | 4 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0
SITE INFRA WORK | Infra - External Plaster | Labour-Site Infra Work | Infra - External Plaster | sqft | 10000 | 10 | 100000 | 1908.8 | 1908.8 | 0 | 19088 | 17179 | 1909 | 8.9999 | 80912 | 19.088 | 17179
SITE INFRA WORK | Infra - Electrical Work | Labour-Site Infra Work | Infra - Electrical Work | nos | 10 | 6000 | 60000 | 2.5 | 3.75 | -1.25 | 15000 | 1788 | 13212 | 476.8 | 45000 | 25 | 1192
SITE INFRA WORK | Infra -Wall Tile Work | Labour-Site Infra Work | Infra -Wall Tile Work | sqft | 500 | 18 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0
SITE INFRA WORK | Infra - Brick Masonry 9 | Labour-Site Infra Work | Infra - Brick Masonry 9" | sqft | 5000 | 22 | 110000 | 4380.434 | 4380.44 | -0.006 | 96369.548 | 90220 | 6149.548 | 20.5961 | 13630.452 | 87.6087 | 90219.8764
SITE INFRA WORK | Infra - Brick Masonry 4.5 | Labour-Site Infra Work | Infra - Brick Masonry 4.5" | sqft | 5000 | 20 | 100000 | 1082.85 | 1082.82 | 0.03 | 21657 | 21890 | -233 | 20.2157 | 78343 | 21.657 | 21890.6065
SITE INFRA WORK | Infra - Fabrication Work | Labour-Site Infra Work | Infra - Fabrication Work | sqft | 25000 | 15 | 375000 | 12221.39 | 24029.37 | -11807.98 | 183320.85 | 229228 | -45907.15 | 9.5395 | 191679.15 | 48.8856 | 116585.8608
SITE INFRA WORK | Infra - Door/Window Fixing Work | Labour-Site Infra Work | Infra - Door/Window Fixing | nos | 150 | 500 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0
STEEL BINDING | Steel Binding Work | Labour-Civil-Reinforcement Work | Reinforcement Work Steel Binding | kg | 4325000 | 7 | 30275000 | 4135146 | 4023130.09 | 112015.91 | 28946022 | 20726214 | 8219808 | 5.1518 | 1328978 | 95.6103 | 21303293.4556
THREADING WORK | Threading work | Labour-Civil-Threading Work | Threading Work 16 MM | nos | 15053.036 | 17 | 255901.61 | 13053.504 | 44 | 13009.504 | 221909.571 | 660 | 221249.571 | 15 | 33992.039 | 86.7168 | 195802.56
THREADING WORK | Threading work | Labour-Civil-Threading Work | Threading Work 20 MM | nos | 23000.677 | 20 | 460013.54 | 19945.44 | 19909 | 36.44 | 398908.803 | 355378 | 43530.803 | 17.8501 | 61104.737 | 86.7168 | 356028.4583
THREADING WORK | Threading work | Labour-Civil-Threading Work | Threading Work 25 MM | nos | 32068.147 | 24 | 769635.53 | 27808.455 | 23641 | 4167.455 | 667402.92 | 502373 | 165029.92 | 21.2501 | 102232.61 | 86.7168 | 590931.7272
THREADING WORK | Threading work | Labour-Civil-Threading Work | Threading Work 32 MM | nos | 22224.906 | 27 | 600072.46 | 19272.716 | 15677 | 3595.716 | 520363.339 | 386438 | 133925.339 | 24.65 | 79709.121 | 86.7167 | 475072.3879
THREADING WORK | Threading work | Labour-Civil-Threading Work | Threading Work 40 MM | nos | 7816.154 | 42 | 328278.47 | 6777.915 | 4074 | 2703.915 | 284672.43 | 162960 | 121712.43 | 40 | 43606.04 | 86.7168 | 271116.6

## Summary
Report Type : Labour Costing Summary
Project Name : WTC Commercial
Generated on: 2026-04-02 06:23:53
Labour Costing Summary | Estimated Amount | Theoritical Amount | Actual Amount
Productive Labour | 92467218.33 | 65580061.523 | 45850432
Site Infra Work | 2198600 | 1094245.788 | 947547
General Site Work | 15090350 | 5984515.75 | 5902553
Hire & Rent | 17443680.3 | 0 | 750330
Site Admin Expenses | 12240000 | 802942 | 5078512