## Detailed Data
Report Type : Labour Costing Report
Project Name : Upasana Centric
Generated on: 2026-04-01 12:38:39
Parent WBS Name | Activity Name | Item Group | Item Desc | Resource Unit | Est Qty | Est Rate | Est Amt | DPR Work Qty | SRN Billed Qty | Difference Qty | Theoritical Work Amt | SRN Amt | Difference Amt | Act Rate | Balance Work Amt [Est - Th] | Percentage Work Completed [DPR/Est]*100 | Work Amt
Brick Masonary | Brick Masonry 9" - Footing | Labour-Civil-Masonry Work | Masonry Work Brick 9" Thick | sqft | 1930.9 | 20 | 38618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38618 | 0 | 0
Earth Work - Back Filiing | Earth Work - Back Filiing | Labour-Civil-Earth Work | Back Filling Work | cuft | 3000 | 2 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0
Earth Work - Excavation | Earth Work - Excavation | Labour-Civil-Earth Work | Excavation Work | cuft | 5500 | 3 | 16500 | 2173.963 | 2173.97 | -0.007 | 6521.889 | 16631 | -10109.111 | 7.6501 | 9978.111 | 39.5266 | 16630.9464
General Site Work | Leveling Dressing | Labour-General Works | Leveling and Dressing | lumpsum | 214 | 350 | 74900 | 4 | 4 | 0 | 1400 | 1600 | -200 | 400 | 73500 | 1.8692 | 1600
General Site Work | House Keeping | Labour-General Works | Housekeeping Work | lumpsum | 690 | 350 | 241500 | 102.625 | 102.64 | -0.015 | 35918.75 | 33040 | 2878.75 | 321.9018 | 205581.25 | 14.8732 | 33035.1715
General Site Work | Electrical, Plumbing,Mechanical Work | Labour-General Works | Electrical-Plumbing-Mechanical Work | lumpsum | 161 | 350 | 56350 | 76 | 69.76 | 6.24 | 26600 | 33004 | -6404 | 473.1078 | 29750 | 47.205 | 35956.1927
General Site Work | Dismantling | Labour-General Works | Dismantling | lumpsum | 115 | 350 | 40250 | 18.875 | 18.88 | -0.005 | 6606.25 | 8959 | -2352.75 | 474.5233 | 33643.75 | 16.413 | 8956.6274
General Site Work | Curing | Labour-General Works | Curing | lumpsum | 770 | 350 | 269500 | 218.875 | 218.88 | -0.005 | 76606.25 | 71612 | 4994.25 | 327.1747 | 192893.75 | 28.4253 | 71610.3641
General Site Work | Cleaning Work | Labour-General Works | Cleaning Work | lumpsum | 920 | 350 | 322000 | 237.375 | 237.39 | -0.015 | 83081.25 | 79561 | 3520.25 | 335.1489 | 238918.75 | 25.8016 | 79555.9728
General Site Work | Chipping, Grinding & Welding | Labour-General Works | Chipping / Grinding & Welding | lumpsum | 545 | 350 | 190750 | 275.875 | 345.41 | -69.535 | 96556.25 | 161061 | -64504.75 | 466.2893 | 94193.75 | 50.6193 | 128637.5709
General Site Work | Barricading Work | Labour-General Works | Barricading Work | lumpsum | 200 | 350 | 70000 | 44.875 | 44.88 | -0.005 | 15706.25 | 16829 | -1122.75 | 374.9777 | 54293.75 | 22.4375 | 16827.1251
General Site Work | Labour Hutments Fabrication Work | Labour-General Works | Labour Hutments Fabrication Work | lumpsum | 70 | 1500 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0
General Site Work | Lift Operator | Labour-General Works | Lift Operator | lumpsum | 690 | 350 | 241500 | 2 | 2 | 0 | 700 | 640 | 60 | 320 | 240800 | 0.28986 | 640
General Site Work | Labour Supply to Other Site/Godown | Labour-General Works | Labour Supply to Other Site/Godown | lumpsum | 1380 | 350 | 483000 | 91 | 91.02 | -0.02 | 31850 | 38843 | -6993 | 426.7524 | 451150 | 6.5942 | 38834.465
General Site Work | Labour Supply to Client | Labour-General Works | Labour Supply to Client | lumpsum | 345 | 350 | 120750 | 31.125 | 31.13 | -0.005 | 10893.75 | 13922 | -3028.25 | 447.2213 | 109856.25 | 9.0217 | 13919.7639
General Site Work | Lab Work | Labour-General Works | Lab Work | lumpsum | 138 | 350 | 48300 | 51.375 | 51.38 | -0.005 | 17981.25 | 18169 | -187.75 | 353.6201 | 30318.75 | 37.2283 | 18167.2319
General Site Work | Level Marking & Layout | Labour-General Works | Level Marking & Layout | lumpsum | 493 | 350 | 172550 | 81.5 | 81.52 | -0.02 | 28525 | 39795 | -11270 | 488.1624 | 144025 | 16.5314 | 39785.2368
General Site Work | Mess Caretaker | Site Expenses | Mess Caretaker | lumpsum | 690 | 350 | 241500 | 61.625 | 61.64 | -0.015 | 21568.75 | 18631 | 2937.75 | 302.255 | 219931.25 | 8.9312 | 18626.4662
General Site Work | Slab Ponding Work | Labour-General Works | Slab Ponding Work | lumpsum | 100 | 350 | 35000 | 20 | 20.01 | -0.01 | 7000 | 8456 | -1456 | 422.5887 | 28000 | 20 | 8451.7741
General Site Work | Material Shifting Loading Unloading | Site Expenses | Material Shifting Loading Unloading | lumpsum | 1840 | 350 | 644000 | 395.125 | 395.15 | -0.025 | 138293.75 | 150668 | -12374.25 | 381.2932 | 505706.25 | 21.4742 | 150658.4677
General Site Work | Sweeper & Office boy | Labour-General Works | Sweeper & Office boy | lumpsum | 820 | 350 | 287000 | 306 | 306 | 0 | 107100 | 70000 | 37100 | 228.7582 | 179900 | 37.3171 | 70000
General Site Work | Shuttering Labour (Cover block, Shuttering oil etc.) | Labour-General Works | Oiling Taping Cover Block Fixing | lumpsum | 645 | 350 | 225750 | 214.5 | 214.51 | -0.01 | 75075 | 85824 | -10749 | 400.0932 | 150675 | 33.2558 | 85819.9991
General Site Work | Labour Hutments Fabrication Work | Labour-General Works | Labour Hutment Dismentling Work | nos | 70 | 600 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 0 | 0
General Site Work | Starter fixing | Labour-General Works | Starter fixing | lumpsum | 455 | 350 | 159250 | 103.75 | 103.76 | -0.01 | 36312.5 | 42914 | -6601.5 | 413.5891 | 122937.5 | 22.8022 | 42909.8641
General Site Work | Scaffolding( Non Productive) | Labour-General Works | Scaffolding (Non Productive) | lumpsum | 100 | 350 | 35000 | 18.25 | 18.25 | 0 | 6387.5 | 6953 | -565.5 | 380.9863 | 28612.5 | 18.25 | 6953
General Site Work | Repairing | Labour-General Works | Repairing | lumpsum | 921 | 350 | 322350 | 92.875 | 92.88 | -0.005 | 32506.25 | 39829 | -7322.75 | 428.8221 | 289843.75 | 10.0841 | 39826.8559
General Site Work | Site infra Construction Work | Labour-General Works | Site Infra Construction Work | lumpsum | 200 | 350 | 70000 | 27.125 | 27.14 | -0.015 | 9493.75 | 13163 | -3669.25 | 485.0037 | 60506.25 | 13.5625 | 13155.7249
Half Brick Masonary | Brick Masonry 4.5" - Footing | Labour-Civil-Masonry Work | Masonry Work Brick 4.5" Thick | sqft | 1384.06 | 20 | 27681.2 | 109.98 | 109.99 | -0.01 | 2199.6 | 1210 | 989.6 | 11.001 | 25481.6 | 7.9462 | 1209.89
Hire & Rent | Shuttering Rent | Hire & Rent | Shuttering Material on Rent | lumpsum | 23 | 98283 | 2260509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2260509 | 0 | 0
Hire & Rent | Tools and plant Rent | Hire & Rent | Tools Rent | lumpsum | 23 | 20000 | 460000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460000 | 0 | 0
Hire & Rent | Machine Hire charges | Hire & Rent | Machinery Hire Charges | lumpsum | 23 | 3913 | 89999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89999 | 0 | 0
INJECTION GROUTING WORK | Injection Grouting Work | Labour-Civil-Grouting Work | Injection Grouting Work | nos | 200 | 145 | 29000 | 132 | 132 | 0 | 19140 | 18480 | 660 | 140 | 9860 | 66 | 18480
PLAIN CEMENT CONCRETE | PCC - Below Footing/Below Stitching Slab/STP ,Drain and Sump | Labour-Civil-Concreting Work | Concreting Work PCC | cuft | 4100 | 5 | 20500 | 184.487 | 184.49 | -0.003 | 922.435 | 5749 | -4826.565 | 31.1616 | 19577.565 | 4.4997 | 5748.9065
PLAIN CEMENT CONCRETE | PCC- Below Retaining Wall footing | Labour-Civil-Concreting Work | Concreting Work PCC | cuft | 1100 | 5 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 0
REINFORCED CEMENT CONCRETE | RCC M25 Stitching Slab | Labour-Civil-Concreting Work | Concreting Work RCC | cuft | 4943.4 | 5 | 24717 | 678.81 | 678.67 | 0.14 | 3394.05 | 21488 | -18093.95 | 31.6619 | 21322.95 | 13.7316 | 21492.4327
REINFORCED CEMENT CONCRETE | RCC M30 Footing, Ramp & Retaining wall | Labour-Civil-Concreting Work | Concreting Work RCC | cuft | 60000 | 5 | 300000 | 2239.324 | 2239.35 | -0.026 | 11196.62 | 16644 | -5447.38 | 7.4325 | 288803.38 | 3.7322 | 16643.8068
REINFORCED CEMENT CONCRETE | RCC M-35 (RMC) In Parapet Wall | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 1020.09 | 5 | 5100.45 | 114.931 | 406.12 | -291.189 | 574.657 | 3655 | -3080.343 | 8.9998 | 4525.793 | 11.2668 | 1034.3564
REINFORCED CEMENT CONCRETE | RCC M40 Column, Slab & Beam | Labour-Civil-Concreting Work | Concreting Work RCC | cuft | 145469.285 | 6.93 | 1008102.15 | 44877.859 | 44877.93 | -0.071 | 311003.563 | 100042 | 210961.563 | 2.2292 | 697098.587 | 30.8504 | 100041.8417
Rebaring work | Rebaring work | Labour-Civil-Rebaring Work | Rebaring Work 12mm Dia | nos | 4.995 | 200 | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 0 | 0
Rebaring work | Rebaring work | Labour-Civil-Rebaring Work | Rebaring Work 16mm Dia | nos | 3.992 | 200 | 798.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 798.4 | 0 | 0
Rebaring work | Rebaring work | Labour-Civil-Rebaring Work | Rebaring Work 10mm Dia | nos | 209 | 200 | 41800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0
SHUTTERING | Shuttering - Footing, Retaining wall | Labour-Civil-Shuttering Work | Shuttering Work | sqft | 29327 | 17 | 498559 | 1635.68 | 1635.68 | 0 | 27806.56 | 21264 | 6542.56 | 13.0001 | 470752.44 | 5.5774 | 21264
SHUTTERING | Shuttering - Footing, Retaining wall | Labour-Civil-Shuttering Work | Shuttering Making Work | sqft | 2584.38 | 8 | 20675.04 | 144.141 | 0 | 144.141 | 1153.127 | 0 | 1153.127 | 0 | 19521.913 | 5.5774 | 0
SHUTTERING | Shuttering - Footing, Retaining wall | Labour-Civil-Shuttering Work | Extra Height Shuttering Work | sqft | 14663.5 | 0 | 0 | 817.84 | 0 | 817.84 | 0 | 0 | 0 | 0 | 0 | 5.5774 | 0
SHUTTERING | Shuttering - Ramp, Column, Slab & Beam | Labour-Civil-Shuttering Work | Shuttering Work | sqft | 201722.88 | 17 | 3429288.96 | 54089.23 | 55484.3 | -1395.07 | 919516.91 | 1196679 | -277162.09 | 21.5679 | 2509772.05 | 26.8136 | 1166590.2907
SHUTTERING | Shuttering - Ramp, Column, Slab & Beam | Labour-Civil-Shuttering Work | Shuttering Making Work | sqft | 10880 | 8 | 87040 | 2917.323 | 800 | 2117.323 | 23338.585 | 5600 | 17738.585 | 7 | 63701.415 | 26.8136 | 20421.261
SHUTTERING | Shuttering - Ramp, Column, Slab & Beam | Labour-Civil-Shuttering Work | Extra Height Shuttering Work | sqft | 100861.44 | 0 | 0 | 27044.615 | 0 | 27044.615 | 0 | 0 | 0 | 0 | 0 | 26.8136 | 0
STEEL BINDING | Steel Binding - Footing & Retaining wall | Labour-Civil-Reinforcement Work | Reinforcement Work Steel Binding | kg | 129850 | 8 | 1038800 | 0 | 2275.47 | -2275.47 | 0 | 15246 | -15246 | 6.7002 | 1038800 | 0 | 0
STEEL BINDING | Steel Binding - Column, Slab & Beam | Labour-Civil-Reinforcement Work | Reinforcement Work Steel Binding | kg | 547290 | 8 | 4378320 | 126522 | 109630.05 | 16891.95 | 1012176 | 825904 | 186272 | 7.5336 | 3366144 | 23.1179 | 953160.4326
Scaffolding work | Scaffolding work | Labour-Civil-Scaffolding | Scaffolding | sqft | 50000 | 5 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0
Scaffolding work | Scaffolding work | Labour-Civil-Scaffolding | De-Scaffolding | sqft | 50000 | 5 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 0 | 0
Site Administrative Expenses | Office Goods | Site Expenses | Office Goods | lumpsum | 200000 | 1 | 200000 | 0 | 130446 | -130446 | 0 | 130446 | -130446 | 1 | 200000 | 0 | 0
Site Administrative Expenses | Safety Items | Site Expenses | Safety Items | lumpsum | 400000 | 1 | 400000 | 0 | 35815.5 | -35815.5 | 0 | 35817 | -35817 | 1 | 400000 | 0 | 0
Site Administrative Expenses | Machine Service Charge | Site Expenses | Machine & Vehicle Service Charges | lumpsum | 115000 | 1 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 0
Site Administrative Expenses | Installation and conveyance | Site Expenses | Installation Charges | lumpsum | 75000 | 1 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0
Site Administrative Expenses | Staff Welfare &medicne | Site Expenses | Staff Welfare and Medicines | lumpsum | 180000 | 1 | 180000 | 0 | 50966 | -50966 | 0 | 50966 | -50966 | 1 | 180000 | 0 | 0
Site Administrative Expenses | Transportation and Courier Charges | Site Expenses | Transportation and Courier Charges | lumpsum | 115000 | 1 | 115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115000 | 0 | 0
Site Administrative Expenses | Lab Material | Site Expenses | Lab Material | lumpsum | 90000 | 1 | 90000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0
Site Administrative Expenses | Tools and Plant Material | Site Expenses | Tools and Plant Material | Rs. | 120000 | 1 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 0
Site Administrative Expenses | Security Guard | Project Activities | Security Guard |  | 0 | 0 | 0 | 0 | 30 | -30 | 0 | 13500 | -13500 | 450 | 0 | 0 | 0
Site Administrative Expenses | Water | Site Expenses | Water Charges | lumpsum | 76000 | 1 | 76000 | 0 | 30930 | -30930 | 0 | 30930 | -30930 | 1 | 76000 | 0 | 0
Site Administrative Expenses | Stationary | Site Expenses | STATIONARY | Rs. | 60000 | 1 | 60000 | 0 | 3555.8 | -3555.8 | 0 | 3556 | -3556 | 1.0001 | 60000 | 0 | 0
Site Administrative Expenses | Travelling Expenses | Site Expenses | Travel & Conveyance | lumpsum | 115000 | 1 | 115000 | 0 | 8487 | -8487 | 0 | 8487 | -8487 | 1 | 115000 | 0 | 0
Site Administrative Expenses | Security Guard | Site Expenses | Security Guard | lumpsum | 770 | 650 | 500500 | 0 | 270 | -270 | 0 | 118797 | -118797 | 439.9889 | 500500 | 0 | 0
Site Infra Work | Infra - Brick Masonry 4.5 | Labour-Site Infra Work | Infra - Brick Masonry 4.5" | sqft | 1000 | 20 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0
Site Infra Work | Infra - RCC Work | Labour-Site Infra Work | Infra - RCC Work | cuft | 5000 | 20 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0
Site Infra Work | Infra -Wall Tile Work | Labour-Site Infra Work | Infra -Wall Tile Work | sqft | 1000 | 18 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0
Site Infra Work | Infra - Shuttering Work | Labour-Site Infra Work | Infra - Shuttering | sqft | 1000 | 15 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0
Site Infra Work | Infra - Brick Masonry 9 | Labour-Site Infra Work | Infra - Brick Masonry 9" | sqft | 1000 | 22 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 0
Site Infra Work | Infra - Door/Window Fixing Work | Labour-Site Infra Work | Infra - Door/Window Fixing | nos | 10 | 500 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0
Site Infra Work | Infra - Electrical Work | Labour-Site Infra Work | Infra - Electrical Work | nos | 10 | 6000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0
Site Infra Work | Infra - External Plaster | Labour-Site Infra Work | Infra - External Plaster | sqft | 1000 | 18 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0
Site Infra Work | Infra - Excavation | Labour-Site Infra Work | Infra - Excavation | cuft | 1000 | 4 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0
Site Infra Work | Infra - Fabrication Work | Labour-Site Infra Work | Infra - Fabrication Work | sqft | 3000 | 15 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 0
Site Infra Work | Infra - Flooring Work | Labour-Site Infra Work | Infra - Flooring Work | sqft | 1000 | 18 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 0 | 0
Site Infra Work | Infra - Internal Plaster | Labour-Site Infra Work | Infra - Internal Plaster | sqft | 1000 | 10 | 10000 | 156.02 | 156 | 0.02 | 1560.2 | 1920 | -359.8 | 12.3077 | 8439.8 | 15.602 | 1920.2462
Site Infra Work | Infra - PCC Work | Labour-Site Infra Work | Infra - PCC Work | cuft | 2000 | 10 | 20000 | 166.85 | 166.85 | 2.8422e-14 | 1668.5 | 4497 | -2828.5 | 26.9524 | 18331.5 | 8.3425 | 4497
Site Infra Work | Infra - Plumbing Work | Labour-Site Infra Work | Infra - Plumbing Work | nos | 10 | 10000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0
Site Infra Work | Infra - Paint Work | Labour-Site Infra Work | Infra - Paint Work | sqft | 5000 | 6 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0
Site Infra Work | Infra - Reinforcement Work | Labour-Site Infra Work | Infra - Reinforcement | MT | 10 | 6000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0
Site Infra Work | Infra - Backfilling | Labour-Site Infra Work | Infra - Backfilling | cuft | 1000 | 3 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0

## Summary
Report Type : Labour Costing Summary
Project Name : Upasana Centric
Generated on: 2026-04-01 12:38:39
Labour Costing Summary | Estimated Amount | Theoritical Amount | Actual Amount
Productive Labour | 11477999.2 | 2338943.996 | 2248592
Site Infra Work | 548000 | 3228.7 | 6417
General Site Work | 4498200 | 866162.5 | 953473
Hire & Rent | 2810508 | 0 | 0
Site Admin Expenses | 2046500 | 0 | 392499