## Detailed Data
Report Type : Labour Costing Report
Project Name : Radisson Collection Hotel
Generated on: 2026-04-07 18:23:56
Parent WBS Name | Activity Name | Total Qty | Item Group | Item Desc | Resource Unit | Est Qty | Est Rate | Est Amt | DPR Work Qty | SRN Billed Qty | Difference Qty | Theoritical Work Amt | SRN Amt | Difference Amt | Act Rate | Balance Work Amt [Est - Th] | Percentage Work Completed [DPR/Est]*100 | Work Amt
ANTI TERMITE TREATMENT | Anti Termite Treatment | 60000 | Labour-Civil-Earth Work | Anti Termite Treatment | sqft | 60000 | 12 | 720000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720000 | 0 | 0
BRICK BAT COBA | Brick Bat Coba on Terrace | 69200 | Labour-Civil-Brick Bat Coba Work | Brick Bat Coba Work | sqft | 69200 | 25 | 1730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730000 | 0 | 0
BRICK MASONRY WORK | Brick Masonry 9" | 103800 | Labour-Civil-Masonry Work | Masonry Work Brick 9" Thick | sqft | 103800 | 22 | 2283600 | 378.784 | 249.61 | 129.174 | 8333.248 | 4980 | 3353.248 | 19.9511 | 2275266.752 | 0.36492 | 7557.1665
BRICK MASONRY WORK | Brick Masonry 4.5" | 269880 | Labour-Civil-Masonry Work | Masonry Work Brick 4.5" Thick | sqft | 269880 | 20 | 5397600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5397600 | 0 | 0
EARTH WORK | Excavation | 1200000 | Labour-Civil-Earth Work | Excavation Work | cuft | 1200000 | 3 | 3600000 | 729747.669 | 729747.669 | 0 | 2189243.007 | 1342736 | 846507.007 | 1.84 | 1410756.993 | 60.8123 | 1342736
EARTH WORK | Back Filling | 22244 | Labour-Civil-Earth Work | Back Filling Work | cuft | 22244 | 3 | 66732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66732 | 0 | 0
GENERAL SITE WORKS | Barricading Work | 450 | Labour-General Works | Barricading Work | lumpsum | 450 | 350 | 157500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157500 | 0 | 0
GENERAL SITE WORKS | Slab Ponding Work | 78 | Labour-General Works | Slab Ponding Work | lumpsum | 78 | 500 | 39000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39000 | 0 | 0
GENERAL SITE WORKS | Sweeper & Office boy | 300 | Labour-General Works | Sweeper & Office boy | lumpsum | 300 | 350 | 105000 | 79 | 53 | 26 | 27650 | 18550 | 9100 | 350 | 77350 | 26.3333 | 27650
GENERAL SITE WORKS | Starter Fixing | 540 | Labour-General Works | Starter fixing | lumpsum | 540 | 525 | 283500 | 86.125 | 53.63 | 32.495 | 45215.625 | 22885 | 22330.625 | 426.7201 | 238284.375 | 15.9491 | 36751.2703
GENERAL SITE WORKS | Repairing | 600 | Labour-General Works | Repairing | lumpsum | 600 | 525 | 315000 | 92.89 | 72.76 | 20.13 | 48767.25 | 31813 | 16954.25 | 437.232 | 266232.75 | 15.4817 | 40614.4801
GENERAL SITE WORKS | Rebarring Work | 1 | Labour-General Works | Rebarring Work | lumpsum | 1 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0
GENERAL SITE WORKS | Oiling Taping Cover Block Fixing | 1620 | Labour-General Works | Oiling Taping Cover Block Fixing | lumpsum | 1620 | 400 | 648000 | 6.75 | 6.75 | 0 | 2700 | 2503 | 197 | 370.8148 | 645300 | 0.41667 | 2503
GENERAL SITE WORKS | Mess Caretaker | 450 | Site Expenses | Mess Caretaker | lumpsum | 450 | 400 | 180000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180000 | 0 | 0
GENERAL SITE WORKS | Level Marking & Layout | 1657 | Labour-General Works | Level Marking & Layout | lumpsum | 1657 | 525 | 869925 | 228.535 | 161.76 | 66.775 | 119980.875 | 70631 | 49349.875 | 436.6407 | 749944.125 | 13.7921 | 99787.6829
GENERAL SITE WORKS | Leveling Dressing | 500 | Labour-General Works | Leveling and Dressing | lumpsum | 500 | 400 | 200000 | 439.46 | 350.63 | 88.83 | 175784 | 121297 | 54487 | 345.9402 | 24216 | 87.892 | 152026.8648
GENERAL SITE WORKS | Labour Supply to Client | 50 | Labour-General Works | Labour Supply to Client | lumpsum | 50 | 0.01 | 0.5 | 9 | 9 | 0 | 0.09 | 4730 | -4729.91 | 525.5556 | 0.41 | 18 | 4730
GENERAL SITE WORKS | Labour Supply to Other Site/Godown | 600 | Labour-General Works | Labour Supply to Other Site/Godown | lumpsum | 600 | 0.01 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
GENERAL SITE WORKS | Lift Operator | 836 | Labour-General Works | Lift Operator | lumpsum | 836 | 350 | 292600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292600 | 0 | 0
GENERAL SITE WORKS | Lab Work | 675 | Labour-General Works | Lab Work | lumpsum | 675 | 500 | 337500 | 52.77 | 26.38 | 26.39 | 26385 | 12785 | 13600 | 484.6475 | 311115 | 7.8178 | 25574.8465
GENERAL SITE WORKS | Housekeeping Work | 1800 | Labour-General Works | Housekeeping Work | lumpsum | 1800 | 400 | 720000 | 67.5 | 61.25 | 6.25 | 27000 | 18609 | 8391 | 303.8204 | 693000 | 3.75 | 20507.8776
GENERAL SITE WORKS | Electrical, Plumbing,Mechanical Work | 450 | Labour-General Works | Electrical-Plumbing-Mechanical Work | lumpsum | 450 | 600 | 270000 | 29.25 | 29.26 | -0.01 | 17550 | 13092 | 4458 | 447.4368 | 252450 | 6.5 | 13087.5256
GENERAL SITE WORKS | Dismantling | 300 | Labour-General Works | Dismantling | lumpsum | 300 | 400 | 120000 | 2 | 2 | 0 | 800 | 770 | 30 | 385 | 119200 | 0.66667 | 770
GENERAL SITE WORKS | Curing | 1350 | Labour-General Works | Curing | lumpsum | 1350 | 400 | 540000 | 124.4 | 56.5 | 67.9 | 49760 | 18735 | 31025 | 331.5929 | 490240 | 9.2148 | 41250.1593
GENERAL SITE WORKS | Cleaning Work | 1800 | Labour-General Works | Cleaning Work | lumpsum | 1800 | 400 | 720000 | 8.38 | 6.5 | 1.88 | 3352 | 1622 | 1730 | 249.5385 | 716648 | 0.46556 | 2091.1323
GENERAL SITE WORKS | Chipping, Grinding & Welding | 600 | Labour-General Works | Chipping / Grinding & Welding | lumpsum | 600 | 650 | 390000 | 10 | 7.5 | 2.5 | 6500 | 2805 | 3695 | 374 | 383500 | 1.6667 | 3740
GENERAL SITE WORKS | Material Shifting Loading Unloading | 3600 | Site Expenses | Material Shifting Loading Unloading | lumpsum | 3600 | 400 | 1440000 | 208.775 | 176.63 | 32.145 | 83510 | 60837 | 22673 | 344.4319 | 1356490 | 5.7993 | 71908.7622
HIRE & RENT | Tools and Plant Rent | 8175000 | Hire & Rent | Tools Rent | lumpsum | 8175000 | 1 | 8175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8175000 | 0 | 0
HIRE & RENT | Shuttering Rent | 6920000 | Hire & Rent | Shuttering Material on Rent | lumpsum | 6920000 | 1 | 6920000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6920000 | 0 | 0
HIRE & RENT | Machine Hire charges | 533600 | Hire & Rent | JCB Hydraulic Rock Breaker (Hours) | perhour | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
HIRE & RENT | Machine Hire charges | 533600 | Hire & Rent | Transit Mixer ( TM) | per month | 18 | 110000 | 1980000 | 0 | 1.193 | -1.193 | 0 | 131230 | -131230 | 110000 | 1980000 | 0 | 0
HIRE & RENT | Machine Hire charges | 533600 | Hire & Rent | JCB & Dumper Hire Charges for Debris Removal (Per Trip) | per trip | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
HIRE & RENT | Machine Hire charges | 533600 | Hire & Rent | JCB Excavator (Poclain) Hire Charges 140 for Excavation 9 (Hours) | perhour | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
HIRE & RENT | Machine Hire charges | 533600 | Hire & Rent | JCB HIRE CHARGE | hours | 72 | 800 | 57600 | 0 | 64.28 | -64.28 | 0 | 54638 | -54638 | 850 | 57600 | 0 | 0
HIRE & RENT | Machine Hire charges | 533600 | Hire & Rent | Vehicle Hire Charges | lumpsum | 50000 | 1 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0
HIRE & RENT | Machine Hire charges | 533600 | Hire & Rent | Tractor Hire Charges (Hours) | hours | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
HIRE & RENT | Machine Hire charges | 533600 | Hire & Rent | Machinery Hire Charges | lumpsum | 30 | 1700 | 51000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51000 | 0 | 0
HIRE & RENT | Machine Hire charges | 533600 | Hire & Rent | Tractor Hire Charges (Monthly) | per month | 15 | 25000 | 375000 | 0 | 2 | -2 | 0 | 49000 | -49000 | 24500 | 375000 | 0 | 0
PLAIN CEMENT CONCRETE | PCC M-10 (Site Plant Mix) | 100000 | Labour-Civil-Concreting Work | Concreting Work PCC | cuft | 100000 | 15 | 1500000 | 8757.045 | 11262.26 | -2505.215 | 131355.675 | 79278 | 52077.675 | 7.0393 | 1368644.325 | 8.757 | 61643.135
PLAIN CEMENT CONCRETE | PCC M-10 (RMC) | 3800 | Labour-Civil-Concreting Work | Concreting Work with RMC M-10 | cuft | 3800 | 3 | 11400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11400 | 0 | 0
PLASTER WORK | Internal Plaster Work | 865000 | Labour-Civil-Plaster Work | Plaster Work Internal | sqft | 865000 | 11 | 9515000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9515000 | 0 | 0
PLASTER WORK | External Plaster Work | 346000 | Labour-Civil-Plaster Work | Plaster Work External | sqft | 346000 | 18 | 6228000 | 564 | 0 | 564 | 10152 | 0 | 10152 | 0 | 6217848 | 0.16301 | 0
REINFORCED CEMENT CONCRETE | RCC M-25 (Site Plant Mix) | 500000 | Labour-Civil-Concreting Work | Concreting Work RCC | cuft | 500000 | 3.6 | 1800000 | 32243.75 | 68118.85 | -35875.1 | 116077.5 | 250169 | -134091.5 | 3.6725 | 1683922.5 | 6.4488 | 118416.3663
REINFORCED CEMENT CONCRETE | RCC M-25 (RMC) | 19000 | Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | 19000 | 3.6 | 68400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68400 | 0 | 0
SCAFFOLDING WORK | Scaffolding Work | 346000 | Labour-Civil-Scaffolding | De-Scaffolding | sqft | 346000 | 5 | 1730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730000 | 0 | 0
SCAFFOLDING WORK | Scaffolding Work | 346000 | Labour-Civil-Scaffolding | Scaffolding | sqft | 346000 | 5 | 1730000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1730000 | 0 | 0
SHUTTERING WORK | Shuttering Making Work | 73515 | Labour-Civil-Shuttering Work | Shuttering Making Work | sqft | 73515 | 8 | 588120 | 5298.43 | 16114.43 | -10816 | 42387.44 | 128915 | -86527.56 | 8 | 545732.56 | 7.2073 | 42387.2953
SHUTTERING WORK | Shuttering Work | 692000 | Labour-Civil-Shuttering Work | Shuttering Work | sqft | 692000 | 22 | 15224000 | 14073.59 | 34261.01 | -20187.42 | 309618.98 | 572681 | -263062.02 | 16.7152 | 14914381.02 | 2.0338 | 235243.4325
SITE ADMINISTRATIVE EXPENSES | Site Office | 135000 | Site Expenses | Site Office | lumpsum | 135000 | 1 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Tools and Plant Material | 170000 | Site Expenses | Tools and Plant Material | Rs. | 170000 | 1 | 170000 | 0 | 482.02 | -482.02 | 0 | 482 | -482 | 0.99996 | 170000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Toilets | 100000 | Labour-General Works | Toilets Construction Work | lumpsum | 100000 | 1 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Transportation & Courier Charges | 150000 | Site Expenses | Transportation and Courier Charges | lumpsum | 150000 | 1 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Travel & Conveyance | 150000 | Site Expenses | Travel & Conveyance | lumpsum | 150000 | 1 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Welfare &medicne | 75000 | Site Expenses | Staff Welfare and Medicines | lumpsum | 75000 | 1 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Staff Salary | 7875000 | Site Expenses | Staff Salary | lumpsum | 7875000 | 1 | 7875000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7875000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Safety Items | 500000 | Site Expenses | Safety Items | lumpsum | 500000 | 1 | 500000 | 0 | 880 | -880 | 0 | 880 | -880 | 1 | 500000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Security Guard | 900000 | Site Expenses | Security Guard | lumpsum | 900000 | 1 | 900000 | 0 | 22415.515 | -22415.515 | 0 | 270640 | -270640 | 12.0738 | 900000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Stationary | 75000 | Site Expenses | STATIONARY | Rs. | 75000 | 1 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Property Rent Charges | 300000 | Site Expenses | Property Rent Charges | lumpsum | 300000 | 1 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Office Goods | 192300 | Site Expenses | Office Goods | lumpsum | 192300 | 1 | 192300 | 0 | 129738.36 | -129738.36 | 0 | 129738 | -129738 | 1 | 192300 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Machine & Vehicle Service Charges | 200000 | Site Expenses | Machine & Vehicle Service Charges | lumpsum | 200000 | 1 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Lab Material | 500000 | Site Expenses | Lab Material | lumpsum | 500000 | 1 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Water Charges | 75000 | Site Expenses | Water Charges | lumpsum | 75000 | 1 | 75000 | 0 | 55.22 | -55.22 | 0 | 55 | -55 | 0.99602 | 75000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Installation Charges | 200000 | Site Expenses | Installation Charges | lumpsum | 200000 | 1 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Electrical Charges | 1 | Site Expenses | Electricity Charges | lumpsum | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Diesel | 150000 | Site Expenses | Diesel Expenses | lumpsum | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SITE ADMINISTRATIVE EXPENSES | Head Office Overhead | 12715500 | Overheads | Head Office Overhead | lumpsum | 12715500 | 1 | 12715500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12715500 | 0 | 0
SITE INFRA WORK | Infra - Hutment Dismantling Work | 58 | Labour-Site Infra Work | Infra - Hutment Dismantling Work | nos | 58 | 500 | 29000 | 0 | 5 | -5 | 0 | 2500 | -2500 | 500 | 29000 | 0 | 0
SITE INFRA WORK | Infra - Flooring Work | 5000 | Labour-Site Infra Work | Infra - Flooring Work | sqft | 1 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
SITE INFRA WORK | Infra - Fabrication Work | 30000 | Labour-Site Infra Work | Infra - Fabrication Work | sqft | 30000 | 15 | 450000 | 74 | 11020 | -10946 | 1110 | 110560 | -109450 | 10.0327 | 448890 | 0.24667 | 742.4174
SITE INFRA WORK | Infra - Excavation | 5000 | Labour-Site Infra Work | Infra - Excavation | cuft | 500 | 4 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0
SITE INFRA WORK | Infra - External Plaster | 10500 | Labour-Site Infra Work | Infra - External Plaster | sqft | 10500 | 18 | 189000 | 1843.489 | 1843.49 | -0.001 | 33182.802 | 15615 | 17567.802 | 8.4703 | 155817.198 | 17.557 | 15614.9915
SITE INFRA WORK | Infra-MS Gate Fixing | 10 | Labour-Site Infra Work | Infra-MS Gate Fixing | nos | 10 | 7000 | 70000 | 0 | 3 | -3 | 0 | 19000 | -19000 | 6333.3333 | 70000 | 0 | 0
SITE INFRA WORK | Infra - Electrical Work | 1 | Labour-Site Infra Work | Infra - Electrical Work | nos | 1 | 0.01 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0
SITE INFRA WORK | Infra - Door/Window Fixing Work | 5000 | Labour-Site Infra Work | Infra - Door/Window Fixing | nos | 5 | 500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0
SITE INFRA WORK | Infra - Brick Masonry 9 (Plus) | 200 | Labour-Site Infra Work | Infra - Brick Masonry 9" Plus | cuft | 400 | 30 | 12000 | 320.25 | 320.25 | 0 | 9607.5 | 1351 | 8256.5 | 4.2186 | 2392.5 | 80.0625 | 1351
SITE INFRA WORK | Infra - Brick Masonry 9 | 10500 | Labour-Site Infra Work | Infra - Brick Masonry 9" | sqft | 10500 | 22 | 231000 | 5797.249 | 5324.19 | 473.059 | 127539.478 | 127408 | 131.478 | 23.93 | 103460.522 | 55.2119 | 138728.3137
SITE INFRA WORK | Infra - Brick Masonry 4.5 | 10000 | Labour-Site Infra Work | Infra - Brick Masonry 4.5" | sqft | 10000 | 20 | 200000 | 2538.237 | 1553.28 | 984.957 | 50764.74 | 30826 | 19938.74 | 19.8457 | 149235.26 | 25.3824 | 50373.2062
SITE INFRA WORK | Infra - Backfilling | 5000 | Labour-Site Infra Work | Infra - Backfilling | cuft | 120 | 0.01 | 1.2 | 120 | 120 | 0 | 1.2 | 1030 | -1028.8 | 8.5833 | 0 | 100 | 1030
SITE INFRA WORK | Dismantling Work (Sqft) | 3000 | Labour-Site Infra Work | Infra-Hutment Fabrication Work | nos | 3000 | 1200 | 3600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600000 | 0 | 0
SITE INFRA WORK | Infra - Paint Work | 5000 | Labour-Site Infra Work | Infra - Paint Work | sqft | 5000 | 6 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0
SITE INFRA WORK | Infra - PCC (RMC 7.5) | 140 | Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | 140 | 2 | 280 | 41.76 | 41.76 | 0 | 83.52 | 452 | -368.48 | 10.8238 | 196.48 | 29.8286 | 452
SITE INFRA WORK | Infra - Hutment Fabrication Work | 100 | Labour-Site Infra Work | Infra-Hutment Fabrication Work | nos | 100 | 1200 | 120000 | 52 | 91.91 | -39.91 | 62400 | 101101 | -38701 | 1100 | 57600 | 52 | 57200
SITE INFRA WORK | Infra - Internal Plaster | 11500 | Labour-Site Infra Work | Infra - Internal Plaster | sqft | 11500 | 10 | 115000 | 5767.66 | 5574.66 | 193 | 57676.6 | 57470 | 206.6 | 10.3091 | 57323.4 | 50.1536 | 59459.6657
SITE INFRA WORK | Infra - PCC Work | 5000 | Labour-Site Infra Work | Infra - PCC Work | cuft | 4000 | 12 | 48000 | 3801.34 | 3801.11 | 0.23 | 45616.08 | 80602 | -34985.92 | 21.2049 | 2383.92 | 95.0335 | 80606.8771
SITE INFRA WORK | Infra - PCC (RMC 10) | 353.14 | Labour-Civil-Concreting Work | Concreting Work with RMC M-10 | cuft | 353.14 | 2 | 706.28 | 353.14 | 353.14 | 0 | 706.28 | 1850 | -1143.72 | 5.2387 | 0 | 100 | 1850
SITE INFRA WORK | Infra -Wall Tile Work | 5000 | Labour-Site Infra Work | Infra -Wall Tile Work | sqft | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
SITE INFRA WORK | Infra - Stone Masonry Work | 2000 | Labour-Site Infra Work | Infra - Stone Masonry Work | cuft | 2000 | 20 | 40000 | 1823.29 | 1823.29 | 0 | 36465.8 | 57737 | -21271.2 | 31.6664 | 3534.2 | 91.1645 | 57737
SITE INFRA WORK | Infra - Shuttering Work | 1000 | Labour-Site Infra Work | Infra - Shuttering | sqft | 1000 | 0.01 | 10 | 1000 | 1000 | 0 | 10 | 15000 | -14990 | 15 | 0 | 100 | 15000
SITE INFRA WORK | Infra - Reinforcement Work | 10 | Labour-Site Infra Work | Infra - Reinforcement | MT | 2.5 | 6000 | 15000 | 2.15 | 2.198 | -0.048 | 12900 | 10990 | 1910 | 5000 | 2100 | 86 | 10750
SITE INFRA WORK | Infra - RCC Work | 5000 | Labour-Site Infra Work | Infra - RCC Work | cuft | 5000 | 25 | 125000 | 259.909 | 187.16 | 72.749 | 6497.725 | 5358 | 1139.725 | 28.6279 | 118502.275 | 5.1982 | 7440.652
SITE INFRA WORK | Infra - RCC (RMC 35) | 794.565 | Labour-Site Infra Work | Infra - RCC Work (RMC) | cuft | 953.478 | 15 | 14302.17 | 938.12 | 938.15 | -0.03 | 14071.8 | 11930 | 2141.8 | 12.7165 | 230.37 | 98.3893 | 11929.6185
SITE INFRA WORK | Infra - RCC (RMC 30) | 1059.441 | Labour-Site Infra Work | Infra - RCC Work (RMC) | cuft | 1059.441 | 15 | 15891.62 | 807.34 | 807.35 | -0.01 | 12110.1 | 6661 | 5449.1 | 8.2504 | 3781.52 | 76.2043 | 6660.9175
SITE INFRA WORK | Dismantling Work (Sqft) | 3000 | Labour-Site Infra Work | Infra-Dismantling Work (Sqft) | sqft | 3000 | 5 | 2500 | 0 | 1552 | -1552 | 0 | 7760 | -7760 | 5 | 2500 | 0 | 0
SITE INFRA WORK | Infra - Plumbing Work | 1 | Labour-Site Infra Work | Infra - Plumbing Work | nos | 1 | 12000 | 12000 | 1 | 1 | 0 | 12000 | 33984 | -21984 | 33984 | 0 | 100 | 33984
STEEL BINDING WORK | Steel Binding Work | 1730000 | Labour-Civil-Reinforcement Work | Reinforcement Work Steel Binding | kg | 1730000 | 7 | 12110000 | 70222.88 | 70222.88 | 0 | 491560.16 | 456449 | 35111.16 | 6.5 | 11618439.84 | 4.0591 | 456449

## Summary
Report Type : Labour Costing Summary
Project Name : Radisson Collection Hotel
Generated on: 2026-04-07 18:23:56
Labour Costing Summary | Estimated Amount | Theoritical Amount | Actual Amount
Productive Labour | 64302852 | 3298728.01 | 2835208
Site Infra Work | 5324210.28 | 482743.625 | 699185
General Site Work | 7628031.51 | 634954.84 | 401664
Hire & Rent | 17608604 | 0 | 234868
Site Admin Expenses | 24312801 | 0 | 401795