## Fund Report
Report Type : Fund Report | Activity Name | Activity Unit | Total Qty | Resource Type | Item Group | Item Desc | Resource Unit | Resource Coefficient | Est Qty | Est Rate | Est Amt
Project Name : WTC Commercial
Generated on: 2026-06-11 17:49:06
Productive Work
Parent WBS Name | Activity Name | Activity Unit | Total Qty | Resource Type | Item Group | Item Desc | Resource Unit | Resource Coefficient | Est Qty | Est Rate | Est Amt
ATT Work | ATT Work - Below Footing | sqft | 9687.01 | Material | Civil Raw Material-Chemical | Anti Termite Chemical | ltr | 10.76 | 104232.2 | 0 | 0
ATT Work | ATT Work - Below Footing | sqft | 9687.01 | Service | Labour-Civil-Earth Work | Anti Termite Treatment | sqft | 10.76 | 104232.2 | 0 | 0
BACKFILLING | Earth Work - Back Filling | cuft | 115278 | Service | Labour-Civil-Earth Work | Back Filling Work | cuft | 1 | 115278 | 2 | 230556
BRICK BAT COBA | Brick Bat Coba Work on Terrace | sqft | 47898 | Material | Civil Raw Material-Bricks | Bricks Bat | cuft | 0.3333 | 15964.4 | 25 | 399110.08
BRICK BAT COBA | Brick Bat Coba Work on Terrace | sqft | 47898 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.038831 | 1859.93 | 210.94 | 392333
BRICK BAT COBA | Brick Bat Coba Work on Terrace | sqft | 47898 | Material | Civil Raw Material-Chemical | Waterproofing Chemical | kg | 0.01 | 478.98 | 50 | 23949
BRICK BAT COBA | Brick Bat Coba Work on Terrace | sqft | 47898 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.34836 | 16685.75 | 40 | 667429.88
BRICK BAT COBA | Brick Bat Coba Work on Terrace | sqft | 47898 | Service | Labour-Civil-Water proofing Work | Water proofing Work Brick Bat Coba | sqft | 1 | 47898 | 25 | 1197450
BRICK MASONRY | Brick Masonry 4.5" Thick | sqft | 40343 | Material | Civil Raw Material-Bricks | Earthen Bricks | nos | 5.855 | 236208.67 | 7 | 1653460.68
BRICK MASONRY | Brick Masonry 4.5" Thick | sqft | 40343 | Material | Civil Raw Material-Bricks | Flyash Bricks | nos | 5.855 | 236208.67 | 7 | 1653460.68
BRICK MASONRY | Brick Masonry 4.5" Thick | sqft | 40343 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.016995 | 685.63 | 210.94 | 144626.58
BRICK MASONRY | Brick Masonry 4.5" Thick | sqft | 40343 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.10746 | 4335.26 | 50 | 216762.95
BRICK MASONRY | Brick Masonry 4.5" Thick | sqft | 40343 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.09684 | 3906.82 | 50 | 195340.8
BRICK MASONRY | Brick Masonry 4.5" Thick | sqft | 40343 | Service | Labour-Civil-Masonry Work | Masonry Work Brick 4.5" Thick | sqft | 1 | 40343 | 22 | 887546
BRICK MASONRY | Brick Masonry 9" Thick | sqft | 102392.04 | Material | Civil Raw Material-Bricks | Earthen Bricks | nos | 5.25 | 537558.21 | 7 | 3762907.47
BRICK MASONRY | Brick Masonry 9" Thick | sqft | 102392.04 | Material | Civil Raw Material-Bricks | Flyash Bricks | nos | 10.549 | 1080137.21 | 7 | 7560960.5
BRICK MASONRY | Brick Masonry 9" Thick | sqft | 102392.04 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.023999 | 2457.31 | 210.94 | 518344.34
BRICK MASONRY | Brick Masonry 9" Thick | sqft | 102392.04 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.10506 | 10757.31 | 50 | 537865.4
BRICK MASONRY | Brick Masonry 9" Thick | sqft | 102392.04 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.10506 | 10757.31 | 50 | 537865.4
BRICK MASONRY | Brick Masonry 9" Thick | sqft | 102392.04 | Service | Labour-Civil-Masonry Work | Masonry Work Brick 9" Thick | sqft | 1 | 102392.04 | 25 | 2559801
CORECUTTING WORK | Corecutting Work 250 MM | nos | 12 | Service | Labour-Civil-Corecutting Work | Corecutting Work | nos | 1 | 12 | 4000 | 48000
EXCAVATION | Earth Work - Excavation | cuft | 3740613.19 | Service | Labour-Civil-Earth Work | Excavation Work | cuft | 1 | 3740613.19 | 3 | 11221839.56
EXTERNAL PLASTER | Plaster - External | sqft | 143253.07 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.017098 | 2449.34 | 210.94 | 516663.99
EXTERNAL PLASTER | Plaster - External | sqft | 143253.07 | Material | Civil Raw Material-Chemical | Waterproofing Chemical | kg | 0.003 | 429.76 | 50 | 21487.95
EXTERNAL PLASTER | Plaster - External | sqft | 143253.07 | Material | Civil Raw Material-Misc | Fibre Mesh | mtr | 0.1 | 14325.31 | 4.8 | 68761.47
EXTERNAL PLASTER | Plaster - External | sqft | 143253.07 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.1248 | 17877.98 | 50 | 893899.15
EXTERNAL PLASTER | Plaster - External | sqft | 143253.07 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.12444 | 17826.41 | 50 | 891320.6
EXTERNAL PLASTER | Plaster - External | sqft | 143253.07 | Service | Labour-Civil-Plaster Work | Plaster Work External | sqft | 1 | 143253.07 | 20 | 2865061.4
HIRE & RENT | Machine Hire charges | lumpsum | 218 |  | Machine Hire charges | Machine Hire charges |  | 0 | 0 | 0 | 0
INTERNAL PLASTER | Plaster - Internal | sqft | 376600 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.017098 | 6439.11 | 210.94 | 1358265.23
INTERNAL PLASTER | Plaster - Internal | sqft | 376600 | Material | Civil Raw Material-Misc | Fibre Mesh | mtr | 0.1 | 37660 | 4.8 | 180768
INTERNAL PLASTER | Plaster - Internal | sqft | 376600 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.04404 | 16585.46 | 50 | 829273.2
INTERNAL PLASTER | Plaster - Internal | sqft | 376600 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.0882 | 33216.12 | 50 | 1660806
INTERNAL PLASTER | Plaster - Internal | sqft | 376600 | Service | Labour-Civil-Plaster Work | Plaster Work Internal | sqft | 1 | 376600 | 10 | 3766000
INTERNAL PLASTER | Plaster - Internal | sqft | 376600 |  | Labour Charges for Supply to Company | Skilled Labour |  | 0 | 0 | 0 | 0
MS COUPLER WORK | Coupler Fixing 16mm Dia | nos | 7000 | Material | Civil Raw Material-Coupler | Coupler 16 16 MM | nos | 1 | 7000 | 220 | 1540000
MS COUPLER WORK | Coupler Fixing 16mm Dia | nos | 7000 | Service | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 16 MM | nos | 1 | 7000 | 30 | 210000
MS COUPLER WORK | Coupler Fixing 20mm Dia | nos | 4600 | Material | Civil Raw Material-Coupler | Coupler 20 20 MM | nos | 1 | 4600 | 220 | 1012000
MS COUPLER WORK | Coupler Fixing 20mm Dia | nos | 4600 | Service | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 20 MM | nos | 1 | 4600 | 20 | 92000
MS COUPLER WORK | Coupler Fixing 25mm Dia | nos | 7000 | Material | Civil Raw Material-Coupler | Coupler 25 25 MM | nos | 1 | 7000 | 220 | 1540000
MS COUPLER WORK | Coupler Fixing 25mm Dia | nos | 7000 | Service | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 25 MM | nos | 1 | 7000 | 30 | 210000
MS COUPLER WORK | Coupler Fixing 25mm X 20mm Dia | nos | 3650 | Material | Civil Raw Material-Coupler | Coupler 25 20 MM | nos | 1 | 3650 | 220 | 803000
MS COUPLER WORK | Coupler Fixing 25mm X 20mm Dia | nos | 3650 | Service | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 25mm X 20mm | nos | 1 | 3650 | 30 | 109500
MS COUPLER WORK | Coupler Fixing 32mm Dia | nos | 7000 | Material | Civil Raw Material-Coupler | Coupler 32 32 MM | nos | 1 | 7000 | 220 | 1540000
MS COUPLER WORK | Coupler Fixing 32mm Dia | nos | 7000 | Service | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 32 MM | nos | 1 | 7000 | 30 | 210000
MS COUPLER WORK | Coupler Fixing 32mm X 20mm Dia | nos | 500 | Material | Civil Raw Material-Coupler | Coupler 32 20 MM | nos | 1 | 500 | 220 | 110000
MS COUPLER WORK | Coupler Fixing 32mm X 20mm Dia | nos | 500 | Service | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 32mm X 20mm | nos | 1 | 500 | 30 | 15000
MS COUPLER WORK | Coupler Fixing 32mm X 25mm Dia | nos | 2350 | Material | Civil Raw Material-Coupler | Coupler 32 25 MM | nos | 1 | 2350 | 220 | 517000
MS COUPLER WORK | Coupler Fixing 32mm X 25mm Dia | nos | 2350 | Service | Labour-Civil-Coupler Fixing Work | Coupler Fixing work 32mm X 25mm | nos | 1 | 2350 | 30 | 70500
MS COUPLER WORK | Coupler Fixing 40mm Dia | nos | 2200 | Material | Civil Raw Material-Coupler | Coupler 40 40 MM | nos | 1 | 2200 | 220 | 484000
MS COUPLER WORK | Coupler Fixing 40mm Dia | nos | 2200 | Service | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 40 MM | nos | 1 | 2200 | 30 | 66000
MS COUPLER WORK | Coupler Fixing 40mm X 25mm Dia | nos | 500 | Material | Civil Raw Material-Coupler | Coupler 40 25 MM | nos | 1 | 500 | 220 | 110000
MS COUPLER WORK | Coupler Fixing 40mm X 25mm Dia | nos | 500 | Service | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 40mm X 25mm | nos | 1 | 500 | 30 | 15000
MS COUPLER WORK | Coupler Fixing 40mm X 32mm Dia | nos | 1500 | Material | Civil Raw Material-Coupler | Coupler 40 32 MM | nos | 1 | 1500 | 220 | 330000
MS COUPLER WORK | Coupler Fixing 40mm X 32mm Dia | nos | 1500 | Service | Labour-Civil-Coupler Fixing Work | Coupler fixing work 40mm X 32mm | nos | 1 | 1500 | 30 | 45000
PLAIN CEMENT CONCRETE | Below Floor PCC M7.5 | cuft | 24599 | Material | Civil Raw Material-RMC | RMC M-7.5 | cum | 0.028321 | 696.66 | 3000 | 2089974
PLAIN CEMENT CONCRETE | Below Floor PCC M7.5 | cuft | 24599 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | 1 | 24599 | 5 | 122995
PLAIN CEMENT CONCRETE | Below Footing PCC M7.5 | cuft | 29000 | Material | Civil Raw Material-RMC | RMC M-7.5 | cum | 0.028321 | 821.3 | 3000 | 2463891
PLAIN CEMENT CONCRETE | Below Footing PCC M7.5 | cuft | 29000 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | 1 | 29000 | 5 | 145000
PONDING WORK | Slab Ponding Work | sqft | 800000 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.000618 | 494.4 | 210.94 | 104288.74
PONDING WORK | Slab Ponding Work | sqft | 800000 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.00912 | 7296 | 50 | 364800
REINFORCED CEMENT CONCRETE | RCC - Column & Wall - M-25 | cuft | 18530 | Material | Civil Raw Material-RMC | RMC M-25 | cum | 0.028317 | 524.71 | 3600 | 1888959.6
REINFORCED CEMENT CONCRETE | RCC - Column & Wall - M-25 | cuft | 18530 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | 1 | 18530 | 15 | 277950
REINFORCED CEMENT CONCRETE | RCC - Column & Wall - M-50 | cuft | 141.26 | Material | Civil Raw Material-RMC | RMC M-50 | cum | 0.024778 | 3.5 | 4000 | 14000
REINFORCED CEMENT CONCRETE | RCC - Column & Wall - M-50 | cuft | 141.26 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-50 | cuft | 0.87501 | 123.6 | 15 | 1854
REINFORCED CEMENT CONCRETE | RCC - Column - M45 | cuft | 335.45 | Material | Civil Raw Material-RMC | RMC M-45 | cum | 0.02832 | 9.5 | 4200 | 39900
REINFORCED CEMENT CONCRETE | RCC - Column - M45 | cuft | 335.45 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-45 | cuft | 1 | 335.45 | 15 | 5031.75
REINFORCED CEMENT CONCRETE | RCC - Column,Walls- M35 | cuft | 1695000 | Material | Civil Raw Material-RMC | RMC M-35 | cum | 0.028321 | 48003.4 | 4000 | 192013596
REINFORCED CEMENT CONCRETE | RCC - Column,Walls- M35 | cuft | 1695000 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 1 | 1695000 | 15 | 25425000
REINFORCED CEMENT CONCRETE | RCC - Ramp - M-35 | cuft | 9646.94 | Material | Civil Raw Material-RMC | RMC M-35 | cum | 0.028 | 270.11 | 4000 | 1080456
REINFORCED CEMENT CONCRETE | RCC - Ramp - M-35 | cuft | 9646.94 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 1 | 9646.94 | 5 | 48234.7
REINFORCED CEMENT CONCRETE | RCC - Slab & beam | cuft | 746725.91 | Material | Civil Raw Material-RMC | RMC M-35 | cum | 0.028321 | 21147.72 | 4000 | 84590872
REINFORCED CEMENT CONCRETE | RCC - Slab & beam | cuft | 746725.91 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 1 | 746725.91 | 5 | 3733629.55
REINFORCED CEMENT CONCRETE | RCC - Slab & beam M-40 | cuft | 353.15 | Material | Civil Raw Material-RMC | RMC M-40 | cum | 0.02832 | 10 | 4200 | 42004.2
REINFORCED CEMENT CONCRETE | RCC - Slab & beam M-40 | cuft | 353.15 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-40 | cuft | 1 | 353.15 | 5 | 1765.74
REINFORCED CEMENT CONCRETE | RCC - Stiching Slab - M25 | cuft | 11800 | Material | Civil Raw Material-RMC | RMC M-25 | cum | 0.028321 | 334.18 | 3600 | 1203058.8
REINFORCED CEMENT CONCRETE | RCC - Stiching Slab - M25 | cuft | 11800 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | 1 | 11800 | 3.6 | 42480
REINFORCED CEMENT CONCRETE | RCC Footing - M25 | cuft | 520 | Material | Civil Raw Material-RMC | RMC M-25 | cum | 0.028319 | 14.73 | 3600 | 53013.6
REINFORCED CEMENT CONCRETE | RCC Footing - M25 | cuft | 520 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | 1 | 520 | 2 | 1040
REINFORCED CEMENT CONCRETE | RCC Footing - M30 | cuft | 300600 | Material | Civil Raw Material-RMC | RMC M-30 | cum | 0.028321 | 8513.17 | 3800 | 31934850.4
REINFORCED CEMENT CONCRETE | RCC Footing - M30 | cuft | 300600 | Service | Labour-Civil-Concreting Work | Concreting Work With RMC M-30 | cuft | 1 | 300600 | 2 | 593484
REINFORCED CEMENT CONCRETE | RCC M-15 Podium Slab | cuft | 11608 | Material | Civil Raw Material-RMC | RMC M-15 | cum | 0.0283 | 328.51 | 3450 | 1133345.7
REINFORCED CEMENT CONCRETE | RCC M-15 Podium Slab | cuft | 11608 | Service | Labour-Civil-Concreting Work | Concreting Work with RMC M-15 | cuft | 1 | 11608 | 5 | 58040
REINFORCED CEMENT CONCRETE | RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.232 | 298.91 | 225 | 67253.85
REINFORCED CEMENT CONCRETE | RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Material | Civil Raw Material-Grit | Grit 10 MM | cuft | 0.387 | 498.61 | 23 | 11467.96
REINFORCED CEMENT CONCRETE | RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Material | Civil Raw Material-Grit | Grit 20 MM | cuft | 0.465 | 599.1 | 28 | 16774.83
REINFORCED CEMENT CONCRETE | RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.432 | 556.58 | 40 | 22263.36
Rebaring work | Rebaring work | nos | 12900 | Service | Labour-Civil-Rebaring Work | Rebaring Work 08mm Dia | nos | 0.233 | 3005.7 | 600 | 1803420
Rebaring work | Rebaring work | nos | 12900 | Service | Labour-Civil-Rebaring Work | Rebaring Work 10mm Dia | nos | 0.621 | 8010.9 | 600 | 4806540
Rebaring work | Rebaring work | nos | 12900 | Service | Labour-Civil-Rebaring Work | Rebaring Work 12mm Dia | nos | 0.094 | 1212.6 | 600 | 727560
Rebaring work | Rebaring work | nos | 12900 | Service | Labour-Civil-Rebaring Work | Rebaring Work 16mm Dia | nos | 0.039 | 503.1 | 600 | 301860
Rebaring work | Rebaring work | nos | 12900 | Service | Labour-Civil-Rebaring Work | Rebaring Work 20mm Dia | nos | 0.016 | 206.4 | 600 | 123840
Rebaring work | Rebaring work | nos | 12900 | Service | Labour-Civil-Rebaring Work | Rebaring Work 25mm Dia | nos | 0.012 | 154.8 | 600 | 92880
SCAFFOLDING | Scaffolding Work | sqft | 127253 | Service | Labour-Civil-Scaffolding | De-Scaffolding | sqft | 1 | 127253 | 2.5 | 318132.5
SCAFFOLDING | Scaffolding Work | sqft | 127253 | Service | Labour-Civil-Scaffolding | Scaffolding | sqft | 1 | 127253 | 2.5 | 318132.5
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Raw Material-Cover Block | Cover Block 20 MM | nos | 0.07422 | 87698.9 | 1 | 87698.9
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Raw Material-Cover Block | Cover Block 25 MM | nos | 0.0677 | 79995.27 | 1 | 79995.27
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Raw Material-Cover Block | Cover Block 50 MM | nos | 0.0678 | 80113.43 | 1 | 80113.43
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Raw Material-Cover Block | Cover Block L Shape 40 MM | nos | 0.0678 | 80113.43 | 1 | 80113.43
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Raw Material-Misc | Shuttering Oil | ltr | 0.0035 | 4135.65 | 65 | 268817.19
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Shuttering-Batten (Mirandi) | Batten 3x2.5x10 (Mirandi) | nos | 0.003 | 3544.84 | 650 | 2304147.3
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Shuttering-Batten (Pine) | Batten 2.25x1.5x8 (Pine) | nos | 0.009 | 10634.53 | 150 | 1595178.9
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Shuttering-Batten (Pine) | Batten 2x2.5x8 (Pine) | nos | 0.02656 | 31383.67 | 200 | 6276733.6
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Shuttering-Misc | Shuttering Tape Brown | nos | 0.0012 | 1417.94 | 75 | 106345.28
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Shuttering-Misc | Shuttering Tape White | nos | 0.0001 | 118.16 | 75 | 8862.08
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Shuttering-Ply | Old Ply Scrap All Size | nos | 0.00332 | 3922.96 | 70 | 274607.06
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Civil Shuttering-Ply | Shuttering Ply 8x4x12 MM | nos | 0.00332 | 3922.96 | 2000 | 7845916
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Consumable Material-Nails | Nails 2 | kg | 0.006 | 7089.68 | 65 | 460829.46
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Consumable Material-Nails | Nails 3 | kg | 0.007 | 8271.3 | 65 | 537634.37
SHUTTERING | Shuttering Work | sqft | 1181614 | Material | Consumable Material-Nails | Nails 4 | kg | 0.007 | 8271.3 | 65 | 537634.37
SHUTTERING | Shuttering Work | sqft | 1181614 | Service | Labour-Civil-Shuttering Work | Extra Height Shuttering Work | sqft | 0.5 | 590807 | 0 | 0
SHUTTERING | Shuttering Work | sqft | 1181614 | Service | Labour-Civil-Shuttering Work | Shuttering Making Work | sqft | 0.10624 | 125534.15 | 8 | 1004273.19
SHUTTERING | Shuttering Work | sqft | 1181614 | Service | Labour-Civil-Shuttering Work | Shuttering Work | sqft | 1 | 1181614 | 20 | 23632280
SITE ADMINISTRATIVE EXPENSES | Site Office | lumpsum | 1 | Material | Site Infra Items-Porta Cabin | Office Container Cabin | nos | 1 | 1 | 1000000 | 1000000
SITE ADMINISTRATIVE EXPENSES | Toilets | lumpsum | 1 | Material | Site Infra Items-Porta Cabin | Container Portable Toilet | nos | 1 | 1 | 50000 | 50000
STEEL BINDING | Steel Binding Work | MT | 4405 | Material | Civil Raw Material-Misc | Binding Wire | kg | 10 | 44050 | 70 | 3083500
STEEL BINDING | Steel Binding Work | MT | 4405 | Material | Civil Raw Material-Steel | TMT Steel 08 MM | MT | 0.103 | 453.72 | 55080 | 24990622.2
STEEL BINDING | Steel Binding Work | MT | 4405 | Material | Civil Raw Material-Steel | TMT Steel 10 MM | MT | 0.206 | 907.43 | 55080 | 49981244.4
STEEL BINDING | Steel Binding Work | MT | 4405 | Material | Civil Raw Material-Steel | TMT Steel 12 MM | MT | 0.103 | 453.72 | 55080 | 24990622.2
STEEL BINDING | Steel Binding Work | MT | 4405 | Material | Civil Raw Material-Steel | TMT Steel 16 MM | MT | 0.103 | 453.72 | 55080 | 24990622.2
STEEL BINDING | Steel Binding Work | MT | 4405 | Material | Civil Raw Material-Steel | TMT Steel 20 MM | MT | 0.103 | 453.72 | 55080 | 24990622.2
STEEL BINDING | Steel Binding Work | MT | 4405 | Material | Civil Raw Material-Steel | TMT Steel 25 MM | MT | 0.206 | 907.43 | 55080 | 49981244.4
STEEL BINDING | Steel Binding Work | MT | 4405 | Material | Civil Raw Material-Steel | TMT Steel 32 MM | MT | 0.103 | 453.72 | 55080 | 24990622.2
STEEL BINDING | Steel Binding Work | MT | 4405 | Material | Civil Raw Material-Steel | TMT Steel 40 MM | MT | 0.103 | 453.72 | 55080 | 24990622.2
STEEL BINDING | Steel Binding Work | MT | 4405 | Service | Labour-Civil-Reinforcement Work | Reinforcement Work Steel Binding | kg | 1000 | 4405000 | 7 | 30835000
THREADING WORK | Threading work | nos | 73048.17 | Service | Labour-Civil-Threading Work | Threading Work 16 MM | nos | 0.20607 | 15053.04 | 17 | 255901.61
THREADING WORK | Threading work | nos | 73048.17 | Service | Labour-Civil-Threading Work | Threading Work 20 MM | nos | 0.31487 | 23000.68 | 20 | 460013.54
THREADING WORK | Threading work | nos | 73048.17 | Service | Labour-Civil-Threading Work | Threading Work 25 MM | nos | 0.439 | 32068.15 | 24 | 769635.53
THREADING WORK | Threading work | nos | 73048.17 | Service | Labour-Civil-Threading Work | Threading Work 32 MM | nos | 0.30425 | 22224.91 | 27 | 600072.46
THREADING WORK | Threading work | nos | 73048.17 | Service | Labour-Civil-Threading Work | Threading Work 40 MM | nos | 0.107 | 7816.15 | 42 | 328278.47
Site Infra Work
Parent WBS Name | Activity Name | Activity Unit | Total Qty | Resource Type | Item Group | Item Desc | Resource Unit | Resource Coefficient | Est Qty | Est Rate | Est Amt
SITE INFRA WORK | Infra - Backfilling | cuft | 8200 | Service | Labour-Site Infra Work | Infra - Backfilling | cuft | 1 | 8200 | 3 | 24600
SITE INFRA WORK | Infra - Brick Masonry 18" | cuft | 1000 | Material | Civil Raw Material-Bricks | Earthen Bricks | nos | 28.35 | 28350 | 6 | 170100
SITE INFRA WORK | Infra - Brick Masonry 18" | cuft | 1000 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.07004 | 70.04 | 220 | 15408.8
SITE INFRA WORK | Infra - Brick Masonry 18" | cuft | 1000 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.6096 | 609.6 | 50 | 30480
SITE INFRA WORK | Infra - Brick Masonry 18" | cuft | 1000 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.9696 | 969.6 | 50 | 48480
SITE INFRA WORK | Infra - Brick Masonry 18" | cuft | 1000 | Material | Civil Raw Material-Sand | Stone Dust | cuft | 0.2496 | 249.6 | 50 | 12480
SITE INFRA WORK | Infra - Brick Masonry 18" | cuft | 1000 | Service | Labour-Site Infra Work | infra - Brick Masonry 18" | cuft | 1 | 1000 | 30 | 30000
SITE INFRA WORK | Infra - Brick Masonry 4.5 | sqft | 5000 | Material | Civil Raw Material-Bricks | Earthen Bricks | nos | 5.855 | 29275.05 | 6 | 175650.3
SITE INFRA WORK | Infra - Brick Masonry 4.5 | sqft | 5000 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.016583 | 82.92 | 210.94 | 17490.09
SITE INFRA WORK | Infra - Brick Masonry 4.5 | sqft | 5000 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.10506 | 525.3 | 50 | 26265
SITE INFRA WORK | Infra - Brick Masonry 4.5 | sqft | 5000 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.029052 | 145.26 | 50 | 7263
SITE INFRA WORK | Infra - Brick Masonry 4.5 | sqft | 5000 | Material | Civil Raw Material-Sand | Stone Dust | cuft | 0.067788 | 338.94 | 40 | 13557.6
SITE INFRA WORK | Infra - Brick Masonry 4.5 | sqft | 5000 | Service | Labour-Site Infra Work | Infra - Brick Masonry 4.5" | sqft | 1 | 5000 | 20 | 100000
SITE INFRA WORK | Infra - Brick Masonry 9 | sqft | 5000 | Material | Civil Raw Material-Bricks | Earthen Bricks | nos | 10.549 | 52745.18 | 6 | 316471.05
SITE INFRA WORK | Infra - Brick Masonry 9 | sqft | 5000 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.023999 | 120 | 220 | 52797.8
SITE INFRA WORK | Infra - Brick Masonry 9 | sqft | 5000 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.21012 | 1050.6 | 50 | 52530
SITE INFRA WORK | Infra - Brick Masonry 9 | sqft | 5000 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.1681 | 840.48 | 50 | 42024
SITE INFRA WORK | Infra - Brick Masonry 9 | sqft | 5000 | Material | Civil Raw Material-Sand | Stone Dust | cuft | 0.042024 | 210.12 | 50 | 10506
SITE INFRA WORK | Infra - Brick Masonry 9 | sqft | 5000 | Service | Labour-Site Infra Work | Infra - Brick Masonry 9" | sqft | 1 | 5000 | 22 | 110000
SITE INFRA WORK | Infra - Door/Window Fixing Work | nos | 150 | Service | Labour-Site Infra Work | Infra - Door/Window Fixing | nos | 1 | 150 | 500 | 75000
SITE INFRA WORK | Infra - Electrical Work | nos | 10 | Service | Labour-Site Infra Work | Infra - Electrical Work | nos | 1 | 10 | 6000 | 60000
SITE INFRA WORK | Infra - Excavation | cuft | 1000 | Service | Labour-Site Infra Work | Infra - Excavation | cuft | 5 | 5000 | 4 | 20000
SITE INFRA WORK | Infra - External Plaster | sqft | 10000 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.017098 | 170.98 | 210.94 | 36066.52
SITE INFRA WORK | Infra - External Plaster | sqft | 10000 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.1248 | 1248 | 50 | 62400
SITE INFRA WORK | Infra - External Plaster | sqft | 10000 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.12444 | 1244.4 | 50 | 62220
SITE INFRA WORK | Infra - External Plaster | sqft | 10000 | Service | Labour-Site Infra Work | Infra - External Plaster | sqft | 1 | 10000 | 10 | 100000
SITE INFRA WORK | Infra - Fabrication Work | sqft | 35000 | Service | Labour-Site Infra Work | Infra - Fabrication Work | sqft | 1 | 35000 | 15 | 525000
SITE INFRA WORK | Infra - Flooring Work | sqft | 5000 | Service | Labour-Site Infra Work | Infra - Flooring Work | sqft | 1 | 5000 | 18 | 90000
SITE INFRA WORK | Infra - Internal Plaster | sqft | 10000 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.010094 | 100.94 | 210.94 | 21292.28
SITE INFRA WORK | Infra - Internal Plaster | sqft | 10000 | Material | Civil Raw Material-Misc | Fibre Mesh | mtr | 0.1 | 1000 | 4.8 | 4800
SITE INFRA WORK | Infra - Internal Plaster | sqft | 10000 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.0882 | 882 | 50 | 44100
SITE INFRA WORK | Infra - Internal Plaster | sqft | 10000 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.0882 | 882 | 50 | 44100
SITE INFRA WORK | Infra - Internal Plaster | sqft | 10000 | Service | Labour-Site Infra Work | Infra - Internal Plaster | sqft | 1 | 10000 | 10 | 100000
SITE INFRA WORK | Infra - Labour Hutment Fabrication | nos | 150 | Material | Site Infra Items-GI Sheet | GI Sheet 10x4 | nos | 4 | 600 | 1200 | 720000
SITE INFRA WORK | Infra - Labour Hutment Fabrication | nos | 150 | Material | Site Infra Items-GI Sheet | GI Sheet 8x4 | nos | 5 | 750 | 1100 | 825000
SITE INFRA WORK | Infra - Labour Hutment Fabrication | nos | 150 | Service | Labour-Site Infra Work | Infra-Hutment Fabrication Work | nos | 1 | 150 | 1500 | 225000
SITE INFRA WORK | Infra - M7.5 PCC Work | cuft | 1000 | Material | Civil Raw Material-RMC | RMC M-7.5 | cum | 0.02831 | 28.31 | 86.38 | 2445.42
SITE INFRA WORK | Infra - M7.5 PCC Work | cuft | 1000 | Service | Labour-Site Infra Work | Infra - PCC Work (RMC) | cuft | 1 | 1000 | 5 | 5000
SITE INFRA WORK | Infra - PCC Work | cuft | 5000 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.093318 | 466.59 | 210.94 | 98422.49
SITE INFRA WORK | Infra - PCC Work | cuft | 5000 | Material | Civil Raw Material-Grit | Grit 10 MM | cuft | 0.495 | 2475 | 22 | 54450
SITE INFRA WORK | Infra - PCC Work | cuft | 5000 | Material | Civil Raw Material-Grit | Grit 20 MM | cuft | 0.495 | 2475 | 27 | 66825
SITE INFRA WORK | Infra - PCC Work | cuft | 5000 | Material | Civil Raw Material-Sand | Silica Sand | cuft | 0.045 | 225 | 50 | 11250
SITE INFRA WORK | Infra - PCC Work | cuft | 5000 | Material | Civil Raw Material-Sand | Stone Dust | cuft | 0.486 | 2430 | 40 | 97200
SITE INFRA WORK | Infra - PCC Work | cuft | 5000 | Service | Labour-Site Infra Work | Infra - PCC Work | cuft | 1 | 5000 | 25 | 125000
SITE INFRA WORK | Infra - Paint Work | sqft | 5000 | Service | Labour-Site Infra Work | Infra - Paint Work | sqft | 1 | 5000 | 6 | 30000
SITE INFRA WORK | Infra - Plumbing Work | nos | 40 | Service | Labour-Site Infra Work | Infra - Plumbing Work | nos | 1 | 40 | 12000 | 480000
SITE INFRA WORK | Infra - RCC Work | cuft | 5000 | Material | Civil Raw Material-Cement | Cement PPC | bags | 0.20085 | 1004.25 | 210.94 | 211836.5
SITE INFRA WORK | Infra - RCC Work | cuft | 5000 | Material | Civil Raw Material-Chemical | Admixture PC Based | kg | 0.04 | 200 | 50 | 10000
SITE INFRA WORK | Infra - RCC Work | cuft | 5000 | Material | Civil Raw Material-Grit | Grit 10 MM | cuft | 0.4268 | 2134 | 22 | 46948
SITE INFRA WORK | Infra - RCC Work | cuft | 5000 | Material | Civil Raw Material-Grit | Grit 20 MM | cuft | 0.50864 | 2543.2 | 27 | 68666.4
SITE INFRA WORK | Infra - RCC Work | cuft | 5000 | Material | Civil Raw Material-Sand | M-Sand | cuft | 0.455 | 2275 | 40 | 91000
SITE INFRA WORK | Infra - RCC Work | cuft | 5000 | Service | Labour-Site Infra Work | Infra - RCC Work | cuft | 1 | 5000 | 15 | 75000
SITE INFRA WORK | Infra - Reinforcement Work | MT | 25 | Material | Civil Raw Material-Misc | Binding Wire | kg | 10 | 250 | 70 | 17500
SITE INFRA WORK | Infra - Reinforcement Work | MT | 25 | Material | Civil Raw Material-Steel | TMT Steel 08 MM | MT | 0.2 | 5 | 55000 | 275000
SITE INFRA WORK | Infra - Reinforcement Work | MT | 25 | Material | Civil Raw Material-Steel | TMT Steel 10 MM | MT | 0.2 | 5 | 55000 | 275000
SITE INFRA WORK | Infra - Reinforcement Work | MT | 25 | Material | Civil Raw Material-Steel | TMT Steel 12 MM | MT | 0.2 | 5 | 55000 | 275000
SITE INFRA WORK | Infra - Reinforcement Work | MT | 25 | Material | Civil Raw Material-Steel | TMT Steel 16 MM | MT | 0.2 | 5 | 55000 | 275000
SITE INFRA WORK | Infra - Reinforcement Work | MT | 25 | Material | Civil Raw Material-Steel | TMT Steel 20 MM | MT | 0.2 | 5 | 55000 | 275000
SITE INFRA WORK | Infra - Reinforcement Work | MT | 25 | Service | Labour-Site Infra Work | Infra - Reinforcement | MT | 1 | 25 | 6000 | 150000
SITE INFRA WORK | Infra - Shuttering Work | sqft | 1000 | Service | Labour-Site Infra Work | Infra - Shuttering | sqft | 1 | 1000 | 15 | 15000
SITE INFRA WORK | Infra -Wall Tile Work | sqft | 500 | Service | Labour-Site Infra Work | Infra -Wall Tile Work | sqft | 1 | 500 | 18 | 9000
Non-Productive (General Site Work)
Parent WBS Name | Activity Name | Activity Unit | Total Qty | Resource Type | Item Group | Item Desc | Resource Unit | Resource Coefficient | Est Qty | Est Rate | Est Amt
GENERAL SITE WORK | Chipping, Grinding & Welding | lumpsum | 2160 | Service | Labour-General Works | Chipping / Grinding & Welding | lumpsum | 1 | 2160 | 350 | 756000
GENERAL SITE WORK | Cleaning Work | lumpsum | 5400 | Service | Labour-General Works | Cleaning Work | lumpsum | 1 | 5400 | 350 | 1890000
GENERAL SITE WORK | Curing | lumpsum | 3240 | Service | Labour-General Works | Curing | lumpsum | 1 | 3240 | 350 | 1134000
GENERAL SITE WORK | Dismantling | lumpsum | 857 | Service | Labour-General Works | Dismantling | lumpsum | 1.0012 | 858 | 350 | 300300
GENERAL SITE WORK | Electrical, Plumbing,Mechanical Work | lumpsum | 857 | Service | Labour-General Works | Electrical-Plumbing-Mechanical Work | lumpsum | 1.0012 | 858 | 350 | 300300
GENERAL SITE WORK | Housekeeping Work | lumpsum | 5400 | Service | Labour-General Works | Housekeeping Work | lumpsum | 1 | 5400 | 350 | 1890000
GENERAL SITE WORK | Lab Work | lumpsum | 720 | Service | Labour-General Works | Lab Work | lumpsum | 1 | 720 | 350 | 252000
GENERAL SITE WORK | Labour Supply to Client | lumpsum | 3600 | Service | Labour-General Works | Labour Supply to Client | lumpsum | 1 | 3600 | 350 | 1260000
GENERAL SITE WORK | Labour Supply to Other Site/Godown | lumpsum | 3600 | Service | Labour-General Works | Labour Supply to Other Site/Godown | lumpsum | 1 | 3600 | 350 | 1260000
GENERAL SITE WORK | Level Marking & Layout | lumpsum | 2160 | Service | Labour-General Works | Level Marking & Layout | lumpsum | 1 | 2160 | 450 | 972000
GENERAL SITE WORK | Leveling Dressing | lumpsum | 1430 | Service | Labour-General Works | Leveling and Dressing | lumpsum | 1 | 1430 | 350 | 500500
GENERAL SITE WORK | Lift Operator | lumpsum | 2160 | Service | Labour-General Works | Lift Operator | lumpsum | 1 | 2160 | 350 | 756000
GENERAL SITE WORK | Oiling Taping Cover Block Fixing | lumpsum | 2778 | Service | Labour-General Works | Oiling Taping Cover Block Fixing | lumpsum | 1 | 2778 | 350 | 972300
GENERAL SITE WORK | Repairing | lumpsum | 2160 | Service | Labour-General Works | Repairing | lumpsum | 1 | 2160 | 450 | 972000
GENERAL SITE WORK | Slab Ponding Work | lumpsum | 720 | Service | Labour-General Works | Slab Ponding Work | lumpsum | 1 | 720 | 350 | 252000
GENERAL SITE WORK | Starter Fixing | lumpsum | 2160 | Service | Labour-General Works | Starter fixing | lumpsum | 1 | 2160 | 450 | 972000
GENERAL SITE WORK | Sweeper & Office boy | lumpsum | 1080 | Service | Labour-General Works | Sweeper & Office boy | lumpsum | 1 | 1080 | 350 | 378000
Overheads
Parent WBS Name | Activity Name | Activity Unit | Total Qty | Resource Type | Item Group | Item Desc | Resource Unit | Resource Coefficient | Est Qty | Est Rate | Est Amt
GENERAL SITE WORK | Material Shifting Loading Unloading | lumpsum | 10800 | Service | Site Expenses | Material Shifting Loading Unloading | lumpsum | 1 | 10800 | 350 | 3780000
HIRE & RENT | Machine Hire charges | lumpsum | 218 | Service | Hire & Rent | JCB HIRE CHARGE | hours | 3.5092 | 765 | 850 | 650250
HIRE & RENT | Machine Hire charges | lumpsum | 218 | Service | Hire & Rent | Machinery Hire Charges | lumpsum | 1 | 218 | 25000 | 5450000
HIRE & RENT | Machine Hire charges | lumpsum | 218 |  | Hire & Rent | Dismantling of rcc work by Hammer machine |  | 0 | 0 | 0 | 0
HIRE & RENT | Machine Hire charges | lumpsum | 218 |  | Hire & Rent | Machine Hire charges |  | 0 | 0 | 0 | 0
HIRE & RENT | Machine Hire charges | lumpsum | 218 |  | Hire & Rent | Tractor Hire Charges (Monthly) |  | 0 | 0 | 0 | 0
HIRE & RENT | Shuttering Rent | lumpsum | 12 | Service | Hire & Rent | Shuttering Rent | lumpsum | 1 | 12 | 1010515 | 12126180
HIRE & RENT | Tools and Plant Rent | lumpsum | 12 | Service | Hire & Rent | Tools Rent | lumpsum | 1 | 12 | 360000 | 4320000
SITE ADMINISTRATIVE EXPENSES | Diesel | lumpsum | 350000 | Service | Site Expenses | Diesel Expenses | lumpsum | 1 | 350000 | 1 | 350000
SITE ADMINISTRATIVE EXPENSES | Electrical Charges | lumpsum | 16 | Service | Site Expenses | Electricity Charges | lumpsum | 1 | 16 | 300000 | 4800000
SITE ADMINISTRATIVE EXPENSES | Installation Charges | lumpsum | 1500000 | Service | Site Expenses | Installation Charges | lumpsum | 1 | 1500000 | 1 | 1500000
SITE ADMINISTRATIVE EXPENSES | Lab Material | lumpsum | 500000 | Service | Site Expenses | Lab Material | lumpsum | 1 | 500000 | 1 | 500000
SITE ADMINISTRATIVE EXPENSES | Machine & Vehicle Service Charges | lumpsum | 240000 | Service | Site Expenses | Machine & Vehicle Service Charges | lumpsum | 1 | 240000 | 1 | 240000
SITE ADMINISTRATIVE EXPENSES | Office Goods | lumpsum | 500000 | Service | Site Expenses | Office Goods | lumpsum | 1 | 500000 | 1 | 500000
SITE ADMINISTRATIVE EXPENSES | Property Rent Charges | lumpsum | 12 | Service | Site Expenses | Property Rent Charges | lumpsum | 1 | 12 | 100000 | 1200000
SITE ADMINISTRATIVE EXPENSES | Safety Items | lumpsum | 600000 | Service | Site Expenses | Safety Items | lumpsum | 1 | 600000 | 1 | 600000
SITE ADMINISTRATIVE EXPENSES | Security Guard | lumpsum | 2660 | Service | Site Expenses | Security Guard | lumpsum | 1 | 2660 | 500 | 1330000
SITE ADMINISTRATIVE EXPENSES | Staff Welfare &medicne | lumpsum | 600000 | Service | Site Expenses | Staff Welfare and Medicines | lumpsum | 1 | 600000 | 1 | 600000
SITE ADMINISTRATIVE EXPENSES | Stationary | lumpsum | 240000 | Service | Site Expenses | STATIONARY | Rs. | 1 | 240000 | 1 | 240000
SITE ADMINISTRATIVE EXPENSES | Tools and Plant Material | lumpsum | 1500000 | Service | Site Expenses | Tools and Plant Material | Rs. | 1 | 1500000 | 1 | 1500000
SITE ADMINISTRATIVE EXPENSES | Transportation & Courier Charges | lumpsum | 120000 | Service | Site Expenses | Transportation and Courier Charges | lumpsum | 1 | 120000 | 1 | 120000
SITE ADMINISTRATIVE EXPENSES | Travel & Conveyance | lumpsum | 240000 | Service | Site Expenses | Travel & Conveyance | lumpsum | 1 | 240000 | 1 | 240000
SITE ADMINISTRATIVE EXPENSES | Water Charges | lumpsum | 70000 | Service | Site Expenses | Water Charges | lumpsum | 1 | 70000 | 1 | 70000

## Summary
Report Type : Fund Report — Summary
Project Name : WTC Commercial
Generated on: 2026-06-11 17:49:06
Material Wise Summary (Productive Work)
Item Group | Item Desc | Resource Unit | Total Est Qty | Total Est Amt
Civil Raw Material-Bricks | Bricks Bat | cuft | 15964.4 | 399110.08
Civil Raw Material-Bricks | Earthen Bricks | nos | 773766.88 | 5416368.15
Civil Raw Material-Bricks | Flyash Bricks | nos | 1316345.88 | 9214421.18
Civil Raw Material-Cement | Cement PPC | bags | 14684.63 | 3101775.73
Civil Raw Material-Chemical | Anti Termite Chemical | ltr | 104232.2 | 0
Civil Raw Material-Chemical | Waterproofing Chemical | kg | 908.74 | 45436.95
Civil Raw Material-Coupler | Coupler 16 16 MM | nos | 7000 | 1540000
Civil Raw Material-Coupler | Coupler 20 20 MM | nos | 4600 | 1012000
Civil Raw Material-Coupler | Coupler 25 20 MM | nos | 3650 | 803000
Civil Raw Material-Coupler | Coupler 25 25 MM | nos | 7000 | 1540000
Civil Raw Material-Coupler | Coupler 32 20 MM | nos | 500 | 110000
Civil Raw Material-Coupler | Coupler 32 25 MM | nos | 2350 | 517000
Civil Raw Material-Coupler | Coupler 32 32 MM | nos | 7000 | 1540000
Civil Raw Material-Coupler | Coupler 40 25 MM | nos | 500 | 110000
Civil Raw Material-Coupler | Coupler 40 32 MM | nos | 1500 | 330000
Civil Raw Material-Coupler | Coupler 40 40 MM | nos | 2200 | 484000
Civil Raw Material-Cover Block | Cover Block 20 MM | nos | 87698.9 | 87698.9
Civil Raw Material-Cover Block | Cover Block 25 MM | nos | 79995.27 | 79995.27
Civil Raw Material-Cover Block | Cover Block 50 MM | nos | 80113.43 | 80113.43
Civil Raw Material-Cover Block | Cover Block L Shape 40 MM | nos | 80113.43 | 80113.43
Civil Raw Material-Grit | Grit 10 MM | cuft | 498.61 | 11467.96
Civil Raw Material-Grit | Grit 20 MM | cuft | 599.1 | 16774.83
Civil Raw Material-Misc | Binding Wire | kg | 44050 | 3083500
Civil Raw Material-Misc | Fibre Mesh | mtr | 51985.31 | 249529.47
Civil Raw Material-Misc | Shuttering Oil | ltr | 4135.65 | 268817.19
Civil Raw Material-RMC | RMC M-15 | cum | 328.51 | 1133345.7
Civil Raw Material-RMC | RMC M-25 | cum | 873.62 | 3145032
Civil Raw Material-RMC | RMC M-30 | cum | 8513.17 | 31934850.4
Civil Raw Material-RMC | RMC M-35 | cum | 69421.23 | 277684924
Civil Raw Material-RMC | RMC M-40 | cum | 10 | 42004.2
Civil Raw Material-RMC | RMC M-45 | cum | 9.5 | 39900
Civil Raw Material-RMC | RMC M-50 | cum | 3.5 | 14000
Civil Raw Material-RMC | RMC M-7.5 | cum | 1517.96 | 4553865
Civil Raw Material-Sand | M-Sand | cuft | 66798.34 | 3167493.94
Civil Raw Material-Sand | Silica Sand | cuft | 73002.66 | 3650132.8
Civil Raw Material-Steel | TMT Steel 08 MM | MT | 453.72 | 24990622.2
Civil Raw Material-Steel | TMT Steel 10 MM | MT | 907.43 | 49981244.4
Civil Raw Material-Steel | TMT Steel 12 MM | MT | 453.72 | 24990622.2
Civil Raw Material-Steel | TMT Steel 16 MM | MT | 453.72 | 24990622.2
Civil Raw Material-Steel | TMT Steel 20 MM | MT | 453.72 | 24990622.2
Civil Raw Material-Steel | TMT Steel 25 MM | MT | 907.43 | 49981244.4
Civil Raw Material-Steel | TMT Steel 32 MM | MT | 453.72 | 24990622.2
Civil Raw Material-Steel | TMT Steel 40 MM | MT | 453.72 | 24990622.2
Civil Shuttering-Batten (Mirandi) | Batten 3x2.5x10 (Mirandi) | nos | 3544.84 | 2304147.3
Civil Shuttering-Batten (Pine) | Batten 2.25x1.5x8 (Pine) | nos | 10634.53 | 1595178.9
Civil Shuttering-Batten (Pine) | Batten 2x2.5x8 (Pine) | nos | 31383.67 | 6276733.6
Civil Shuttering-Misc | Shuttering Tape Brown | nos | 1417.94 | 106345.28
Civil Shuttering-Misc | Shuttering Tape White | nos | 118.16 | 8862.08
Civil Shuttering-Ply | Old Ply Scrap All Size | nos | 3922.96 | 274607.06
Civil Shuttering-Ply | Shuttering Ply 8x4x12 MM | nos | 3922.96 | 7845916
Consumable Material-Nails | Nails 2 | kg | 7089.68 | 460829.46
Consumable Material-Nails | Nails 3 | kg | 8271.3 | 537634.37
Consumable Material-Nails | Nails 4 | kg | 8271.3 | 537634.37
Site Infra Items-Porta Cabin | Container Portable Toilet | nos | 1 | 50000
Site Infra Items-Porta Cabin | Office Container Cabin | nos | 1 | 1000000
Service Wise Summary (Productive Work)
Item Group | Item Desc | Resource Unit | Total Est Qty | Total Est Amt
Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | 30850 | 321470
Labour-Civil-Concreting Work | Concreting Work With RMC M-30 | cuft | 300600 | 593484
Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 2451372.85 | 29206864.25
Labour-Civil-Concreting Work | Concreting Work With RMC M-40 | cuft | 353.15 | 1765.74
Labour-Civil-Concreting Work | Concreting Work With RMC M-45 | cuft | 335.45 | 5031.75
Labour-Civil-Concreting Work | Concreting Work With RMC M-50 | cuft | 123.6 | 1854
Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | 53599 | 267995
Labour-Civil-Concreting Work | Concreting Work with RMC M-15 | cuft | 11608 | 58040
Labour-Civil-Corecutting Work | Corecutting Work | nos | 12 | 48000
Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 16 MM | nos | 7000 | 210000
Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 20 MM | nos | 4600 | 92000
Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 25 MM | nos | 7000 | 210000
Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 25mm X 20mm | nos | 3650 | 109500
Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 32 MM | nos | 7000 | 210000
Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 32mm X 20mm | nos | 500 | 15000
Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 40 MM | nos | 2200 | 66000
Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 40mm X 25mm | nos | 500 | 15000
Labour-Civil-Coupler Fixing Work | Coupler Fixing work 32mm X 25mm | nos | 2350 | 70500
Labour-Civil-Coupler Fixing Work | Coupler fixing work 40mm X 32mm | nos | 1500 | 45000
Labour-Civil-Earth Work | Anti Termite Treatment | sqft | 104232.2 | 0
Labour-Civil-Earth Work | Back Filling Work | cuft | 115278 | 230556
Labour-Civil-Earth Work | Excavation Work | cuft | 3740613.19 | 11221839.56
Labour-Civil-Masonry Work | Masonry Work Brick 4.5" Thick | sqft | 40343 | 887546
Labour-Civil-Masonry Work | Masonry Work Brick 9" Thick | sqft | 102392.04 | 2559801
Labour-Civil-Plaster Work | Plaster Work External | sqft | 143253.07 | 2865061.4
Labour-Civil-Plaster Work | Plaster Work Internal | sqft | 376600 | 3766000
Labour-Civil-Rebaring Work | Rebaring Work 08mm Dia | nos | 3005.7 | 1803420
Labour-Civil-Rebaring Work | Rebaring Work 10mm Dia | nos | 8010.9 | 4806540
Labour-Civil-Rebaring Work | Rebaring Work 12mm Dia | nos | 1212.6 | 727560
Labour-Civil-Rebaring Work | Rebaring Work 16mm Dia | nos | 503.1 | 301860
Labour-Civil-Rebaring Work | Rebaring Work 20mm Dia | nos | 206.4 | 123840
Labour-Civil-Rebaring Work | Rebaring Work 25mm Dia | nos | 154.8 | 92880
Labour-Civil-Reinforcement Work | Reinforcement Work Steel Binding | kg | 4405000 | 30835000
Labour-Civil-Scaffolding | De-Scaffolding | sqft | 127253 | 318132.5
Labour-Civil-Scaffolding | Scaffolding | sqft | 127253 | 318132.5
Labour-Civil-Shuttering Work | Extra Height Shuttering Work | sqft | 590807 | 0
Labour-Civil-Shuttering Work | Shuttering Making Work | sqft | 125534.15 | 1004273.19
Labour-Civil-Shuttering Work | Shuttering Work | sqft | 1181614 | 23632280
Labour-Civil-Threading Work | Threading Work 16 MM | nos | 15053.04 | 255901.61
Labour-Civil-Threading Work | Threading Work 20 MM | nos | 23000.68 | 460013.54
Labour-Civil-Threading Work | Threading Work 25 MM | nos | 32068.15 | 769635.53
Labour-Civil-Threading Work | Threading Work 32 MM | nos | 22224.91 | 600072.46
Labour-Civil-Threading Work | Threading Work 40 MM | nos | 7816.15 | 328278.47
Labour-Civil-Water proofing Work | Water proofing Work Brick Bat Coba | sqft | 47898 | 1197450