## Detailed Data
Report Type : Material Reconciliation Report
Project Name : WTC Commercial
Generated on: 2026-07-13 18:37:06
Item Group | Item Desc | Resource Unit | Est Qty | Est Rate | Est Amt | Theoritical Qty | Theoritical Amt | Actual Qty | Actual Rate | Actual Amt | Wastage | Wastage % | Stock Received Qty (B) | Project Transfer Qty (E) | Stock Issue Qty (D) | Closing Stock Qty (CG) | Actual - Tag Issue Qty Difference | Stock Issue Amount
Civil Raw Material-Bricks | Bricks Bat | cuft | 15964.4 | 25 | 399110.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil Raw Material-Bricks | Earthen Bricks | nos | 219259.54 | 6.4 | 1424446.56 | 176220.34 | 1158846.55 | 89489 | 4.03 | 360333.8 | -86731.336 | -49.2176 | 89489 | 0 | 89489 | 0 | 0 | 360640.67
Civil Raw Material-Bricks | Flyash Bricks | nos | 1165338.86 | 7 | 8157372 | 1035096.4 | 7245674.81 | 770220 | 5.45 | 4198766 | -264876.402 | -25.5895 | 780079 | 0 | 771220 | 8859 | 1000 | 4203149
Civil Raw Material-Cement | Cement PPC | bags | 16672.5 | 213.24 | 3549220.81 | 10169.98 | 2146743 | 7988.67 | 214.33 | 1712213.5 | -2181.315 | -21.4486 | 10800 | 380 | 9578 | 842 | 1589.33 | 2052852.74
Civil Raw Material-Chemical | Admixture PC Based | kg | 200 | 50 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil Raw Material-Chemical | Anti Termite Chemical | ltr | 104232.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil Raw Material-Chemical | Waterproofing Chemical | kg | 928.64 | 50 | 46431.9 | 142.06 | 7102.77 | 0 | 0 | 0 | -142.055 | -100 | 0 | 0 | 0 | 0 | 0 | 0
Civil Raw Material-Coupler | Coupler 16 16 MM | nos | 7000 | 220 | 1540000 | 0 | 0 | 22 | 28.1 | 618.2 | 22 | 0 | 200 | 178 | 22 | 0 | 0 | 618.2
Civil Raw Material-Coupler | Coupler 20 20 MM | nos | 4600 | 220 | 1012000 | 4165 | 916300 | 4175 | 39.5 | 164912.5 | 10 | 0.2401 | 4258 | 75 | 4183 | 0 | 8 | 165228.5
Civil Raw Material-Coupler | Coupler 25 20 MM | nos | 3650 | 220 | 803000 | 3586 | 788920 | 3517 | 80 | 281360 | -69 | -1.9241 | 3662 | 2 | 3660 | 0 | 143 | 292800
Civil Raw Material-Coupler | Coupler 25 25 MM | nos | 5676 | 220 | 1248720 | 5567 | 1224740 | 5585 | 61.2 | 341802 | 18 | 0.32333 | 6242 | 586 | 5656 | 0 | 71 | 346147.2
Civil Raw Material-Coupler | Coupler 32 20 MM | nos | 100 | 220 | 22000 | 26 | 5720 | 5 | 125 | 625 | -21 | -80.7692 | 188 | 183 | 5 | 0 | 0 | 625
Civil Raw Material-Coupler | Coupler 32 25 MM | nos | 2350 | 220 | 517000 | 2225 | 489500 | 2264 | 125 | 283000 | 39 | 1.7528 | 2393 | 114 | 2279 | 0 | 15 | 284875
Civil Raw Material-Coupler | Coupler 32 32 MM | nos | 5070 | 220 | 1115400 | 4859 | 1068980 | 4974 | 94.4 | 469545.6 | 115 | 2.3667 | 5099 | 125 | 4974 | 0 | 0 | 469545.6
Civil Raw Material-Coupler | Coupler 40 25 MM | nos | 500 | 220 | 110000 | 44 | 9680 | 41 | 262 | 10742 | -3 | -6.8182 | 42 | 1 | 41 | 0 | 0 | 10742
Civil Raw Material-Coupler | Coupler 40 32 MM | nos | 850 | 220 | 187000 | 722 | 158840 | 864 | 262 | 226368 | 142 | 19.6676 | 869 | 5 | 864 | 0 | 0 | 226368
Civil Raw Material-Coupler | Coupler 40 40 MM | nos | 1354 | 220 | 297880 | 1348 | 296560 | 1357 | 210 | 284970 | 9 | 0.66766 | 1409 | 52 | 1357 | 0 | 0 | 284970
Civil Raw Material-Cover Block | Cover Block 20 MM | nos | 87698.9 | 1 | 87698.9 | 86406.36 | 86406.36 | 150000 | 0.32 | 48132 | 63593.641 | 73.5983 | 154200 | 0 | 151200 | 3000 | 1200 | 48384
Civil Raw Material-Cover Block | Cover Block 25 MM | nos | 79995.27 | 1 | 79995.27 | 78816.27 | 78816.27 | 93100 | 0.52 | 48690 | 14283.73 | 18.1228 | 97200 | 2000 | 93700 | 1500 | 600 | 48724
Civil Raw Material-Cover Block | Cover Block 50 MM | nos | 80113.43 | 1 | 80113.43 | 78932.69 | 78932.69 | 15300 | 1.61 | 24690 | -63632.689 | -80.6164 | 21600 | 6300 | 15300 | 0 | 0 | 24633
Civil Raw Material-Cover Block | Cover Block L Shape 40 MM | nos | 80113.43 | 1 | 80113.43 | 78932.69 | 78932.69 | 18564 | 1 | 18479.75 | -60368.689 | -76.4812 | 20400 | 0 | 20200 | 200 | 1636 | 20200
Civil Raw Material-Grit | Grit 10 MM | cuft | 5107.61 | 22.33 | 112865.96 | 2164.14 | 47611.13 | 2455 | 24.21 | 59445 | 290.858 | 13.4399 | 3957 | 0 | 3927 | 30 | 1472 | 95072.67
Civil Raw Material-Grit | Grit 20 MM | cuft | 5617.3 | 27.33 | 152266.23 | 2164.14 | 58431.84 | 144 | 27.31 | 3932 | -2020.142 | -93.3461 | 184 | 0 | 144 | 40 | 0 | 3932.64
Civil Raw Material-Misc | Binding Wire | kg | 44300 | 70 | 3101000 | 43313.94 | 3031975.8 | 25910 | 57.62 | 1492846.19 | -17403.94 | -40.1809 | 26475 | 100 | 26265 | 110 | 355 | 1513389.3
Civil Raw Material-Misc | Fibre Mesh | mtr | 55082 | 4.8 | 264393.6 | 42479.95 | 203903.74 | 2600 | 4.2 | 10920 | -39879.946 | -93.8795 | 4500 | 0 | 4000 | 500 | 1400 | 16800
Civil Raw Material-Misc | Shuttering Oil | ltr | 4135.65 | 65 | 268817.19 | 4074.7 | 264855.26 | 3245 | 60.95 | 197767.05 | -829.696 | -20.3622 | 3740 | 0 | 3383 | 357 | 138 | 206193.85
Civil Raw Material-RMC | RMC M-15 | cum | 328.51 | 3450 | 1133345.7 | 171.88 | 592968.6 | 172 | 2358.14 | 405600 | 0.125 | 0.072727 | 172 | 0 | 172 | 0 | 0 | 405600.08
Civil Raw Material-RMC | RMC M-25 | cum | 873.62 | 3600 | 3145032 | 666.96 | 2401046.56 | 646 | 2669.08 | 1724225.4 | -20.958 | -3.1423 | 646 | 0 | 646 | 0 | 0 | 1724225.68
Civil Raw Material-RMC | RMC M-30 | cum | 8513.17 | 3800 | 31934850.4 | 8407.55 | 31948692.03 | 8407 | 3018.63 | 25377612.7 | -0.551 | -0.0065536 | 8407 | 0 | 8407 | 0 | 0 | 25377622.41
Civil Raw Material-RMC | RMC M-35 | cum | 26430.58 | 4000 | 105722304 | 25246.51 | 100986046.04 | 25216.5 | 2521.73 | 63589169.68 | -30.011 | -0.11887 | 25216.5 | 0 | 25216.5 | 0 | 0 | 63589204.545
Civil Raw Material-RMC | RMC M-40 | cum | 10 | 4200 | 42004.2 | 6.5 | 27300 | 6.5 | 4525 | 29412.5 | 0 | 0 | 6.5 | 0 | 6.5 | 0 | 0 | 29412.5
Civil Raw Material-RMC | RMC M-45 | cum | 9.5 | 4200 | 39900 | 9.5 | 39900 | 9.5 | 2300 | 21850 | 0 | 0 | 9.5 | 0 | 9.5 | 0 | 0 | 21850
Civil Raw Material-RMC | RMC M-50 | cum | 3.5 | 4000 | 14000 | 3.5 | 14000 | 3.5 | 5152.54 | 18033.89 | 0 | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 18033.89
Civil Raw Material-RMC | RMC M-7.5 | cum | 1546.26 | 2028.79 | 4556310.42 | 1381.51 | 4125601.93 | 1383.5 | 2607.08 | 3606888.74 | 1.989 | 0.14397 | 1383.5 | 0 | 1383.5 | 0 | 0 | 3606895.18
Civil Raw Material-Sand | M-Sand | cuft | 71116.52 | 47.5 | 3360652.89 | 30596.18 | 1529809.01 | 24245.54 | 39.6 | 960052.01 | -6350.64 | -20.7563 | 25905.54 | 80 | 25349.54 | 476 | 1104 | 1003841.784
Civil Raw Material-Sand | Silica Sand | cuft | 75791.3 | 50 | 3789564.9 | 44342.47 | 2217123.27 | 40365.46 | 50 | 2018273.2 | -3977.003 | -8.9688 | 49389.93 | 83 | 47306.39 | 2000.54 | 6940.93 | 2365319.5
Civil Raw Material-Sand | Stone Dust | cuft | 3228.66 | 45 | 133743.6 | 2352.19 | 97520.38 | 1530 | 22.5 | 34425 | -822.187 | -34.9542 | 1590 | 0 | 1590 | 0 | 60 | 35775
Civil Raw Material-Steel | TMT Steel 08 MM | MT | 458.72 | 55040 | 25265622.2 | 434.07 | 23908234.48 | 222.72 | 46824.6 | 10428587.48 | -211.35 | -48.6908 | 253.85 | 0 | 230.11 | 23.74 | 7.39 | 10774808.706
Civil Raw Material-Steel | TMT Steel 10 MM | MT | 912.43 | 55040 | 50256244.4 | 866.28 | 47714487.97 | 1149.72 | 37316.28 | 42903203.33 | 283.439 | 32.7191 | 1227.84 | 0 | 1160.61 | 67.23 | 10.89 | 43309647.7308
Civil Raw Material-Steel | TMT Steel 12 MM | MT | 458.72 | 55040 | 25265622.2 | 434.07 | 23908234.48 | 447.99 | 38845.8 | 17402648.48 | 13.927 | 3.2085 | 480.08 | 0 | 452.92 | 27.16 | 4.93 | 17594039.736
Civil Raw Material-Steel | TMT Steel 16 MM | MT | 458.72 | 55040 | 25265622.2 | 434.07 | 23908234.48 | 206.96 | 45954.82 | 9510994.22 | -227.102 | -52.3197 | 237.04 | 0 | 212.62 | 24.42 | 5.66 | 9770913.8284
Civil Raw Material-Steel | TMT Steel 20 MM | MT | 458.72 | 55040 | 25265622.2 | 434.07 | 23908234.48 | 264.29 | 48327.17 | 12772243.5 | -169.779 | -39.1136 | 292.36 | 6.11 | 264.29 | 21.96 | 0 | 12772387.7593
Civil Raw Material-Steel | TMT Steel 25 MM | MT | 907.43 | 55080 | 49981244.4 | 864.42 | 47612506.97 | 1634.01 | 43961.67 | 71833724.35 | 769.583 | 89.0283 | 1655.92 | 3.27 | 1634.01 | 18.64 | 0 | 71833808.3967
Civil Raw Material-Steel | TMT Steel 32 MM | MT | 453.72 | 55080 | 24990622.2 | 432.21 | 23806253.48 | 407.47 | 50931.34 | 20752841.71 | -24.745 | -5.7252 | 422.8 | 4.52 | 407.47 | 10.82 | 0 | 20752993.1098
Civil Raw Material-Steel | TMT Steel 40 MM | MT | 453.72 | 55080 | 24990622.2 | 432.21 | 23806253.48 | 94.22 | 55988.77 | 5275485.5 | -337.988 | -78.1996 | 94.24 | 0 | 94.22 | 0.02 | 0 | 5275261.9094
Civil Shuttering-Batten (Mirandi) | Batten 3x2.5x10 (Mirandi) | nos | 3544.84 | 650 | 2304147.3 | 3492.6 | 2270187.97 | 1052 | 525.26 | 552573.32 | -2440.597 | -69.8791 | 1062 | 0 | 1062 | 0 | 10 | 557826.12
Civil Shuttering-Batten (Pine) | Batten 2.25x1.5x8 (Pine) | nos | 10634.53 | 150 | 1595178.9 | 10477.79 | 1571668.6 | 9188 | 120.4 | 1106240.64 | -1289.791 | -12.3098 | 9278 | 30 | 9248 | 0 | 60 | 1113459.2
Civil Shuttering-Batten (Pine) | Batten 2x2.5x8 (Pine) | nos | 31383.67 | 200 | 6276733.6 | 30921.12 | 6184224.88 | 16855 | 186.2 | 3138407.49 | -14066.124 | -45.4903 | 17267 | 0 | 17267 | 0 | 412 | 3215115.4
Civil Shuttering-Misc | Shuttering Tape Brown | nos | 1417.94 | 75 | 106345.28 | 1397.04 | 104777.91 | 17 | 25.24 | 429.16 | -1380.039 | -98.7831 | 1638 | 0 | 1618 | 20 | 1601 | 40838.32
Civil Shuttering-Misc | Shuttering Tape White | nos | 118.16 | 75 | 8862.08 | 116.42 | 8731.49 | 0 | 0 | 0 | -116.42 | -100 | 12 | 0 | 11 | 1 | 11 | 0
Civil Shuttering-Ply | Old Ply Scrap All Size | nos | 3922.96 | 70 | 274607.06 | 3865.14 | 270559.84 | 11 | 59.09 | 650 | -3854.141 | -99.7154 | 651 | 622 | 12 | 17 | 1 | 709.08
Civil Shuttering-Ply | Shuttering Ply 8x4x12 MM | nos | 3922.96 | 2000 | 7845916 | 3865.14 | 7730281.09 | 1830 | 1947.15 | 3563280.85 | -2035.141 | -52.6537 | 1830 | 0 | 1830 | 0 | 0 | 3563284.5
Consumable Material-Nails | Nails 2 | kg | 7089.68 | 65 | 460829.46 | 6985.19 | 454037.59 | 1760 | 53.96 | 94968.99 | -5225.194 | -74.8038 | 1800 | 0 | 1800 | 0 | 40 | 97128
Consumable Material-Nails | Nails 3 | kg | 8271.3 | 65 | 537634.37 | 8149.39 | 529710.53 | 5961 | 52.06 | 310313.15 | -2188.393 | -26.8534 | 6200 | 0 | 6186 | 14 | 225 | 322043.16
Consumable Material-Nails | Nails 4 | kg | 8271.3 | 65 | 537634.37 | 8149.39 | 529710.53 | 3479 | 51.45 | 179003.17 | -4670.393 | -57.3097 | 3550 | 0 | 3540 | 10 | 61 | 182133
Site Infra Items-GI Sheet | GI Sheet 10x4 | nos | 600 | 1200 | 720000 | 480 | 576000 | 0 | 0 | 0 | -480 | -100 | 780 | 22 | 758 | 0 | 758 | 0
Site Infra Items-GI Sheet | GI Sheet 8x4 | nos | 750 | 1100 | 825000 | 600 | 660000 | 0 | 0 | 0 | -600 | -100 | 671 | 60 | 611 | 0 | 611 | 0
Site Infra Items-Porta Cabin | Container Portable Toilet | nos | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
Site Infra Items-Porta Cabin | Office Container Cabin | nos | 1 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
Total |  |  | 2268252.82 | 15224.75 | 452362663.89 | 1857471.01 | 422889811 | 1348385.55 | 228.31 | 307851297.05 | -509085.465 | -27.4075 | 0 | 0 | 0 | 0 | -1348385.55 | 0

## Activity Wise Estimate
Report Type : Material Reconciliation Report
Project Name : WTC Commercial
Generated on: 2026-07-13 18:37:06
Sr | Project Name | Sub Project | Parent WBS Name | Activity Code | Activity Name | Activity Unit | Total Qty | Item Group | Item Desc | Resource Unit | Est Qty | Est Rate | Est Amt | Theoritical Qty | Actual Qty | Difference Qty | Theoritical Amt | Actual Amt | Difference Amt | Key | Resource Type
29 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Bricks | Earthen Bricks | nos | 28350 | 6 | 170100 | 24648.705 | 14606.81 | 10041.895 | 147892.23 | 59105.878 | 88786.352 | Infra - Brick Masonry 18" Earthen Bricks | Material
30 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Cement | Cement PPC | bags | 70.04 | 220 | 15408.8 | 62.078 | 49.71 | 12.368 | 13657.208 | 10709.936 | 2947.272 | Infra - Brick Masonry 18" Cement PPC | Material
31 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Sand | M-Sand | cuft | 609.6 | 50 | 30480 | 463.761 | 83 | 380.761 | 23188.041 | 2905 | 20283.041 | Infra - Brick Masonry 18" M-Sand | Material
32 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Sand | Silica Sand | cuft | 969.6 | 50 | 48480 | 737.635 | 694.15 | 43.485 | 36881.766 | 34707.5 | 2174.266 | Infra - Brick Masonry 18" Silica Sand | Material
33 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18" | cuft | 1000 | Civil Raw Material-Sand | Stone Dust | cuft | 249.6 | 50 | 12480 | 189.886 | 0 | 189.886 | 9494.316 | 0 | 9494.316 | Infra - Brick Masonry 18" Stone Dust | Material
35 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Bricks | Earthen Bricks | nos | 29275.05 | 6 | 175650.3 | 6038.188 | 8371.445 | -2333.257 | 36229.129 | 32291.491 | 3937.638 | Infra - Brick Masonry 4.5 Earthen Bricks | Material
36 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Cement | Cement PPC | bags | 82.915 | 210.94 | 17490.09 | 17.434 | 23.112 | -5.678 | 3677.504 | 5006.705 | -1329.201 | Infra - Brick Masonry 4.5 Cement PPC | Material
37 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Sand | M-Sand | cuft | 525.3 | 50 | 26265 | 94.804 | 0 | 94.804 | 4740.176 | 0 | 4740.176 | Infra - Brick Masonry 4.5 M-Sand | Material
38 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Sand | Silica Sand | cuft | 145.26 | 50 | 7263 | 26.216 | 175.065 | -148.849 | 1310.79 | 8753.25 | -7442.46 | Infra - Brick Masonry 4.5 Silica Sand | Material
39 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Sand | Stone Dust | cuft | 338.94 | 40 | 13557.6 | 61.17 | 80 | -18.83 | 2446.808 | 1800 | 646.808 | Infra - Brick Masonry 4.5 Stone Dust | Material
41 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Bricks | Earthen Bricks | nos | 52745.175 | 6 | 316471.05 | 44008.906 | 41373.717 | 2635.189 | 264053.438 | 165644.125 | 98409.313 | Infra - Brick Masonry 9 Earthen Bricks | Material
42 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Cement | Cement PPC | bags | 119.995 | 220 | 52797.8 | 102.064 | 117.485 | -15.421 | 22454.105 | 25996.381 | -3542.276 | Infra - Brick Masonry 9 Cement PPC | Material
43 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Sand | M-Sand | cuft | 1050.6 | 50 | 52530 | 767.014 | 142 | 625.014 | 38350.7 | 4930 | 33420.7 | Infra - Brick Masonry 9 M-Sand | Material
44 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Sand | Silica Sand | cuft | 840.48 | 50 | 42024 | 613.611 | 1317.236 | -703.625 | 30680.56 | 65861.8 | -35181.24 | Infra - Brick Masonry 9 Silica Sand | Material
45 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Sand | Stone Dust | cuft | 210.12 | 50 | 10506 | 153.403 | 160 | -6.597 | 7670.14 | 3600 | 4070.14 | Infra - Brick Masonry 9 Stone Dust | Material
49 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IEPLS | Infra - External Plaster | sqft | 10000 | Civil Raw Material-Cement | Cement PPC | bags | 170.98 | 210.94 | 36066.52 | 31.686 | 34.028 | -2.342 | 6683.862 | 7398.74 | -714.878 | Infra - External Plaster Cement PPC | Material
50 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IEPLS | Infra - External Plaster | sqft | 10000 | Civil Raw Material-Sand | M-Sand | cuft | 1248 | 50 | 62400 | 198.515 | 62 | 136.515 | 9925.76 | 2170 | 7755.76 | Infra - External Plaster M-Sand | Material
51 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IEPLS | Infra - External Plaster | sqft | 10000 | Civil Raw Material-Sand | Silica Sand | cuft | 1244.4 | 50 | 62220 | 197.943 | 338.971 | -141.028 | 9897.128 | 16948.55 | -7051.422 | Infra - External Plaster Silica Sand | Material
56 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IIPLS | Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Cement | Cement PPC | bags | 100.94 | 210.94 | 21292.28 | 41.445 | 45.99 | -4.545 | 8742.424 | 10005.182 | -1262.758 | Infra - Internal Plaster Cement PPC | Material
57 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IIPLS | Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Misc | Fibre Mesh | mtr | 1000 | 4.8 | 4800 | 422.909 | 0 | 422.909 | 2029.963 | 0 | 2029.963 | Infra - Internal Plaster Fibre Mesh | Material
58 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IIPLS | Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Sand | M-Sand | cuft | 882 | 50 | 44100 | 310.838 | 30 | 280.838 | 15541.902 | 1020 | 14521.902 | Infra - Internal Plaster M-Sand | Material
59 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IIPLS | Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Sand | Silica Sand | cuft | 882 | 50 | 44100 | 310.838 | 552.292 | -241.454 | 15541.902 | 27614.6 | -12072.698 | Infra - Internal Plaster Silica Sand | Material
62 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--ILHFW | Infra - Labour Hutment Fabrication | nos | 150 | Site Infra Items-GI Sheet | GI Sheet 10x4 | nos | 600 | 1200 | 720000 | 480 | 0 | 480 | 576000 | 0 | 576000 | Infra - Labour Hutment Fabrication GI Sheet 10x4 | Material
63 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--ILHFW | Infra - Labour Hutment Fabrication | nos | 150 | Site Infra Items-GI Sheet | GI Sheet 8x4 | nos | 750 | 1100 | 825000 | 600 | 0 | 600 | 660000 | 0 | 660000 | Infra - Labour Hutment Fabrication GI Sheet 8x4 | Material
64 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Cement | Cement PPC | bags | 466.59 | 210.94 | 98422.49 | 435.714 | 436.702 | -0.988 | 91909.505 | 93909.592 | -2000.086 | Infra - PCC Work Cement PPC | Material
65 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 10 MM | cuft | 2475 | 22 | 54450 | 2164.142 | 1710 | 454.142 | 47611.129 | 39330 | 8281.129 | Infra - PCC Work Grit 10 MM | Material
66 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 20 MM | cuft | 2475 | 27 | 66825 | 2164.142 | 144 | 2020.142 | 58431.841 | 3932 | 54499.841 | Infra - PCC Work Grit 20 MM | Material
67 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Sand | Silica Sand | cuft | 225 | 50 | 11250 | 216.414 | 0 | 216.414 | 10820.711 | 0 | 10820.711 | Infra - PCC Work Silica Sand | Material
68 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Sand | Stone Dust | cuft | 2430 | 40 | 97200 | 1947.728 | 1290 | 657.728 | 77909.121 | 29025 | 48884.121 | Infra - PCC Work Stone Dust | Material
72 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Cement | Cement PPC | bags | 1004.25 | 210.94 | 211836.5 | 0 | 0 | 0 | 0 | 0 | 0 | Infra - RCC Work Cement PPC | Material
73 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Chemical | Admixture PC Based | kg | 200 | 50 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | Infra - RCC Work Admixture PC Based | Material
74 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 10 MM | cuft | 2134 | 22 | 46948 | 0 | 0 | 0 | 0 | 0 | 0 | Infra - RCC Work Grit 10 MM | Material
75 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 20 MM | cuft | 2543.2 | 27 | 68666.4 | 0 | 0 | 0 | 0 | 0 | 0 | Infra - RCC Work Grit 20 MM | Material
76 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Sand | M-Sand | cuft | 2275 | 40 | 91000 | 0 | 0 | 0 | 0 | 0 | 0 | Infra - RCC Work M-Sand | Material
78 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Misc | Binding Wire | kg | 250 | 70 | 17500 | 92.71 | 0 | 92.71 | 6489.7 | 0 | 6489.7 | Infra - Reinforcement Work Binding Wire | Material
79 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 08 MM | MT | 5 | 55000 | 275000 | 1.854 | 0 | 1.854 | 101981 | 0 | 101981 | Infra - Reinforcement Work TMT Steel 08 MM | Material
80 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 10 MM | MT | 5 | 55000 | 275000 | 1.854 | 0 | 1.854 | 101981 | 0 | 101981 | Infra - Reinforcement Work TMT Steel 10 MM | Material
81 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 12 MM | MT | 5 | 55000 | 275000 | 1.854 | 0 | 1.854 | 101981 | 0 | 101981 | Infra - Reinforcement Work TMT Steel 12 MM | Material
82 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 16 MM | MT | 5 | 55000 | 275000 | 1.854 | 0 | 1.854 | 101981 | 0 | 101981 | Infra - Reinforcement Work TMT Steel 16 MM | Material
83 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 20 MM | MT | 5 | 55000 | 275000 | 1.854 | 0 | 1.854 | 101981 | 0 | 101981 | Infra - Reinforcement Work TMT Steel 20 MM | Material
87 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW16mm | Coupler Fixing 16mm Dia | nos | 7000 | Civil Raw Material-Coupler | Coupler 16 16 MM | nos | 7000 | 220 | 1540000 | 0 | 22 | -22 | 0 | 618.2 | -618.2 | Coupler Fixing 16mm Dia Coupler 16 16 MM | Material
89 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW20mm | Coupler Fixing 20mm Dia | nos | 4600 | Civil Raw Material-Coupler | Coupler 20 20 MM | nos | 4600 | 220 | 1012000 | 4165 | 4175 | -10 | 916300 | 164912.5 | 751387.5 | Coupler Fixing 20mm Dia Coupler 20 20 MM | Material
91 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW25X20mm | Coupler Fixing 25mm X 20mm Dia | nos | 3650 | Civil Raw Material-Coupler | Coupler 25 20 MM | nos | 3650 | 220 | 803000 | 3586 | 3517 | 69 | 788920 | 281360 | 507560 | Coupler Fixing 25mm X 20mm Dia Coupler 25 20 MM | Material
93 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW25mm | Coupler Fixing 25mm Dia | nos | 5676 | Civil Raw Material-Coupler | Coupler 25 25 MM | nos | 5676 | 220 | 1248720 | 5567 | 5585 | -18 | 1224740 | 341802 | 882938 | Coupler Fixing 25mm Dia Coupler 25 25 MM | Material
95 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW32X20mm | Coupler Fixing 32mm X 20mm Dia | nos | 100 | Civil Raw Material-Coupler | Coupler 32 20 MM | nos | 100 | 220 | 22000 | 26 | 5 | 21 | 5720 | 625 | 5095 | Coupler Fixing 32mm X 20mm Dia Coupler 32 20 MM | Material
97 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW32X25mm | Coupler Fixing 32mm X 25mm Dia | nos | 2350 | Civil Raw Material-Coupler | Coupler 32 25 MM | nos | 2350 | 220 | 517000 | 2225 | 2264 | -39 | 489500 | 283000 | 206500 | Coupler Fixing 32mm X 25mm Dia Coupler 32 25 MM | Material
99 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW32mm | Coupler Fixing 32mm Dia | nos | 5070 | Civil Raw Material-Coupler | Coupler 32 32 MM | nos | 5070 | 220 | 1115400 | 4859 | 4974 | -115 | 1068980 | 469545.6 | 599434.4 | Coupler Fixing 32mm Dia Coupler 32 32 MM | Material
101 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW40X25mm | Coupler Fixing 40mm X 25mm Dia | nos | 500 | Civil Raw Material-Coupler | Coupler 40 25 MM | nos | 500 | 220 | 110000 | 44 | 41 | 3 | 9680 | 10742 | -1062 | Coupler Fixing 40mm X 25mm Dia Coupler 40 25 MM | Material
103 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW40X32mm | Coupler Fixing 40mm X 32mm Dia | nos | 850 | Civil Raw Material-Coupler | Coupler 40 32 MM | nos | 850 | 220 | 187000 | 722 | 864 | -142 | 158840 | 226368 | -67528 | Coupler Fixing 40mm X 32mm Dia Coupler 40 32 MM | Material
105 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW40mm | Coupler Fixing 40mm Dia | nos | 1354 | Civil Raw Material-Coupler | Coupler 40 40 MM | nos | 1354 | 220 | 297880 | 1348 | 1357 | -9 | 296560 | 284970 | 11590 | Coupler Fixing 40mm Dia Coupler 40 40 MM | Material
107 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial--RCCFM25 | RCC Footing - M25 | cuft | 520 | Civil Raw Material-RMC | RMC M-25 | cum | 14.726 | 3600 | 53013.6 | 10.5 | 10.5 | 0 | 37799.214 | 24937.5 | 12861.714 | RCC Footing - M25 RMC M-25 | Material
109 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial--RCCRW35 | RCC - Ramp - M-35 | cuft | 9646.94 | Civil Raw Material-RMC | RMC M-35 | cum | 270.114 | 4000 | 1080456 | 0 | 0 | 0 | 0 | 0 | 0 | RCC - Ramp - M-35 RMC M-35 | Material
111 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--RMC7.5IPCC | Infra - M7.5 PCC Work | cuft | 1000 | Civil Raw Material-RMC | RMC M-7.5 | cum | 28.31 | 86.38 | 2445.42 | 6.498 | 6.5 | -0.002 | 561.26 | 17221.2 | -16659.94 | Infra - M7.5 PCC Work RMC M-7.5 | Material
123 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SASO | Site Office | lumpsum | 1 | Site Infra Items-Porta Cabin | Office Container Cabin | nos | 1 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Site Office Office Container Cabin | Material
127 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SATOILT | Toilets | lumpsum | 1 | Site Infra Items-Porta Cabin | Container Portable Toilet | nos | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | Toilets Container Portable Toilet | Material
130 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial--WTCRCCMLWM35 | RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Civil Raw Material-Cement | Cement PPC | bags | 298.906 | 225 | 67253.85 | 0 | 152 | -152 | 0 | 33425.75 | -33425.75 | RCC M-35 (Manual) Ledge wall Cement PPC | Material
131 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial--WTCRCCMLWM35 | RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Civil Raw Material-Grit | Grit 10 MM | cuft | 498.607 | 23 | 11467.96 | 0 | 745 | -745 | 0 | 20115 | -20115 | RCC M-35 (Manual) Ledge wall Grit 10 MM | Material
132 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial--WTCRCCMLWM35 | RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Civil Raw Material-Grit | Grit 20 MM | cuft | 599.101 | 28 | 16774.83 | 0 | 0 | 0 | 0 | 0 | 0 | RCC M-35 (Manual) Ledge wall Grit 20 MM | Material
133 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial--WTCRCCMLWM35 | RCC M-35 (Manual) Ledge wall | cuft | 1288.39 | Civil Raw Material-Sand | M-Sand | cuft | 556.584 | 40 | 22263.36 | 0 | 216.35 | -216.35 | 0 | 8654 | -8654 | RCC M-35 (Manual) Ledge wall M-Sand | Material
134 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial--WTCRCCSBM40 | RCC - Slab & beam M-40 | cuft | 353.147 | Civil Raw Material-RMC | RMC M-40 | cum | 10.001 | 4200 | 42004.2 | 6.5 | 6.5 | -1.5665e-08 | 27300 | 29412.5 | -2112.5 | RCC - Slab & beam M-40 RMC M-40 | Material
136 | WTC Commercial | WTC Commercial | ATT Work | WTC-WTC Commercial-ALL-ATTWBF | ATT Work - Below Footing | sqft | 9687.01 | Civil Raw Material-Chemical | Anti Termite Chemical | ltr | 104232.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ATT Work - Below Footing Anti Termite Chemical | Material
138 | WTC Commercial | WTC Commercial | BRICK BAT COBA | WTC-WTC Commercial-ALL-BBCWT | Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Bricks | Bricks Bat | cuft | 15964.403 | 25 | 399110.08 | 0 | 0 | 0 | 0 | 0 | 0 | Brick Bat Coba Work on Terrace Bricks Bat | Material
139 | WTC Commercial | WTC Commercial | BRICK BAT COBA | WTC-WTC Commercial-ALL-BBCWT | Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Cement | Cement PPC | bags | 1859.927 | 210.94 | 392333 | 0 | 0 | 0 | 0 | 0 | 0 | Brick Bat Coba Work on Terrace Cement PPC | Material
140 | WTC Commercial | WTC Commercial | BRICK BAT COBA | WTC-WTC Commercial-ALL-BBCWT | Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Chemical | Waterproofing Chemical | kg | 478.98 | 50 | 23949 | 0 | 0 | 0 | 0 | 0 | 0 | Brick Bat Coba Work on Terrace Waterproofing Chemical | Material
141 | WTC Commercial | WTC Commercial | BRICK BAT COBA | WTC-WTC Commercial-ALL-BBCWT | Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Sand | M-Sand | cuft | 16685.747 | 40 | 667429.88 | 0 | 0 | 0 | 0 | 0 | 0 | Brick Bat Coba Work on Terrace M-Sand | Material
143 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5" Thick | sqft | 28702.63 | Civil Raw Material-Bricks | Earthen Bricks | nos | 14351.315 | 7 | 100459.21 | 13665.408 | 1094 | 12571.408 | 95657.853 | 4157.2 | 91500.653 | Brick Masonry 4.5" Thick Earthen Bricks | Material
144 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5" Thick | sqft | 28702.63 | Civil Raw Material-Bricks | Flyash Bricks | nos | 168054.186 | 7 | 1176379.3 | 152402.091 | 106227 | 46175.091 | 1066814.634 | 579892.5 | 486922.134 | Brick Masonry 4.5" Thick Flyash Bricks | Material
145 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5" Thick | sqft | 28702.63 | Civil Raw Material-Cement | Cement PPC | bags | 487.801 | 210.94 | 102896.74 | 450.958 | 358.5 | 92.458 | 95125.175 | 76012.275 | 19112.9 | Brick Masonry 4.5" Thick Cement PPC | Material
146 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5" Thick | sqft | 28702.63 | Civil Raw Material-Sand | M-Sand | cuft | 3084.385 | 50 | 154219.25 | 2447.474 | 3561 | -1113.526 | 122373.724 | 141894.15 | -19520.426 | Brick Masonry 4.5" Thick M-Sand | Material
147 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5" Thick | sqft | 28702.63 | Civil Raw Material-Sand | Silica Sand | cuft | 2779.563 | 50 | 138978.15 | 2205.597 | 19 | 2186.597 | 110279.839 | 950 | 109329.839 | Brick Masonry 4.5" Thick Silica Sand | Material
149 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9" Thick | sqft | 94538 | Civil Raw Material-Bricks | Earthen Bricks | nos | 94538 | 7 | 661766 | 87859.129 | 24043.028 | 63816.101 | 615013.903 | 99135.106 | 515878.797 | Brick Masonry 9" Thick Earthen Bricks | Material
150 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9" Thick | sqft | 94538 | Civil Raw Material-Bricks | Flyash Bricks | nos | 997284.671 | 7 | 6980992.7 | 882694.311 | 663993 | 218701.311 | 6178860.179 | 3618873.5 | 2559986.679 | Brick Masonry 9" Thick Flyash Bricks | Material
151 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9" Thick | sqft | 94538 | Civil Raw Material-Cement | Cement PPC | bags | 2268.817 | 210.94 | 478584.26 | 2047.118 | 2422.64 | -375.522 | 431819.009 | 515431.453 | -83612.444 | Brick Masonry 9" Thick Cement PPC | Material
152 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9" Thick | sqft | 94538 | Civil Raw Material-Sand | M-Sand | cuft | 8276.802 | 50 | 413840.1 | 7692.067 | 20151.19 | -12459.123 | 384603.337 | 798478.86 | -413875.523 | Brick Masonry 9" Thick M-Sand | Material
153 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9" Thick | sqft | 94538 | Civil Raw Material-Sand | Silica Sand | cuft | 8276.802 | 50 | 413840.1 | 7692.067 | 138.75 | 7553.317 | 384603.337 | 6937.5 | 377665.837 | Brick Masonry 9" Thick Silica Sand | Material
157 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 149886 | Civil Raw Material-Cement | Cement PPC | bags | 2562.751 | 210.94 | 540586.7 | 786.04 | 497 | 289.04 | 165807.182 | 111404.17 | 54403.012 | Plaster - External Cement PPC | Material
158 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 149886 | Civil Raw Material-Chemical | Waterproofing Chemical | kg | 449.658 | 50 | 22482.9 | 142.055 | 0 | 142.055 | 7102.767 | 0 | 7102.767 | Plaster - External Waterproofing Chemical | Material
159 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 149886 | Civil Raw Material-Misc | Fibre Mesh | mtr | 14988.6 | 4.8 | 71945.28 | 4735.178 | 400 | 4335.178 | 22728.854 | 1680 | 21048.854 | Plaster - External Fibre Mesh | Material
160 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 149886 | Civil Raw Material-Sand | M-Sand | cuft | 18705.773 | 50 | 935288.65 | 4924.585 | 0 | 4924.585 | 246229.256 | 0 | 246229.256 | Plaster - External M-Sand | Material
161 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 149886 | Civil Raw Material-Sand | Silica Sand | cuft | 18651.814 | 50 | 932590.7 | 4910.38 | 3338 | 1572.38 | 245518.979 | 166900 | 78618.979 | Plaster - External Silica Sand | Material
163 | WTC Commercial | WTC Commercial | INTERNAL PLASTER | WTC-WTC Commercial-ALL-INTPL | Plaster - Internal | sqft | 390934 | Civil Raw Material-Cement | Cement PPC | bags | 6684.19 | 210.94 | 1409963.04 | 6195.429 | 3788 | 2407.429 | 1306863.715 | 809910.01 | 496953.705 | Plaster - Internal Cement PPC | Material
164 | WTC Commercial | WTC Commercial | INTERNAL PLASTER | WTC-WTC Commercial-ALL-INTPL | Plaster - Internal | sqft | 390934 | Civil Raw Material-Misc | Fibre Mesh | mtr | 39093.4 | 4.8 | 187648.32 | 37321.859 | 2200 | 35121.859 | 179144.924 | 9240 | 169904.924 | Plaster - Internal Fibre Mesh | Material
165 | WTC Commercial | WTC Commercial | INTERNAL PLASTER | WTC-WTC Commercial-ALL-INTPL | Plaster - Internal | sqft | 390934 | Civil Raw Material-Sand | M-Sand | cuft | 17216.733 | 50 | 860836.65 | 13697.122 | 0 | 13697.122 | 684856.116 | 0 | 684856.116 | Plaster - Internal M-Sand | Material
166 | WTC Commercial | WTC Commercial | INTERNAL PLASTER | WTC-WTC Commercial-ALL-INTPL | Plaster - Internal | sqft | 390934 | Civil Raw Material-Sand | Silica Sand | cuft | 34480.379 | 50 | 1724018.95 | 27431.567 | 33792 | -6360.433 | 1371578.326 | 1689600 | -318021.674 | Plaster - Internal Silica Sand | Material
169 | WTC Commercial | WTC Commercial | PLAIN CEMENT CONCRETE | WTC-WTC Commercial-ALL-PCC7.5 | Below Footing PCC M7.5 | cuft | 29000 | Civil Raw Material-RMC | RMC M-7.5 | cum | 821.297 | 3000 | 2463891 | 819 | 966.5 | -147.5 | 2457000.948 | 2521985.68 | -64984.732 | Below Footing PCC M7.5 RMC M-7.5 | Material
171 | WTC Commercial | WTC Commercial | PLAIN CEMENT CONCRETE | WTC-WTC Commercial-ALL-PCCBFLM7.5 | Below Floor PCC M7.5 | cuft | 24599 | Civil Raw Material-RMC | RMC M-7.5 | cum | 696.658 | 3000 | 2089974 | 556.013 | 410.5 | 145.513 | 1668039.726 | 1067681.86 | 600357.866 | Below Floor PCC M7.5 RMC M-7.5 | Material
173 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCCLM35 | RCC - Column,Walls- M35 | cuft | 177000 | Civil Raw Material-RMC | RMC M-35 | cum | 5012.744 | 4000 | 20050976 | 4821.013 | 4419 | 402.013 | 19284053.604 | 11639583.615 | 7644469.989 | RCC - Column,Walls- M35 RMC M-35 | Material
175 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCCLM45 | RCC - Column - M45 | cuft | 335.45 | Civil Raw Material-RMC | RMC M-45 | cum | 9.5 | 4200 | 39900 | 9.5 | 9.5 | 1.065e-08 | 39900 | 21850 | 18050 | RCC - Column - M45 RMC M-45 | Material
177 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCCWM50 | RCC - Column & Wall - M-50 | cuft | 141.256 | Civil Raw Material-RMC | RMC M-50 | cum | 3.5 | 4000 | 14000 | 3.5 | 3.5 | -8.435e-09 | 14000 | 18033.89 | -4033.89 | RCC - Column & Wall - M-50 RMC M-50 | Material
179 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCFM30 | RCC Footing - M30 | cuft | 300600 | Civil Raw Material-RMC | RMC M-30 | cum | 8513.169 | 3800 | 31934850.4 | 8407.551 | 8407 | 0.551 | 31948692.027 | 25377612.7 | 6571079.327 | RCC Footing - M30 RMC M-30 | Material
181 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCSBM35 | RCC - Slab & beam | cuft | 746725.91 | Civil Raw Material-RMC | RMC M-35 | cum | 21147.718 | 4000 | 84590872 | 20425.498 | 20797.5 | -372.002 | 81701992.44 | 51949586.07 | 29752406.37 | RCC - Slab & beam RMC M-35 | Material
183 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCSSM25 | RCC - Stiching Slab - M25 | cuft | 11800 | Civil Raw Material-RMC | RMC M-25 | cum | 334.183 | 3600 | 1203058.8 | 331.501 | 350.5 | -18.999 | 1193402.036 | 1027487.9 | 165914.136 | RCC - Stiching Slab - M25 RMC M-25 | Material
193 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Raw Material-Cover Block | Cover Block 20 MM | nos | 87698.896 | 1 | 87698.9 | 86406.359 | 150000 | -63593.641 | 86406.359 | 48132 | 38274.359 | Shuttering Work Cover Block 20 MM | Material
194 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Raw Material-Cover Block | Cover Block 25 MM | nos | 79995.268 | 1 | 79995.27 | 78816.27 | 93100 | -14283.73 | 78816.27 | 48690 | 30126.27 | Shuttering Work Cover Block 25 MM | Material
195 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Raw Material-Cover Block | Cover Block 50 MM | nos | 80113.429 | 1 | 80113.43 | 78932.689 | 15300 | 63632.689 | 78932.689 | 24690 | 54242.689 | Shuttering Work Cover Block 50 MM | Material
196 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Raw Material-Cover Block | Cover Block L Shape 40 MM | nos | 80113.429 | 1 | 80113.43 | 78932.689 | 18564 | 60368.689 | 78932.689 | 18479.75 | 60452.939 | Shuttering Work Cover Block L Shape 40 MM | Material
197 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Raw Material-Misc | Shuttering Oil | ltr | 4135.649 | 65 | 268817.19 | 4074.696 | 3245 | 829.696 | 264855.263 | 197767.05 | 67088.213 | Shuttering Work Shuttering Oil | Material
198 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Shuttering-Batten (Mirandi) | Batten 3x2.5x10 (Mirandi) | nos | 3544.842 | 650 | 2304147.3 | 3492.597 | 1052 | 2440.597 | 2270187.972 | 552573.32 | 1717614.652 | Shuttering Work Batten 3x2.5x10 (Mirandi) | Material
199 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Shuttering-Batten (Pine) | Batten 2x2.5x8 (Pine) | nos | 31383.668 | 200 | 6276733.6 | 30921.124 | 16855 | 14066.124 | 6184224.876 | 3138407.49 | 3045817.386 | Shuttering Work Batten 2x2.5x8 (Pine) | Material
200 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Shuttering-Batten (Pine) | Batten 2.25x1.5x8 (Pine) | nos | 10634.526 | 150 | 1595178.9 | 10477.791 | 9188 | 1289.791 | 1571668.596 | 1106240.64 | 465427.956 | Shuttering Work Batten 2.25x1.5x8 (Pine) | Material
201 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Shuttering-Misc | Shuttering Tape Brown | nos | 1417.937 | 75 | 106345.28 | 1397.039 | 17 | 1380.039 | 104777.906 | 429.16 | 104348.746 | Shuttering Work Shuttering Tape Brown | Material
202 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Shuttering-Misc | Shuttering Tape White | nos | 118.161 | 75 | 8862.08 | 116.42 | 0 | 116.42 | 8731.492 | 0 | 8731.492 | Shuttering Work Shuttering Tape White | Material
203 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Shuttering-Ply | Old Ply Scrap All Size | nos | 3922.958 | 70 | 274607.06 | 3865.141 | 11 | 3854.141 | 270559.838 | 650 | 269909.838 | Shuttering Work Old Ply Scrap All Size | Material
204 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Civil Shuttering-Ply | Shuttering Ply 8x4x12 MM | nos | 3922.958 | 2000 | 7845916 | 3865.141 | 1830 | 2035.141 | 7730281.094 | 3563280.85 | 4167000.244 | Shuttering Work Shuttering Ply 8x4x12 MM | Material
205 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Consumable Material-Nails | Nails 2 | kg | 7089.684 | 65 | 460829.46 | 6985.194 | 1760 | 5225.194 | 454037.594 | 94968.99 | 359068.604 | Shuttering Work Nails 2 | Material
206 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Consumable Material-Nails | Nails 3 | kg | 8271.298 | 65 | 537634.37 | 8149.393 | 5961 | 2188.393 | 529710.527 | 310313.15 | 219397.377 | Shuttering Work Nails 3 | Material
207 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1181614 | Consumable Material-Nails | Nails 4 | kg | 8271.298 | 65 | 537634.37 | 8149.393 | 3479 | 4670.393 | 529710.527 | 179003.17 | 350707.357 | Shuttering Work Nails 4 | Material
211 | WTC Commercial | WTC Commercial | PONDING WORK | WTC-WTC Commercial-ALL-SPW | Slab Ponding Work | sqft | 800000 | Civil Raw Material-Cement | Cement PPC | bags | 494.4 | 210.94 | 104288.74 | 0.016 | 63.5 | -63.484 | 3.306 | 13003.305 | -12999.999 | Slab Ponding Work Cement PPC | Material
212 | WTC Commercial | WTC Commercial | PONDING WORK | WTC-WTC Commercial-ALL-SPW | Slab Ponding Work | sqft | 800000 | Civil Raw Material-Sand | Silica Sand | cuft | 7296 | 50 | 364800 | 0.199 | 0 | 0.199 | 9.928 | 0 | 9.928 | Slab Ponding Work Silica Sand | Material
213 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 4405 | Civil Raw Material-Misc | Binding Wire | kg | 44050 | 70 | 3083500 | 43221.23 | 25910 | 17311.23 | 3025486.1 | 1492846.19 | 1532639.91 | Steel Binding Work Binding Wire | Material
214 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 08 MM | MT | 453.715 | 55080 | 24990622.2 | 432.212 | 222.716 | 209.496 | 23806253.484 | 10428587.481 | 13377666.003 | Steel Binding Work TMT Steel 08 MM | Material
215 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 10 MM | MT | 907.43 | 55080 | 49981244.4 | 864.425 | 1149.718 | -285.293 | 47612506.968 | 42903203.327 | 4709303.641 | Steel Binding Work TMT Steel 10 MM | Material
216 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 12 MM | MT | 453.715 | 55080 | 24990622.2 | 432.212 | 447.993 | -15.781 | 23806253.484 | 17402648.484 | 6403605 | Steel Binding Work TMT Steel 12 MM | Material
217 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 16 MM | MT | 453.715 | 55080 | 24990622.2 | 432.212 | 206.964 | 225.248 | 23806253.484 | 9510994.218 | 14295259.266 | Steel Binding Work TMT Steel 16 MM | Material
218 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 20 MM | MT | 453.715 | 55080 | 24990622.2 | 432.212 | 264.287 | 167.925 | 23806253.484 | 12772243.5 | 11034009.984 | Steel Binding Work TMT Steel 20 MM | Material
219 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 25 MM | MT | 907.43 | 55080 | 49981244.4 | 864.425 | 1634.008 | -769.583 | 47612506.968 | 71833724.348 | -24221217.38 | Steel Binding Work TMT Steel 25 MM | Material
220 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 32 MM | MT | 453.715 | 55080 | 24990622.2 | 432.212 | 407.467 | 24.745 | 23806253.484 | 20752841.707 | 3053411.777 | Steel Binding Work TMT Steel 32 MM | Material
221 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 4405 | Civil Raw Material-Steel | TMT Steel 40 MM | MT | 453.715 | 55080 | 24990622.2 | 432.212 | 94.224 | 337.988 | 23806253.484 | 5275485.5 | 18530767.984 | Steel Binding Work TMT Steel 40 MM | Material
229 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-WTCRCCM15PS | RCC M-15 Podium Slab | cuft | 11608 | Civil Raw Material-RMC | RMC M-15 | cum | 328.506 | 3450 | 1133345.7 | 171.875 | 172 | -0.125 | 592968.598 | 405600 | 187368.598 | RCC M-15 Podium Slab RMC M-15 | Material
231 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-WTCRCCM25 | RCC - Column & Wall - M-25 | cuft | 18530 | Civil Raw Material-RMC | RMC M-25 | cum | 524.711 | 3600 | 1888959.6 | 324.957 | 285 | 39.957 | 1169845.309 | 671800 | 498045.309 | RCC - Column & Wall - M-25 RMC M-25 | Material

## WBS Wise Estimate
Report Type : Material Reconciliation Report
Project Name : WTC Commercial
Generated on: 2026-07-13 18:37:06
Parent WBS Name | Est Amt
ATT Work | 0
BRICK BAT COBA | 1482821.96
BRICK MASONRY | 10621955.81
EXTERNAL PLASTER | 2502894.23
INTERNAL PLASTER | 4182466.96
MS COUPLER WORK | 6853000
PLAIN CEMENT CONCRETE | 4553865
PONDING WORK | 469088.74
REINFORCED CEMENT CONCRETE | 142149196.3
SHUTTERING | 20544626.64
SITE ADMINISTRATIVE EXPENSES | 1050000
SITE INFRA WORK | 4963026.25
STEEL BINDING | 252989722
Total | 452362663.89