## Bill Master
Report Type : Bill Master Report
Project Name : RHB Greenwood Mansion
Generated on: 2026-07-01 15:40:07
Item Group | Particulars | Unit | AARYAN ARTS |  |  | AMAN INDUSTRIAL SECURITY AGENCY |  |  | BHABEN BARMEN |  |  | C M B SANITATION |  |  | DEV PLUMBING AND SANITARY CONTRACTOR |  |  | DIPU DAS |  |  | Deviram |  |  | FORCE 10 SECURITY SERVICES |  |  | Fortune Creations |  |  | Global Chowk Labour |  |  | Global Departmental Labour |  |  | Global Site Overheads |  |  | IDEAS |  |  | JEET SINGH |  |  | KAMAL BARMAN |  |  | KANWAR ENTERPRISES |  |  | L2G PROJECTS |  |  | LR PLUMBRING SERVICES |  |  | M/S GOPAL LAL YADAV |  |  | M/S MOHAMMAD BELAL |  |  | M/s Vimla |  |  | MD EHSAN |  |  | MOHAMMAD RASHID |  |  | Md.Jakir |  |  | N.R.ENTERPRISES |  |  | NAGAR STEEL AND FABRICATION |  |  | NK CONSTRUCTION COMPANY |  |  | National Pest Management Service |  |  | Pramod Kumar Sahu |  |  | RAJESH JANGID |  |  | Rajveer Singh |  |  | Ramkishan |  |  | Raviraj |  |  | S. N. STEEL |  |  | SAVAN SONI |  |  | SHIV POOJAN VERMA |  |  | SHYAM CONSTRUCTION GROUP |  |  | SOL TECHNO |  |  | SONI ENTERPRISES |  |  | TEAM INFRASTRUCTURES |  |  | Tanwar Security Services |  |  | Grand Total
|  |  | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount | Billed Qty | Billed Rate | Billed Amount
Hire & Rent | Earth Compactor Roller | Rs. | [54 empty] | 5.35 | 70000 | 374500 | [66 empty] | 5.35 | 70000 | 374500
Hire & Rent | JCB & Dumper Hire Charges for Debris Removal (Per Trip) | per trip | [54 empty] | 344.5 | 1574.75 | 542500 | [66 empty] | 344.5 | 1574.75 | 542500
Hire & Rent | JCB Excavator (Poclain) Hire Charges 140 for Excavation 9 (Hours) | perhour | [54 empty] | 23.55 | 1800 | 42390 | [66 empty] | 23.55 | 1800 | 42390
Hire & Rent | JCB HIRE CHARGE | hours | [54 empty] | 1084.86 | 850 | 922135 | [66 empty] | 1084.86 | 850 | 922135
Hire & Rent | Vehicle Hire Charges | lumpsum | [90 empty] | 13 | 25000 | 325000 | [30 empty] | 13 | 25000 | 325000
Labour Charges for Supply to Company | Skilled Labour | nos | [45 empty] | 12.5 | 600 | 7500 | [24 empty] | 2 | 600 | 1200 | [18 empty] | 36 | 750 | 27000 | 18.5 | 550 | 10175 | [24 empty] | 69 | 664.86 | 45875
Labour Charges for Supply to Company | Unskilled Labour | nos | [45 empty] | 45.5 | 350 | 15925 | [24 empty] | 6 | 350 | 2100 | [18 empty] | 38.5 | 500 | 19250 | 18.5 | 350 | 6475 | [24 empty] | 108.5 | 403.23 | 43750
Labour-Aluminium Work | Aluminium Work Window/Door Fixing | sqft | [24 empty] | 313.07 | 340 | 106444 | [96 empty] | 313.07 | 340 | 106444
Labour-Civil-Concreting Work | Concreting Work RCC | cuft | [96 empty] | 5.5 | 120 | 660 | [24 empty] | 5.5 | 120 | 660
Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | [30 empty] | 9544.69 | 4.09 | 39011 | [60 empty] | 5904.79 | 10 | 59049 | [27 empty] | 15449.48 | 6.35 | 98060
Labour-Civil-Concreting Work | Concreting Work With RMC M-30 | cuft | [30 empty] | 1100.2 | 3.28 | 3610 | [90 empty] | 1100.2 | 3.28 | 3610
Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | [30 empty] | 1674.74 | 4.69 | 7847 | [90 empty] | 1674.74 | 4.69 | 7847
Labour-Civil-Construction Work | Brick Works | sqft | [45 empty] | 53321.19 | 30 | 1599636 | [75 empty] | 53321.19 | 30 | 1599636
Labour-Civil-Construction Work | Internal Plaster Work and Chokhat Fixing | sqft | [45 empty] | 37962.36 | 20 | 759247 | [75 empty] | 37962.36 | 20 | 759247
Labour-Civil-Construction Work | PCC Foundation Casting of Blocks | sqft | [45 empty] | 114657.01 | 20 | 2293141 | [75 empty] | 114657.01 | 20 | 2293141
Labour-Civil-Construction Work | PCC Under Floor & Stitching Slabs | sqft | [45 empty] | 114657.01 | 10 | 1146570 | [75 empty] | 114657.01 | 10 | 1146570
Labour-Civil-Construction Work | RCC Columns & Casting of RCC Slabs | sqft | [45 empty] | 76037.32 | 80 | 6082986 | [75 empty] | 76037.32 | 80 | 6082986
Labour-Civil-Construction Work | Work upto Plinth Beam of Blocks | sqft | [45 empty] | 95223.82 | 10 | 952239 | [75 empty] | 95223.82 | 10 | 952239
Labour-Civil-Earth Work | Anti Termite Treatment | sqft | [81 empty] | 116567.48 | 6 | 699404 | [39 empty] | 116567.48 | 6 | 699404
Labour-Civil-Earth Work | Back Filling Work | cuft | [30 empty] | 730.79 | 3.55 | 2597 | [21 empty] | 2906928.83 | 2 | 5824996 | [66 empty] | 2907659.62 | 2 | 5827593
Labour-Civil-Earth Work | Excavation Work | cuft | [30 empty] | 564.04 | 6.91 | 3897 | [21 empty] | 3260636.59 | 1.84 | 5997135 | [66 empty] | 3261200.63 | 1.84 | 6001032
Labour-Civil-Fabrication Work | Fabrication Work | sqft | [75 empty] | 1930 | 10 | 19300 | [45 empty] | 1930 | 10 | 19300
Labour-Civil-Fabrication Work | MS Door Frame Fabrication | kg | [99 empty] | 36487.2 | 95 | 3466284 | [21 empty] | 36487.2 | 95 | 3466284
Labour-Civil-Masonry Work | Masonry Work Brick 4.5" Thick | sqft | [30 empty] | 37.97 | 31.76 | 1206 | [60 empty] | 1860.02 | 22 | 40920 | 862.94 | 20 | 17259 |  |  |  | 1662.02 | 23 | 38226 | [18 empty] | 4422.95 | 22.07 | 97611
Labour-Civil-Masonry Work | Masonry Work Brick 9" Thick | sqft | [93 empty] | 645.52 | 22 | 14201 | 2721.4 | 22 | 59870 |  |  |  | 939.48 | 25 | 23487 | [18 empty] | 4306.4 | 22.65 | 97558
Labour-Civil-Masonry Work | Masonry Work RR Stone | cuft | [93 empty] | 1805.19 | 30 | 54156 | [27 empty] | 1805.19 | 30 | 54156
Labour-Civil-Plaster Work | Plaster Work External | sqft | [57 empty] | 1546.92 | 12 | 18563 | [24 empty] | 942.09 | 12 | 11305 | [9 empty] | 1936.47 | 10 | 19365 | [24 empty] | 4425.48 | 11.12 | 49233
Labour-Civil-Plaster Work | Plaster Work Internal | sqft | [57 empty] | 14713.93 | 9.62 | 141548 |  |  |  | 22829.42 | 9 | 205465 | [18 empty] | 21791.03 | 9 | 196120 | [9 empty] | 3799.35 | 10 | 37994 | [24 empty] | 63133.73 | 9.2 | 581127
Labour-Civil-Plaster Work | Plaster Work Internal/External Water Tank | sqft | [96 empty] | 907.92 | 10 | 9079 | [24 empty] | 907.92 | 10 | 9079
Labour-Civil-Reinforcement Work | Reinforcement Work Steel Binding | kg | [6 empty] | 2562.64 | 10 | 25626 | [21 empty] | 3771.95 | 10.28 | 38788 | [9 empty] | 14372.31 | 10 | 143723 | [24 empty] | 26544.46 | 10 | 265444 | [51 empty] | 47251.36 | 10.02 | 473581
Labour-Civil-Road Construction Work | Providing and Laying of GSB | cuft | [54 empty] | 7198.73 | 35.4 | 254835 | [66 empty] | 7198.73 | 35.4 | 254835
Labour-Civil-Scaffolding | Scaffolding | sqft | [30 empty] | 2767.42 | 5.28 | 14612 | [27 empty] | 3990.57 | 5 | 19953 | [60 empty] | 6757.99 | 5.11 | 34565
Labour-Civil-Shuttering Work | Shuttering Making Work | sqft | [6 empty] | 690.5 | 10 | 6905 | [6 empty] | 1920 | 10 | 19200 | [42 empty] | 2228.23 | 10 | 22282 | [60 empty] | 4838.73 | 10 | 48387
Labour-Civil-Shuttering Work | Shuttering Work | sqft | [6 empty] | 8339.03 | 18 | 150103 | [6 empty] | 14304.61 | 18 | 257483 | [12 empty] | 13949.13 | 13.82 | 192748 | [27 empty] | 10937.65 | 18 | 196878 | [6 empty] | 2270.55 | 18 | 40870 | [51 empty] | 49800.97 | 16.83 | 838082
Labour-Civil-Soling Work | Soling Work Brick kharanja | sqft | [96 empty] | 1610.22 | 12 | 19323 | [24 empty] | 1610.22 | 12 | 19323
Labour-Civil-Villa Construction | Brick Work | sqft | [45 empty] | 19806.61 | 38.25 | 757602 | [24 empty] | 60384.07 | 38.25 | 2309691 |  |  |  | 65324.94 | 38.25 | 2498677 | [27 empty] | 94935.3 | 38.25 | 3631275 | [12 empty] | 240450.92 | 38.25 | 9197245
Labour-Civil-Villa Construction | External Plaster Work | sqft | [78 empty] | 14195.06 | 12.75 | 180987 | [42 empty] | 14195.06 | 12.75 | 180987
Labour-Civil-Villa Construction | Internal Plaster Work with Chokhat Fixing | sqft | [45 empty] | 6177.7 | 25.5 | 157531 | [24 empty] | 17973.18 | 25.5 | 458315 |  |  |  | 23202.16 | 25.5 | 591655 | [27 empty] | 38353.22 | 25.5 | 978008 | [12 empty] | 85706.26 | 25.5 | 2185509
Labour-Civil-Villa Construction | Other Work - Railing / UG-Tank Etc | sqft | [78 empty] | 13143.57 | 12.75 | 167581 | [27 empty] | 34805.1 | 12.75 | 443765 | [12 empty] | 47948.67 | 12.75 | 611346
Labour-Civil-Villa Construction | PCC Foundation Casting of Block | sqft | [45 empty] | 28911.63 | 25.5 | 737247 | [24 empty] | 104694.36 | 25.5 | 2669706 |  |  |  | 92023.44 | 25.5 | 2346597 | [27 empty] | 152391.43 | 25.5 | 3885981 | [12 empty] | 378020.86 | 25.5 | 9639531
Labour-Civil-Villa Construction | PCC Under Floor & Stitching Slab | sqft | [45 empty] | 28911.63 | 12.75 | 368623 | [24 empty] | 104570.09 | 12.75 | 1333268 |  |  |  | 91893.25 | 12.75 | 1171638 | [27 empty] | 152316.86 | 12.75 | 1942041 | [12 empty] | 377691.83 | 12.75 | 4815570
Labour-Civil-Villa Construction | Parapet Wall / Mumty Work | sqft | [108 empty] | 15699.68 | 12.75 | 200171 | [12 empty] | 15699.68 | 12.75 | 200171
Labour-Civil-Villa Construction | RCC Columns & Casting of RCC Slab | sqft | [45 empty] | 25066.79 | 102 | 2556812 | [24 empty] | 98574.3 | 102 | 10054580 |  |  |  | 90950.8 | 102 | 9276982 | [27 empty] | 148640.83 | 102 | 15161365 | [12 empty] | 363232.72 | 102 | 37049739
Labour-Civil-Villa Construction | Work upto Plinth Beam of Block | sqft | [45 empty] | 28911.63 | 12.75 | 368623 | [24 empty] | 104570.09 | 12.75 | 1333268 |  |  |  | 91893.25 | 12.75 | 1171638 | [27 empty] | 152316.86 | 12.75 | 1942038 | [12 empty] | 377691.83 | 12.75 | 4815567
Labour-Civil-Water proofing Work | Water proofing Work | sqft | [111 empty] | 8052 | 22 | 177144 | [9 empty] | 8052 | 22 | 177144
Labour-Electrical Internal work | Fixing of MCB DB Fixing finish with cement mortar | sqft | [48 empty] | 58925 | 3.65 | 215076 | [72 empty] | 58925 | 3.65 | 215076
Labour-Electrical Internal work | Roof/ Slab Conduiting Work | sqft | [48 empty] | 443863.06 | 7.07 | 3140265 | [72 empty] | 443863.06 | 7.07 | 3140265
Labour-Electrical Internal work | Wall Conduiting / Box Fixing and DB Fixing Work | sqft | [48 empty] | 218870 | 14.03 | 3069903 | [72 empty] | 218870 | 14.03 | 3069903
Labour-Finishing-False Ceiling | False Ceiling Work-Gypsum Board | sqft | 892.88 | 55 | 49108 | [120 empty] | 892.88 | 55 | 49108
Labour-Finishing-Flooring Work | Flooring Work - Kota Stone | sqft | [96 empty] | 114.44 | 25 | 2861 | [24 empty] | 114.44 | 25 | 2861
Labour-Finishing-Flooring Work | Flooring Work Tile | sqft | [96 empty] | 1713.83 | 18 | 30849 | [24 empty] | 1713.83 | 18 | 30849
Labour-Finishing-Flooring Work | Flooring Work-Granite | sqft | [96 empty] | 20 | 100 | 2000 | [24 empty] | 20 | 100 | 2000
Labour-Finishing-Flush Door Fixing | Flush Door Fixing Work | sqft | [87 empty] | 243.72 | 64.01 | 15601 | [33 empty] | 243.72 | 64.01 | 15601
Labour-Finishing-POP Work | POP Groove Work | rft | [105 empty] | 214.18 | 10 | 2142 | [15 empty] | 214.18 | 10 | 2142
Labour-Finishing-POP Work | POP Work Punning | sqft | [105 empty] | 6990.69 | 17 | 118842 | [15 empty] | 6990.69 | 17 | 118842
Labour-Finishing-Paint Work | Painting Work External | sqft | [18 empty] | 1936.47 | 6 | 11619 | [102 empty] | 1936.47 | 6 | 11619
Labour-Finishing-Paint Work | Painting Work Internal | sqft | [18 empty] | 3799.34 | 8 | 30395 | [102 empty] | 3799.34 | 8 | 30395
Labour-General Works | Barricading Work | lumpsum | [66 empty] | 185 | 150 | 27750 | [54 empty] | 185 | 150 | 27750
Labour-General Works | Chipping / Grinding & Welding | lumpsum | [30 empty] | 8.75 | 387.09 | 3387 | [90 empty] | 8.75 | 387.09 | 3387
Labour-General Works | Cleaning Work | lumpsum | [30 empty] | 182.89 | 358.92 | 65644 | [90 empty] | 182.89 | 358.92 | 65644
Labour-General Works | Curing | lumpsum | [30 empty] | 152.26 | 320.85 | 48853 | [90 empty] | 152.26 | 320.85 | 48853
Labour-General Works | Dismantling | lumpsum | [30 empty] | 4.26 | 456.1 | 1943 | [90 empty] | 4.26 | 456.1 | 1943
Labour-General Works | Electrical-Plumbing-Mechanical Work | lumpsum | [30 empty] | 269.76 | 383.95 | 103574 | [90 empty] | 269.76 | 383.95 | 103574
Labour-General Works | Housekeeping Work | lumpsum | [30 empty] | 100.88 | 319.9 | 32273 | [90 empty] | 100.88 | 319.9 | 32273
Labour-General Works | Lab Work | lumpsum | [30 empty] | 458.02 | 382.34 | 175119 | [90 empty] | 458.02 | 382.34 | 175119
Labour-General Works | Labour Hutments Fabrication Work | lumpsum | [39 empty] | 80 | 1100 | 88000 | [33 empty] | 230 | 1013.04 | 233000 | [45 empty] | 310 | 1035.48 | 321000
Labour-General Works | Labour Supply to Other Site/Godown | lumpsum | [30 empty] | 380.12 | 318.25 | 120976 | [90 empty] | 380.12 | 318.25 | 120976
Labour-General Works | Level Marking & Layout | lumpsum | [30 empty] | 147.88 | 454.13 | 67157 | [90 empty] | 147.88 | 454.13 | 67157
Labour-General Works | Leveling and Dressing | lumpsum | [30 empty] | 264.5 | 357.54 | 94571 | [90 empty] | 264.5 | 357.54 | 94571
Labour-General Works | Oiling Taping Cover Block Fixing | lumpsum | [30 empty] | 98.63 | 605.9 | 59760 | [90 empty] | 98.63 | 605.9 | 59760
Labour-General Works | Repairing | lumpsum | [30 empty] | 41 | 431.71 | 17700 | [90 empty] | 41 | 431.71 | 17700
Labour-General Works | Site Infra Construction Work | lumpsum | [30 empty] | 27.5 | 419.96 | 11549 | [90 empty] | 27.5 | 419.96 | 11549
Labour-General Works | Starter fixing | lumpsum | [30 empty] | 25.25 | 425.5 | 10744 | [90 empty] | 25.25 | 425.5 | 10744
Labour-General Works | Sweeper & Office boy | lumpsum | [30 empty] | 692 | 369.22 | 255501 | [90 empty] | 692 | 369.22 | 255501
Labour-HVAC Work | HVAC Laying of Copper Cable | mtr | [114 empty] | 1016.2 | 506.36 | 514560 | [6 empty] | 1016.2 | 506.36 | 514560
Labour-HVAC Work | HVAC Laying of Drain Pipe in each Villas | mtr | [114 empty] | 445.2 | 100 | 44520 | [6 empty] | 445.2 | 100 | 44520
Labour-Internal Plumbing work | Making of GT and manhole complete in all in each Villa. | nos | [9 empty] | 41.5 | 3625.01 | 150438 | 18.5 | 3625.03 | 67063 | [36 empty] | 22 | 3625.05 | 79751 | [69 empty] | 82 | 3625.02 | 297252
Labour-Internal Plumbing work | Plumbing CPVC work Complete all villas. | nos | [9 empty] | 21 | 2818.76 | 59194 | 16.5 | 2818.73 | 46509 | [36 empty] | 7 | 2718.71 | 19031 | [69 empty] | 44.5 | 2803.01 | 124734
Labour-Internal Plumbing work | Plumbing UPVC work complete in Villas. | nos | [9 empty] | 21 | 2818.76 | 59194 | 16.5 | 2818.73 | 46509 | [36 empty] | 13 | 2718.77 | 35344 | [69 empty] | 50.5 | 2793.01 | 141047
Labour-Internal Plumbing work | Under Ground UPVC/DWC pipe work( Without toilet area)complete villa | nos | [9 empty] | 83 | 3625 | 300875 | 37 | 3625 | 134125 | [36 empty] | 44 | 3625 | 159500 | [69 empty] | 164 | 3625 | 594500
Labour-Site Infra Work | Infra - Backfilling | cuft | [30 empty] | 983.21 | 4.02 | 3950 | [60 empty] | 3310.6 | 3 | 9932 | [27 empty] | 4293.81 | 3.23 | 13882
Labour-Site Infra Work | Infra - Brick Masonry 4.5" | sqft | [30 empty] | 209.49 | 16.94 | 3548 | [60 empty] | 426.34 | 20 | 8527 | [27 empty] | 635.83 | 18.99 | 12075
Labour-Site Infra Work | Infra - Brick Masonry 9" | sqft | [30 empty] | 2534.15 | 19.72 | 49961 | [60 empty] | 2694.91 | 20 | 53898 | 754.3 | 22 | 16595 | [24 empty] | 5983.36 | 20.13 | 120454
Labour-Site Infra Work | Infra - Excavation | cuft | [30 empty] | 607.21 | 12.56 | 7628 | [21 empty] | 30150 | 1.84 | 55476 | [66 empty] | 30757.21 | 2.05 | 63104
Labour-Site Infra Work | Infra - External Plaster | sqft | [30 empty] | 868.28 | 9.28 | 8054 | [60 empty] | 2543.91 | 8 | 20351 | 477.78 | 10 | 4778 | [24 empty] | 3889.97 | 8.53 | 33183
Labour-Site Infra Work | Infra - Fabrication Work | sqft | [66 empty] | 21510.02 | 12 | 258120 | [6 empty] | 2713 | 10 | 27130 | [21 empty] | 5883.84 | 10 | 58838 | [21 empty] | 30106.86 | 11.43 | 344088
Labour-Site Infra Work | Infra - Internal Plaster | sqft | [30 empty] | 881.93 | 8.55 | 7541 | [60 empty] | 1325.45 | 8 | 10604 | 576.74 | 10 | 5767 | [24 empty] | 2784.12 | 8.59 | 23912
Labour-Site Infra Work | Infra - Neeru Plaster | sqft | [30 empty] | 263 | 1.57 | 413 | [60 empty] | 1722.95 | 1 | 1723 | 936.12 | 1 | 936 | [24 empty] | 2922.07 | 1.05 | 3072
Labour-Site Infra Work | Infra - PCC Work | cuft | [30 empty] | 5335.77 | 4.9 | 26147 | [60 empty] | 1737.5 | 25 | 43438 | [27 empty] | 7073.27 | 9.84 | 69585
Labour-Site Infra Work | Infra - Pipe Laying Work | rft | [93 empty] | 175 | 45.66 | 7991 | [27 empty] | 175 | 45.66 | 7991
Labour-Site Infra Work | Infra - Plumbing Work | nos | [93 empty] | 33 | 2918.18 | 96300 | [27 empty] | 33 | 2918.18 | 96300
Labour-Site Infra Work | Infra - RCC Work | cuft | [30 empty] | 876.64 | 7.11 | 6237 | [90 empty] | 876.64 | 7.11 | 6237
Labour-Site Infra Work | Infra - RCC Work (RMC) | cuft | [30 empty] | 2086.68 | 4.9 | 10234 | [90 empty] | 2086.68 | 4.9 | 10234
Labour-Site Infra Work | Infra - Shuttering | sqft | [27 empty] | 659.96 | 10.23 | 6751 | [93 empty] | 659.96 | 10.23 | 6751
Labour-Site Infra Work | Structural Steel Fabrication Works | kg | [99 empty] | 7618.41 | 95 | 723749 | [21 empty] | 7618.41 | 95 | 723749
Site Expenses | Consultancy Service Charges | lumpsum | [36 empty] | 2083334 | 1 | 2083334 | [78 empty] | 243000 | 1 | 243000 |  |  |  | 2326334 | 1 | 2326334
Site Expenses | Diesel Expenses | lumpsum | [33 empty] | 209738.25 | 1 | 209739 | [87 empty] | 209738.25 | 1 | 209739
Site Expenses | Electricity Charges | lumpsum | [30 empty] | 9 | 159001.67 | 1431015 | [90 empty] | 9 | 159001.67 | 1431015
Site Expenses | Installation Charges | lumpsum | [33 empty] | 6420 | 1 | 6420 | [87 empty] | 6420 | 1 | 6420
Site Expenses | Lab Material | lumpsum | [33 empty] | 277540.96 | 1 | 277541 | [87 empty] | 277540.96 | 1 | 277541
Site Expenses | Machine & Vehicle Service Charges | lumpsum | [33 empty] | 14300 | 1 | 14300 | [87 empty] | 14300 | 1 | 14300
Site Expenses | Material Shifting Loading Unloading | lumpsum | [30 empty] | 750.38 | 412.1 | 309228 | [90 empty] | 750.38 | 412.1 | 309228
Site Expenses | Mess Caretaker | lumpsum | [30 empty] | 303.5 | 346.54 | 105176 | [90 empty] | 303.5 | 346.54 | 105176
Site Expenses | Office Goods | lumpsum | [33 empty] | 947551.88 | 1 | 947552 | [87 empty] | 947551.88 | 1 | 947552
Site Expenses | Property Rent Charges | lumpsum | [33 empty] | 84686.43 | 1 | 84686 | [87 empty] | 84686.43 | 1 | 84686
Site Expenses | STATIONARY | Rs. | [33 empty] | 32951.2 | 1 | 32950 | [87 empty] | 32951.2 | 1 | 32950
Site Expenses | Safety Items | lumpsum | [33 empty] | 135583.62 | 1 | 135585 | [87 empty] | 135583.62 | 1 | 135585
Site Expenses | Security Guard | lumpsum |  |  |  | 4 | 466.75 | 1867 | [15 empty] | 593 | 490.15 | 290661 | [96 empty] | 2671 | 525.56 | 1403759 | 3268 | 519.06 | 1696287
Site Expenses | Site Office | lumpsum | [33 empty] | 133368.4 | 1 | 133369 | [87 empty] | 133368.4 | 1 | 133369
Site Expenses | Staff Welfare and Medicines | lumpsum | [33 empty] | 35347 | 1 | 35347 | [87 empty] | 35347 | 1 | 35347
Site Expenses | Tools and Plant Material | Rs. | [33 empty] | 4188 | 1 | 4188 | [87 empty] | 4188 | 1 | 4188
Site Expenses | Transportation and Courier Charges | lumpsum | [33 empty] | 13800 | 1 | 13800 | [87 empty] | 13800 | 1 | 13800
Site Expenses | Travel & Conveyance | lumpsum | [33 empty] | 10460 | 1 | 10460 | [87 empty] | 10460 | 1 | 10460
Site Expenses | Water Charges | lumpsum | [33 empty] | 84121.25 | 1 | 84121 | [87 empty] | 84121.25 | 1 | 84121
Total Billed Amount |  |  |  |  | 49108 |  |  | 1867 |  |  | 182634 |  |  | 569701 |  |  | 294206 |  |  | 276683 |  |  | 42014 |  |  | 290661 |  |  | 106444 |  |  | 6751 |  |  | 3342199 |  |  | 1990058 |  |  | 2083334 |  |  | 88000 |  |  | 143723 |  |  | 17803682 |  |  | 6425244 |  |  | 293626 |  |  | 14013967 |  |  | 160111 |  |  | 239113 |  |  | 205465 |  |  | 285870 |  |  | 306314 |  |  | 18162128 |  |  | 279430 |  |  | 17405755 |  |  | 699404 |  |  | 207425 |  |  | 15601 |  |  | 325000 |  |  | 467340 |  |  | 243986 |  |  | 4248871 |  |  | 61713 |  |  | 120984 |  |  | 28184644 |  |  | 177144 |  |  | 559080 |  |  | 243000 |  |  | 1403759 |  |  | 122006039