## Sheet1
Pivot Summary Table
Sr | Project Name | Sub Project | Parent WBS Name | Activity Code | Activity Name | Activity Unit | 3Total Qty | Item Group | Item Desc | Resource Unit | 3Est Qty | Est Rate | Est Amt | 3Theoritical Qty | 3Actual Qty | 3Difference Qty | Theoritical Amt | Actual Amt | Difference Amt
1 | WTC Commercial | WTC Commercial | ATT Work | WTC-WTC Commercial-ALL-ATTWBF | ATT Work - Below Footing | sqft | 9687.01 | Civil Raw Material-Chemical | Anti Termite Chemical | ltr | 104232.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | WTC Commercial | WTC Commercial | ATT Work | WTC-WTC Commercial-ALL-ATTWBF | ATT Work - Below Footing | sqft | 9687.01 | Labour-Civil-Earth Work | Anti Termite Treatment | sqft | 104232.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | WTC Commercial | WTC Commercial | BRICK BAT COBA | WTC-WTC Commercial-ALL-BBCWT | Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Bricks | Bricks Bat | cuft | 15964.403 | 25 | 399110.08 | 0 | 0 | 0 | 0 | 0 | 0
4 | WTC Commercial | WTC Commercial | BRICK BAT COBA | WTC-WTC Commercial-ALL-BBCWT | Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Cement | Cement PPC | bags | 1859.927 | 210.94 | 392333 | 0 | 0 | 0 | 0 | 0 | 0
5 | WTC Commercial | WTC Commercial | BRICK BAT COBA | WTC-WTC Commercial-ALL-BBCWT | Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Chemical | Waterproofing Chemical | kg | 478.98 | 50 | 23949 | 0 | 0 | 0 | 0 | 0 | 0
6 | WTC Commercial | WTC Commercial | BRICK BAT COBA | WTC-WTC Commercial-ALL-BBCWT | Brick Bat Coba Work on Terrace | sqft | 47898 | Civil Raw Material-Sand | M-Sand | cuft | 16685.747 | 40 | 667429.88 | 0 | 0 | 0 | 0 | 0 | 0
7 | WTC Commercial | WTC Commercial | BRICK BAT COBA | WTC-WTC Commercial-ALL-BBCWT | Brick Bat Coba Work on Terrace | sqft | 47898 | Labour-Civil-Water proofing Work | Water proofing Work Brick Bat Coba | sqft | 47898 | 25 | 1197450 | 0 | 0 | 0 | 0 | 0 | 0
8 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5\ Thick | sqft | 11411.15 | Civil Raw Material-Bricks | Earthen Bricks | nos | 11981.708 | 7 | 83871.96 | 389.747 | 1094 | -704.253 | 2728.229 | 4157.2 | -1428.971
9 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5\ Thick | sqft | 11411.15 | Civil Raw Material-Bricks | Flyash Bricks | nos | 66812.397 | 7 | 467686.78 | 2173.307 | 166 | 2007.307 | 15213.151 | 846.6 | 14366.551
10 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5\ Thick | sqft | 11411.15 | Civil Raw Material-Cement | Cement PPC | bags | 189.231 | 210.94 | 39916.39 | 6.275 | 7.5 | -1.225 | 1323.633 | 1617.405 | -293.772
11 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5\ Thick | sqft | 11411.15 | Civil Raw Material-Sand | M-Sand | cuft | 1226.242 | 50 | 61312.1 | 34.902 | 33 | 1.902 | 1745.092 | 1152 | 593.092
12 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5\ Thick | sqft | 11411.15 | Civil Raw Material-Sand | Silica Sand | cuft | 1105.056 | 50 | 55252.8 | 31.453 | 19 | 12.453 | 1572.629 | 950 | 622.629
13 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM4.5 | Brick Masonry 4.5\ Thick | sqft | 11411.15 | Labour-Civil-Masonry Work | Masonry Work Brick 4.5\ Thick | sqft | 11411.15 | 22 | 251045.3 | 389.747 | 370.7 | 19.047 | 8574.434 | 8860 | -285.566
14 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9\ Thick | sqft | 109013.56 | Civil Raw Material-Bricks | Earthen Bricks | nos | 572321.19 | 7 | 4006248.33 | 18511.765 | 24043.028 | -5531.263 | 129582.355 | 99135.106 | 30447.249
15 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9\ Thick | sqft | 109013.56 | Civil Raw Material-Bricks | Flyash Bricks | nos | 1149987.86 | 7 | 8049915.02 | 37196.43 | 6333 | 30863.43 | 260375.009 | 32298.3 | 228076.709
16 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9\ Thick | sqft | 109013.56 | Civil Raw Material-Cement | Cement PPC | bags | 2616.216 | 210.94 | 551864.6 | 86.265 | 124.14 | -37.875 | 18196.702 | 27706.731 | -9510.029
17 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9\ Thick | sqft | 109013.56 | Civil Raw Material-Sand | M-Sand | cuft | 11452.965 | 50 | 572648.25 | 324.141 | 644 | -319.859 | 16207.05 | 22198 | -5990.95
18 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9\ Thick | sqft | 109013.56 | Civil Raw Material-Sand | Silica Sand | cuft | 11452.965 | 50 | 572648.25 | 324.141 | 138.75 | 185.391 | 16207.05 | 6937.5 | 9269.55
19 | WTC Commercial | WTC Commercial | BRICK MASONRY | WTC-WTC Commercial-ALL-BM9 | Brick Masonry 9\ Thick | sqft | 109013.56 | Labour-Civil-Masonry Work | Masonry Work Brick 9\ Thick | sqft | 109013.56 | 25 | 2725339 | 3702.353 | 3701.44 | 0.913 | 92558.825 | 81380 | 11178.825
20 | WTC Commercial | WTC Commercial | BACKFILLING | WTC-WTC Commercial-ALL-EWBF | Earth Work - Back Filling | cuft | 115277.53 | Labour-Civil-Earth Work | Back Filling Work | cuft | 115277.53 | 2 | 230555.06 | 0 | 0 | 0 | 0 | 0 | 0
21 | WTC Commercial | WTC Commercial | EXCAVATION | WTC-WTC Commercial-ALL-EWEX | Earth Work - Excavation | cuft | 3740539.05 | Labour-Civil-Earth Work | Excavation Work | cuft | 3740539.05 | 3 | 11221617.15 | 238.484 | 238.48 | 0.004 | 715.452 | 11371 | -10655.548
22 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 147761.21 | Civil Raw Material-Cement | Cement PPC | bags | 2526.421 | 210.94 | 532923.25 | 0 | 0 | 0 | 0 | 0 | 0
23 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 147761.21 | Civil Raw Material-Chemical | Waterproofing Chemical | kg | 443.284 | 50 | 22164.2 | 0 | 0 | 0 | 0 | 0 | 0
24 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 147761.21 | Civil Raw Material-Misc | Fibre Mesh | mtr | 14776.121 | 4.8 | 70925.38 | 0 | 0 | 0 | 0 | 0 | 0
25 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 147761.21 | Civil Raw Material-Sand | M-Sand | cuft | 18440.599 | 50 | 922029.95 | 0 | 0 | 0 | 0 | 0 | 0
26 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 147761.21 | Civil Raw Material-Sand | Silica Sand | cuft | 18387.405 | 50 | 919370.25 | 0 | 0 | 0 | 0 | 0 | 0
27 | WTC Commercial | WTC Commercial | EXTERNAL PLASTER | WTC-WTC Commercial-ALL-EXTPL | Plaster - External | sqft | 147761.21 | Labour-Civil-Plaster Work | Plaster Work External | sqft | 147761.21 | 20 | 2955224.2 | 0 | 0 | 0 | 0 | 0 | 0
28 | WTC Commercial | WTC Commercial | INTERNAL PLASTER | WTC-WTC Commercial-ALL-INTPL | Plaster - Internal | sqft | 351546.97 | Civil Raw Material-Cement | Cement PPC | bags | 3548.515 | 210.94 | 748523.75 | 0 | 3 | -3 | 0 | 625.77 | -625.77
29 | WTC Commercial | WTC Commercial | INTERNAL PLASTER | WTC-WTC Commercial-ALL-INTPL | Plaster - Internal | sqft | 351546.97 | Civil Raw Material-Misc | Fibre Mesh | mtr | 35154.697 | 4.8 | 168742.55 | 0 | 0 | 0 | 0 | 0 | 0
30 | WTC Commercial | WTC Commercial | INTERNAL PLASTER | WTC-WTC Commercial-ALL-INTPL | Plaster - Internal | sqft | 351546.97 | Civil Raw Material-Sand | M-Sand | cuft | 15482.129 | 50 | 774106.45 | 0 | 0 | 0 | 0 | 0 | 0
31 | WTC Commercial | WTC Commercial | INTERNAL PLASTER | WTC-WTC Commercial-ALL-INTPL | Plaster - Internal | sqft | 351546.97 | Civil Raw Material-Sand | Silica Sand | cuft | 15482.129 | 50 | 774106.45 | 0 | 0 | 0 | 0 | 0 | 0
32 | WTC Commercial | WTC Commercial | INTERNAL PLASTER | WTC-WTC Commercial-ALL-INTPL | Plaster - Internal | sqft | 351546.97 | Labour-Civil-Plaster Work | Plaster Work Internal | sqft | 351546.97 | 10 | 3377312.2 | 0 | 0 | 0 | 0 | 0 | 0
33 | WTC Commercial | WTC Commercial | PLAIN CEMENT CONCRETE | WTC-WTC Commercial-ALL-PCC7.5 | Below Footing PCC M7.5 | cuft | 29000 | Civil Raw Material-RMC | RMC M-7.5 | cum | 821.297 | 3000 | 2463891 | 816 | 948.5 | -132.5 | 2448000.945 | 2479985.68 | -31984.735
34 | WTC Commercial | WTC Commercial | PLAIN CEMENT CONCRETE | WTC-WTC Commercial-ALL-PCC7.5 | Below Footing PCC M7.5 | cuft | 29000 | Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | 29000 | 5 | 145000 | 28812.96 | 28320.75 | 492.21 | 144064.8 | 87704 | 56360.8
35 | WTC Commercial | WTC Commercial | PLAIN CEMENT CONCRETE | WTC-WTC Commercial-ALL-PCCBFLM7.5 | Below Floor PCC M7.5 | cuft | 25613.87 | Civil Raw Material-RMC | RMC M-7.5 | cum | 1047.084 | 3000 | 3141252 | 482 | 351.5 | 130.5 | 1446000.558 | 928369.36 | 517631.198
36 | WTC Commercial | WTC Commercial | PLAIN CEMENT CONCRETE | WTC-WTC Commercial-ALL-PCCBFLM7.5 | Below Floor PCC M7.5 | cuft | 25613.87 | Labour-Civil-Concreting Work | Concreting Work With RMC M-7.5 | cuft | 36972.53 | 5 | 184862.65 | 17019.42 | 17513.87 | -494.45 | 85097.1 | 53474 | 31623.1
37 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCCLM35 | RCC - Column,Walls- M35 | cuft | 136527.17 | Civil Raw Material-RMC | RMC M-35 | cum | 4140.583 | 4000 | 16562332 | 2688.003 | 2032.5 | 655.503 | 10752012.473 | 6011108.615 | 4740903.858
38 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCCLM35 | RCC - Column,Walls- M35 | cuft | 136527.17 | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 146204 | 15 | 2193060 | 94913.39 | 83172.72 | 11740.67 | 1423700.85 | 161602 | 1262098.85
39 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCCLM45 | RCC - Column - M45 | cuft | 353.1 | Civil Raw Material-RMC | RMC M-45 | cum | 10 | 4200 | 42000 | 9.5 | 9.5 | 1.065e-08 | 39900 | 21850 | 18050
40 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCCLM45 | RCC - Column - M45 | cuft | 353.1 | Labour-Civil-Concreting Work | Concreting Work With RMC M-45 | cuft | 353.1 | 15 | 5296.5 | 335.445 | 335.45 | -0.005 | 5031.675 | 352 | 4679.675
41 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCCWM50 | RCC - Column & Wall - M-50 | cuft | 141.256 | Civil Raw Material-RMC | RMC M-50 | cum | 4 | 4000 | 16000 | 3.5 | 3.5 | -8.435e-09 | 14000 | 18033.89 | -4033.89
42 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCCWM50 | RCC - Column & Wall - M-50 | cuft | 141.256 | Labour-Civil-Concreting Work | Concreting Work With RMC M-50 | cuft | 141.256 | 15 | 2118.84 | 123.585 | 123.59 | -0.005 | 1853.775 | 292 | 1561.775
43 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCFM30 | RCC Footing - M30 | cuft | 305000 | Civil Raw Material-RMC | RMC M-30 | cum | 8637.78 | 3800 | 32823564 | 8373.551 | 8344 | 29.551 | 31819492.027 | 25228662.7 | 6590829.327
44 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCFM30 | RCC Footing - M30 | cuft | 305000 | Labour-Civil-Concreting Work | Concreting Work With RMC M-30 | cuft | 305000 | 5 | 1525000 | 295670.069 | 294646.08 | 1023.989 | 1478350.345 | 611956 | 866394.345
45 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCSBM35 | RCC - Slab & beam | cuft | 801221.92 | Civil Raw Material-RMC | RMC M-35 | cum | 22691.077 | 4000 | 90764308 | 8538.5 | 7680 | 858.5 | 34153999.918 | 20914798.57 | 13239201.348
46 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCSBM35 | RCC - Slab & beam | cuft | 801221.92 | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 801221.92 | 5 | 4006109.6 | 301494.435 | 259493.19 | 42001.245 | 1507472.175 | 582336 | 925136.175
47 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCSSM25 | RCC - Stiching Slab - M25 | cuft | 10593 | Civil Raw Material-RMC | RMC M-25 | cum | 332 | 3600 | 1195200 | 331.501 | 331.5 | 0.001 | 1193402.036 | 982662.9 | 210739.136
48 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial-ALL-RCCSSM25 | RCC - Stiching Slab - M25 | cuft | 10593 | Labour-Civil-Concreting Work | Concreting Work With RMC M-25 | cuft | 11722.92 | 5 | 58614.6 | 11705.285 | 11705.29 | -0.005 | 58526.425 | 18982 | 39544.425
49 | WTC Commercial | WTC Commercial | Rebaring work | WTC-WTC Commercial-ALL-RW | Rebaring work | nos | 12900 | Labour-Civil-Rebaring Work | Rebaring Work 08mm Dia | nos | 3005.7 | 600 | 1803420 | 1164.534 | 1510 | -345.466 | 698720.4 | 37750 | 660970.4
50 | WTC Commercial | WTC Commercial | Rebaring work | WTC-WTC Commercial-ALL-RW | Rebaring work | nos | 12900 | Labour-Civil-Rebaring Work | Rebaring Work 10mm Dia | nos | 8010.9 | 600 | 4806540 | 3103.758 | 4173 | -1069.242 | 1862254.8 | 146055 | 1716199.8
51 | WTC Commercial | WTC Commercial | Rebaring work | WTC-WTC Commercial-ALL-RW | Rebaring work | nos | 12900 | Labour-Civil-Rebaring Work | Rebaring Work 12mm Dia | nos | 1212.6 | 600 | 727560 | 469.812 | 878 | -408.188 | 281887.2 | 35120 | 246767.2
52 | WTC Commercial | WTC Commercial | Rebaring work | WTC-WTC Commercial-ALL-RW | Rebaring work | nos | 12900 | Labour-Civil-Rebaring Work | Rebaring Work 16mm Dia | nos | 361.2 | 600 | 216720 | 139.944 | 361 | -221.056 | 83966.4 | 21660 | 62306.4
53 | WTC Commercial | WTC Commercial | Rebaring work | WTC-WTC Commercial-ALL-RW | Rebaring work | nos | 12900 | Labour-Civil-Rebaring Work | Rebaring Work 20mm Dia | nos | 206.4 | 600 | 123840 | 79.968 | 189 | -109.032 | 47980.8 | 20790 | 27190.8
54 | WTC Commercial | WTC Commercial | Rebaring work | WTC-WTC Commercial-ALL-RW | Rebaring work | nos | 12900 | Labour-Civil-Rebaring Work | Rebaring Work 25mm Dia | nos | 154.8 | 600 | 92880 | 59.976 | 83 | -23.024 | 35985.6 | 12450 | 23535.6
55 | WTC Commercial | WTC Commercial | SCAFFOLDING | WTC-WTC Commercial-ALL-SCWK | Scaffolding Work | sqft | 143253.1 | Labour-Civil-Scaffolding | De-Scaffolding | sqft | 143253.1 | 2.5 | 358132.75 | 10329.6 | 0 | 10329.6 | 25824 | 0 | 25824
56 | WTC Commercial | WTC Commercial | SCAFFOLDING | WTC-WTC Commercial-ALL-SCWK | Scaffolding Work | sqft | 143253.1 | Labour-Civil-Scaffolding | Scaffolding | sqft | 143253.1 | 2.5 | 358132.75 | 10329.6 | 3808.56 | 6521.04 | 25824 | 28928 | -3104
57 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Raw Material-Cover Block | Cover Block 20 MM | nos | 84131.479 | 1 | 84131.48 | 35038.247 | 49800 | -14761.753 | 35038.247 | 16596 | 18442.247
58 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Raw Material-Cover Block | Cover Block 25 MM | nos | 76741.219 | 1 | 76741.22 | 31960.425 | 55500 | -23539.575 | 31960.425 | 29290 | 2670.425
59 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Raw Material-Cover Block | Cover Block 50 MM | nos | 76854.574 | 1 | 76854.57 | 32007.634 | 15300 | 16707.634 | 32007.634 | 24690 | 7317.634
60 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Raw Material-Cover Block | Cover Block L Shape 40 MM | nos | 76854.574 | 1 | 76854.57 | 32007.634 | 9464 | 22543.634 | 32007.634 | 9834.75 | 22172.884
61 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Raw Material-Misc | Shuttering Oil | ltr | 3967.419 | 65 | 257882.24 | 1652.311 | 1575 | 77.311 | 107400.245 | 99304.5 | 8095.745
62 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Shuttering-Batten (Mirandi) | Batten 3x2.5x10 (Mirandi) | nos | 3400.645 | 650 | 2210419.25 | 1416.267 | 1052 | 364.267 | 920573.531 | 552573.32 | 368000.21
63 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Shuttering-Batten (Pine) | Batten 2.25x1.5x8 (Pine) | nos | 10201.935 | 150 | 1530290.25 | 4248.801 | 8270 | -4021.199 | 637320.137 | 997689.3 | -360369.164
64 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Shuttering-Batten (Pine) | Batten 2x2.5x8 (Pine) | nos | 30107.043 | 200 | 6021408.6 | 12538.684 | 15361 | -2822.316 | 2507736.715 | 2857418.69 | -349681.975
65 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Shuttering-Misc | Shuttering Tape Brown | nos | 1360.258 | 75 | 102019.35 | 566.507 | 0 | 566.507 | 42488.009 | 0 | 42488.009
66 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Shuttering-Misc | Shuttering Tape White | nos | 113.355 | 75 | 8501.63 | 47.209 | 0 | 47.209 | 3540.667 | 0 | 3540.667
67 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Shuttering-Ply | Old Ply Scrap All Size | nos | 3763.38 | 70 | 263436.6 | 1567.335 | 368 | 1199.335 | 109713.481 | 20680 | 89033.481
68 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Civil Shuttering-Ply | Shuttering Ply 8x4x12 MM | nos | 3763.38 | 2000 | 7526760 | 1567.335 | 1735 | -167.665 | 3134670.894 | 3379440.85 | -244769.956
69 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Consumable Material-Nails | Nails 2 | kg | 6801.29 | 65 | 442083.85 | 2832.534 | 1462 | 1370.534 | 184114.706 | 79815.69 | 104299.016
70 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Consumable Material-Nails | Nails 3 | kg | 7934.838 | 65 | 515764.47 | 3304.623 | 2888 | 416.623 | 214800.49 | 156177.15 | 58623.34
71 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Consumable Material-Nails | Nails 4 | kg | 7934.838 | 65 | 515764.47 | 3304.623 | 2169 | 1135.623 | 214800.49 | 113055.5 | 101744.99
72 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Labour-Civil-Shuttering Work | Extra Height Shuttering Work | sqft | 566774.145 | 0 | 0 | 236044.495 | 214248.66 | 21795.835 | 0 | 160687 | -160687
73 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Labour-Civil-Shuttering Work | Shuttering Making Work | sqft | 120427.669 | 8 | 963421.35 | 50154.525 | 54944 | -4789.475 | 401236.204 | 439552 | -38315.796
74 | WTC Commercial | WTC Commercial | SHUTTERING | WTC-WTC Commercial-ALL-SHUTWK | Shuttering Work | sqft | 1133548.29 | Labour-Civil-Shuttering Work | Shuttering Work | sqft | 1133548.29 | 20 | 22670965.8 | 472088.99 | 427571.59 | 44517.4 | 9441779.8 | 6413574 | 3028205.8
75 | WTC Commercial | WTC Commercial | PONDING WORK | WTC-WTC Commercial-ALL-SPW | Slab Ponding Work | sqft | 800000 | Civil Raw Material-Cement | Cement PPC | bags | 494.4 | 210.94 | 104288.74 | 0.013 | 18 | -17.987 | 2.8 | 3783.57 | -3780.77
76 | WTC Commercial | WTC Commercial | PONDING WORK | WTC-WTC Commercial-ALL-SPW | Slab Ponding Work | sqft | 800000 | Civil Raw Material-Sand | Silica Sand | cuft | 7296 | 50 | 364800 | 0.168 | 0 | 0.168 | 8.407 | 0 | 8.407
77 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Civil Raw Material-Misc | Binding Wire | kg | 36524.1 | 70 | 2556687 | 22630.2 | 13508 | 9122.2 | 1584114 | 790286.34 | 793827.66
78 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Civil Raw Material-Steel | TMT Steel 08 MM | MT | 376.198 | 55080 | 20720985.84 | 226.302 | 103.369 | 122.933 | 12464714.16 | 5623523.5 | 6841190.66
79 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Civil Raw Material-Steel | TMT Steel 10 MM | MT | 752.396 | 55080 | 41441971.68 | 452.604 | 445.348 | 7.256 | 24929428.32 | 23717936.482 | 1211491.838
80 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Civil Raw Material-Steel | TMT Steel 12 MM | MT | 376.198 | 55080 | 20720985.84 | 226.302 | 134.485 | 91.817 | 12464714.16 | 7073045.25 | 5391668.91
81 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Civil Raw Material-Steel | TMT Steel 16 MM | MT | 376.198 | 55080 | 20720985.84 | 226.302 | 90.459 | 135.843 | 12464714.16 | 4944559.5 | 7520154.66
82 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Civil Raw Material-Steel | TMT Steel 20 MM | MT | 376.198 | 55080 | 20720985.84 | 226.302 | 128.776 | 97.526 | 12464714.16 | 7112213.2 | 5352500.96
83 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Civil Raw Material-Steel | TMT Steel 25 MM | MT | 752.396 | 55080 | 41441971.68 | 452.604 | 903.922 | -451.318 | 24929428.32 | 48089376.448 | -23159948.128
84 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Civil Raw Material-Steel | TMT Steel 32 MM | MT | 376.198 | 55080 | 20720985.84 | 226.302 | 306.844 | -80.542 | 12464714.16 | 16430539.557 | -3965825.397
85 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Civil Raw Material-Steel | TMT Steel 40 MM | MT | 376.198 | 55080 | 20720985.84 | 226.302 | 82.274 | 144.028 | 12464714.16 | 4582099 | 7882615.16
86 | WTC Commercial | WTC Commercial | STEEL BINDING | WTC-WTC Commercial-ALL-STBWK | Steel Binding Work | MT | 3652.41 | Labour-Civil-Reinforcement Work | Reinforcement Work Steel Binding | kg | 3652410 | 7 | 25566870 | 2263020 | 2175104 | 87916 | 15841140 | 10875520 | 4965620
87 | WTC Commercial | WTC Commercial | THREADING WORK | WTC-WTC Commercial-ALL-TW | Threading work | nos | 73048.17 | Labour-Civil-Threading Work | Threading Work 16 MM | nos | 15053.036 | 17 | 255901.61 | 8959.305 | 44 | 8915.305 | 152308.192 | 660 | 151648.192
88 | WTC Commercial | WTC Commercial | THREADING WORK | WTC-WTC Commercial-ALL-TW | Threading work | nos | 73048.17 | Labour-Civil-Threading Work | Threading Work 20 MM | nos | 10378.684 | 20 | 207573.68 | 6177.212 | 8696 | -2518.788 | 123544.243 | 155226 | -31681.757
89 | WTC Commercial | WTC Commercial | THREADING WORK | WTC-WTC Commercial-ALL-TW | Threading work | nos | 73048.17 | Labour-Civil-Threading Work | Threading Work 25 MM | nos | 17577.581 | 24 | 421861.94 | 10461.871 | 15898 | -5436.129 | 251084.892 | 337833 | -86748.108
90 | WTC Commercial | WTC Commercial | THREADING WORK | WTC-WTC Commercial-ALL-TW | Threading work | nos | 73048.17 | Labour-Civil-Threading Work | Threading Work 32 MM | nos | 22224.906 | 27 | 600072.46 | 13227.877 | 14781 | -1553.123 | 357152.686 | 364352 | -7199.314
91 | WTC Commercial | WTC Commercial | THREADING WORK | WTC-WTC Commercial-ALL-TW | Threading work | nos | 73048.17 | Labour-Civil-Threading Work | Threading Work 40 MM | nos | 7816.154 | 42 | 328278.47 | 4652.039 | 4058 | 594.039 | 195385.638 | 162320 | 33065.638
92 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GCHPG | Chipping, Grinding & Welding | lumpsum | 1440 | Labour-General Works | Chipping / Grinding & Welding | lumpsum | 1440 | 350 | 504000 | 241.25 | 240.26 | 0.99 | 84437.5 | 110053 | -25615.5
93 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GCLNG | Cleaning Work | lumpsum | 3600 | Labour-General Works | Cleaning Work | lumpsum | 3600 | 350 | 1260000 | 670.5 | 605.38 | 65.12 | 234675 | 208286 | 26389
94 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GCURG | Curing | lumpsum | 2160 | Labour-General Works | Curing | lumpsum | 2160 | 350 | 756000 | 683.005 | 605.64 | 77.365 | 239051.75 | 223315 | 15736.75
95 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GDISMLG | Dismantling | lumpsum | 857 | Labour-General Works | Dismantling | lumpsum | 858 | 350 | 300300 | 49.875 | 41.38 | 8.495 | 17456.25 | 20728 | -3271.75
96 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GELECT | Electrical, Plumbing,Mechanical Work | lumpsum | 857 | Labour-General Works | Electrical-Plumbing-Mechanical Work | lumpsum | 858 | 350 | 300300 | 58.125 | 39.13 | 18.995 | 20343.75 | 15129 | 5214.75
97 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GHSKPG | Housekeeping Work | lumpsum | 3600 | Labour-General Works | Housekeeping Work | lumpsum | 3600 | 350 | 1260000 | 200.5 | 118.93 | 81.57 | 70175 | 39826 | 30349
98 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GLAB | Lab Work | lumpsum | 480 | Labour-General Works | Lab Work | lumpsum | 480 | 350 | 168000 | 358.875 | 321.39 | 37.485 | 125606.25 | 118593 | 7013.25
99 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GLOP | Lift Operator | lumpsum | 1440 | Labour-General Works | Lift Operator | lumpsum | 1440 | 350 | 504000 | 0 | 0 | 0 | 0 | 0 | 0
100 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GLSOS | Labour Supply to Other Site/Godown | lumpsum | 3600 | Labour-General Works | Labour Supply to Other Site/Godown | lumpsum | 3600 | 350 | 1260000 | 0 | 0 | 0 | 0 | 0 | 0
101 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GLST | Labour Supply to Client | lumpsum | 3600 | Labour-General Works | Labour Supply to Client | lumpsum | 3600 | 350 | 1260000 | 0 | 0 | 0 | 0 | 0 | 0
102 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GLVLD | Leveling Dressing | lumpsum | 1430 | Labour-General Works | Leveling and Dressing | lumpsum | 1430 | 350 | 500500 | 1415.25 | 1333.38 | 81.87 | 495337.5 | 482314 | 13023.5
103 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GLVLM | Level Marking & Layout | lumpsum | 1851 | Labour-General Works | Level Marking & Layout | lumpsum | 1440 | 450 | 648000 | 859.275 | 766.01 | 93.265 | 386673.75 | 354525 | 32148.75
104 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GMATSHF | Material Shifting Loading Unloading | lumpsum | 7200 | Site Expenses | Material Shifting Loading Unloading | lumpsum | 7200 | 350 | 2520000 | 3913.38 | 3725.02 | 188.36 | 1369683 | 1301433 | 68250
105 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GOTCBF | Oiling Taping Cover Block Fixing | lumpsum | 3465 | Labour-General Works | Oiling Taping Cover Block Fixing | lumpsum | 1440 | 350 | 504000 | 1416.75 | 1231.26 | 185.49 | 495862.5 | 450516 | 45346.5
106 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GREP | Repairing | lumpsum | 2469 | Labour-General Works | Repairing | lumpsum | 1440 | 450 | 648000 | 492.25 | 398.25 | 94 | 221512.5 | 179406 | 42106.5
107 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GSF | Starter Fixing | lumpsum | 2469 | Labour-General Works | Starter fixing | lumpsum | 1440 | 450 | 648000 | 445.63 | 353.63 | 92 | 200533.5 | 157863 | 42670.5
108 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GSOB | Sweeper & Office boy | lumpsum | 1029 | Labour-General Works | Sweeper & Office boy | lumpsum | 720 | 350 | 252000 | 225.75 | 197.75 | 28 | 79012.5 | 66639 | 12373.5
109 | WTC Commercial | WTC Commercial | GENERAL SITE WORK | WTC-WTC Commercial--GSPON | Slab Ponding Work | lumpsum | 720 | Labour-General Works | Slab Ponding Work | lumpsum | 720 | 350 | 252000 | 5 | 27.13 | -22.13 | 1750 | 12183 | -10433
110 | WTC Commercial | WTC Commercial | HIRE & RENT | WTC-WTC Commercial--HRMHCR | Machine Hire charges | lumpsum | 15 | Hire & Rent | Dismantling of rcc work by Hammer machine |  | 0 | 0 | 0 | 0 | 47.83 | -47.83 | 0 | 9566 | -9566
111 | WTC Commercial | WTC Commercial | HIRE & RENT | WTC-WTC Commercial--HRMHCR | Machine Hire charges | lumpsum | 15 | Hire & Rent | JCB HIRE CHARGE | hours | 536.765 | 850 | 456250.25 | 0 | 507.91 | -507.91 | 0 | 431724 | -431724
112 | WTC Commercial | WTC Commercial | HIRE & RENT | WTC-WTC Commercial--HRMHCR | Machine Hire charges | lumpsum | 15 | Hire & Rent | Machinery Hire Charges | lumpsum | 7.5 | 25000 | 187500 | 0 | 6 | -6 | 0 | 150000 | -150000
113 | WTC Commercial | WTC Commercial | HIRE & RENT | WTC-WTC Commercial--HRSHUTR | Shuttering Rent | lumpsum | 12 | Hire & Rent | Shuttering Rent | lumpsum | 12 | 1010515 | 12126180 | 0 | 0 | 0 | 0 | 0 | 0
114 | WTC Commercial | WTC Commercial | HIRE & RENT | WTC-WTC Commercial--HRTMPR | Tools and Plant Rent | lumpsum | 12 | Hire & Rent | Tools Rent | lumpsum | 12 | 360000 | 4320000 | 0 | 0 | 0 | 0 | 0 | 0
115 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBCF | Infra - Backfilling | cuft | 8200 | Labour-Site Infra Work | Infra - Backfilling | cuft | 8200 | 3 | 24600 | 8009.45 | 8009.45 | 0 | 24028.35 | 24029 | -0.65
116 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18\ | cuft | 1000 | Civil Raw Material-Bricks | Earthen Bricks | nos | 28350 | 6 | 170100 | 24648.705 | 14606.81 | 10041.895 | 147892.23 | 59105.878 | 88786.352
117 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18\ | cuft | 1000 | Civil Raw Material-Cement | Cement PPC | bags | 70.04 | 220 | 15408.8 | 62.078 | 49.71 | 12.368 | 13657.208 | 10709.936 | 2947.272
118 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18\ | cuft | 1000 | Civil Raw Material-Sand | M-Sand | cuft | 609.6 | 50 | 30480 | 463.761 | 83 | 380.761 | 23188.041 | 2905 | 20283.041
119 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18\ | cuft | 1000 | Civil Raw Material-Sand | Silica Sand | cuft | 969.6 | 50 | 48480 | 737.635 | 694.15 | 43.485 | 36881.766 | 34707.5 | 2174.266
120 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18\ | cuft | 1000 | Civil Raw Material-Sand | Stone Dust | cuft | 249.6 | 50 | 12480 | 189.886 | 0 | 189.886 | 9494.316 | 0 | 9494.316
121 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM18 | Infra - Brick Masonry 18\ | cuft | 1000 | Labour-Site Infra Work | infra - Brick Masonry 18\ | cuft | 1000 | 30 | 30000 | 912.915 | 912.92 | -0.005 | 27387.45 | 23923 | 3464.45
122 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Bricks | Earthen Bricks | nos | 29275.05 | 6 | 175650.3 | 6038.188 | 8371.445 | -2333.257 | 36229.129 | 32291.491 | 3937.638
123 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Cement | Cement PPC | bags | 82.915 | 210.94 | 17490.09 | 17.434 | 23.112 | -5.678 | 3677.504 | 5006.705 | -1329.201
124 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Sand | M-Sand | cuft | 525.3 | 50 | 26265 | 94.804 | 0 | 94.804 | 4740.176 | 0 | 4740.176
125 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Sand | Silica Sand | cuft | 145.26 | 50 | 7263 | 26.216 | 175.065 | -148.849 | 1310.79 | 8753.25 | -7442.46
126 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Civil Raw Material-Sand | Stone Dust | cuft | 338.94 | 40 | 13557.6 | 61.17 | 80 | -18.83 | 2446.808 | 1800 | 646.808
127 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM4.5 | Infra - Brick Masonry 4.5 | sqft | 5000 | Labour-Site Infra Work | Infra - Brick Masonry 4.5\ | sqft | 5000 | 20 | 100000 | 1082.85 | 1082.82 | 0.03 | 21657 | 21890 | -233
128 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Bricks | Earthen Bricks | nos | 52745.175 | 6 | 316471.05 | 44008.906 | 41373.717 | 2635.189 | 264053.438 | 165644.125 | 98409.313
129 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Cement | Cement PPC | bags | 119.995 | 220 | 52797.8 | 102.064 | 117.485 | -15.421 | 22454.105 | 25996.381 | -3542.276
130 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Sand | M-Sand | cuft | 1050.6 | 50 | 52530 | 767.014 | 142 | 625.014 | 38350.7 | 4930 | 33420.7
131 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Sand | Silica Sand | cuft | 840.48 | 50 | 42024 | 613.611 | 1317.236 | -703.625 | 30680.56 | 65861.8 | -35181.24
132 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Civil Raw Material-Sand | Stone Dust | cuft | 210.12 | 50 | 10506 | 153.403 | 160 | -6.597 | 7670.14 | 3600 | 4070.14
133 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IBM9 | Infra - Brick Masonry 9 | sqft | 5000 | Labour-Site Infra Work | Infra - Brick Masonry 9\ | sqft | 5000 | 22 | 110000 | 4380.434 | 4380.44 | -0.006 | 96369.548 | 90220 | 6149.548
134 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IDFFW | Infra - Door/Window Fixing Work | nos | 150 | Labour-Site Infra Work | Infra - Door/Window Fixing | nos | 150 | 500 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
135 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IELE | Infra - Electrical Work | nos | 10 | Labour-Site Infra Work | Infra - Electrical Work | nos | 10 | 6000 | 60000 | 2.5 | 3.75 | -1.25 | 15000 | 1788 | 13212
136 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IEPLS | Infra - External Plaster | sqft | 10000 | Civil Raw Material-Cement | Cement PPC | bags | 170.98 | 210.94 | 36066.52 | 31.686 | 34.028 | -2.342 | 6683.862 | 7454.069 | -770.207
137 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IEPLS | Infra - External Plaster | sqft | 10000 | Civil Raw Material-Sand | M-Sand | cuft | 1248 | 50 | 62400 | 198.515 | 62 | 136.515 | 9925.76 | 2170 | 7755.76
138 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IEPLS | Infra - External Plaster | sqft | 10000 | Civil Raw Material-Sand | Silica Sand | cuft | 1244.4 | 50 | 62220 | 197.943 | 338.971 | -141.028 | 9897.128 | 16948.55 | -7051.422
139 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IEPLS | Infra - External Plaster | sqft | 10000 | Labour-Site Infra Work | Infra - External Plaster | sqft | 10000 | 10 | 100000 | 1908.8 | 1908.8 | 0 | 19088 | 17179 | 1909
140 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IEXAV | Infra - Excavation | cuft | 1000 | Labour-Site Infra Work | Infra - Excavation | cuft | 5000 | 4 | 20000 | 0 | 0 | 0 | 0 | 0 | 0
141 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IFAB | Infra - Fabrication Work | sqft | 1 | Labour-Site Infra Work | Infra - Fabrication Work | sqft | 20000 | 15 | 300000 | 12221.39 | 17814.9 | -5593.51 | 183320.85 | 181749 | 1571.85
142 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IFLW | Infra - Flooring Work | sqft | 5000 | Labour-Site Infra Work | Infra - Flooring Work | sqft | 5000 | 18 | 90000 | 0 | 0 | 0 | 0 | 0 | 0
143 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IIPLS | Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Cement | Cement PPC | bags | 100.94 | 210.94 | 21292.28 | 41.445 | 45.99 | -4.545 | 8742.424 | 10005.181 | -1262.758
144 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IIPLS | Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Misc | Fibre Mesh | mtr | 1000 | 4.8 | 4800 | 422.909 | 0 | 422.909 | 2029.963 | 0 | 2029.963
145 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IIPLS | Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Sand | M-Sand | cuft | 882 | 50 | 44100 | 310.838 | 30 | 280.838 | 15541.902 | 1020 | 14521.902
146 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IIPLS | Infra - Internal Plaster | sqft | 10000 | Civil Raw Material-Sand | Silica Sand | cuft | 882 | 50 | 44100 | 310.838 | 552.292 | -241.454 | 15541.902 | 27614.6 | -12072.698
147 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IIPLS | Infra - Internal Plaster | sqft | 10000 | Labour-Site Infra Work | Infra - Internal Plaster | sqft | 10000 | 10 | 100000 | 4229.089 | 4229.05 | 0.039 | 42290.89 | 38947 | 3343.89
148 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--ILHFW | Infra - Labour Hutment Fabrication | nos | 150 | Labour-Site Infra Work | Infra-Hutment Fabrication Work | nos | 150 | 1500 | 225000 | 120 | 120 | 0 | 180000 | 147404 | 32596
149 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--ILHFW | Infra - Labour Hutment Fabrication | nos | 150 | Site Infra Items-GI Sheet | GI Sheet 10x4 | nos | 600 | 1200 | 720000 | 480 | 0 | 480 | 576000 | 0 | 576000
150 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--ILHFW | Infra - Labour Hutment Fabrication | nos | 150 | Site Infra Items-GI Sheet | GI Sheet 8x4 | nos | 750 | 1100 | 825000 | 600 | 0 | 600 | 660000 | 0 | 660000
151 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Cement | Cement PPC | bags | 466.59 | 210.94 | 98422.49 | 435.714 | 436.702 | -0.988 | 91909.505 | 93909.592 | -2000.086
152 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 10 MM | cuft | 2475 | 22 | 54450 | 2164.142 | 1710 | 454.142 | 47611.129 | 39330 | 8281.129
153 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 20 MM | cuft | 2475 | 27 | 66825 | 2164.142 | 144 | 2020.142 | 58431.841 | 3932 | 54499.841
154 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Sand | Silica Sand | cuft | 225 | 50 | 11250 | 216.414 | 0 | 216.414 | 10820.711 | 0 | 10820.711
155 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Civil Raw Material-Sand | Stone Dust | cuft | 2430 | 40 | 97200 | 1947.728 | 1290 | 657.728 | 77909.121 | 29025 | 48884.121
156 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPCC | Infra - PCC Work | cuft | 5000 | Labour-Site Infra Work | Infra - PCC Work | cuft | 5000 | 25 | 125000 | 4809.205 | 4809.22 | -0.015 | 120230.125 | 123569 | -3338.875
157 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPLM | Infra - Plumbing Work | nos | 40 | Labour-Site Infra Work | Infra - Plumbing Work | nos | 40 | 12000 | 480000 | 28 | 32.86 | -4.86 | 336000 | 55060 | 280940
158 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IPW | Infra - Paint Work | sqft | 5000 | Labour-Site Infra Work | Infra - Paint Work | sqft | 5000 | 6 | 30000 | 0 | 0 | 0 | 0 | 0 | 0
159 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Cement | Cement PPC | bags | 1004.25 | 210.94 | 211836.5 | 0 | 0 | 0 | 0 | 0 | 0
160 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Chemical | Admixture PC Based | kg | 200 | 50 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
161 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 10 MM | cuft | 2134 | 22 | 46948 | 0 | 0 | 0 | 0 | 0 | 0
162 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Grit | Grit 20 MM | cuft | 2543.2 | 27 | 68666.4 | 0 | 0 | 0 | 0 | 0 | 0
163 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Civil Raw Material-Sand | M-Sand | cuft | 2275 | 40 | 91000 | 0 | 0 | 0 | 0 | 0 | 0
164 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCCW | Infra - RCC Work | cuft | 5000 | Labour-Site Infra Work | Infra - RCC Work | cuft | 5000 | 15 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
165 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Misc | Binding Wire | kg | 250 | 70 | 17500 | 46.21 | 0 | 46.21 | 3234.7 | 0 | 3234.7
166 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 08 MM | MT | 5 | 55000 | 275000 | 0.924 | 0 | 0.924 | 50831 | 0 | 50831
167 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 10 MM | MT | 5 | 55000 | 275000 | 0.924 | 0 | 0.924 | 50831 | 0 | 50831
168 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 12 MM | MT | 5 | 55000 | 275000 | 0.924 | 0 | 0.924 | 50831 | 0 | 50831
169 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 16 MM | MT | 5 | 55000 | 275000 | 0.924 | 0 | 0.924 | 50831 | 0 | 50831
170 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Civil Raw Material-Steel | TMT Steel 20 MM | MT | 5 | 55000 | 275000 | 0.924 | 0 | 0.924 | 50831 | 0 | 50831
171 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IRCW | Infra - Reinforcement Work | MT | 25 | Labour-Site Infra Work | Infra - Reinforcement | MT | 25 | 6000 | 150000 | 4.621 | 9.271 | -4.65 | 27726 | 171702 | -143976
172 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--ISHW | Infra - Shuttering Work | sqft | 1000 | Labour-Site Infra Work | Infra - Shuttering | sqft | 1000 | 15 | 15000 | 0 | 0 | 0 | 0 | 0 | 0
173 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--IWAW | Infra -Wall Tile Work | sqft | 500 | Labour-Site Infra Work | Infra -Wall Tile Work | sqft | 500 | 18 | 9000 | 0 | 0 | 0 | 0 | 0 | 0
174 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW16mm | Coupler Fixing 16mm Dia | nos | 7000 | Civil Raw Material-Coupler | Coupler 16 16 MM | nos | 7000 | 220 | 1540000 | 0 | 22 | -22 | 0 | 618.2 | -618.2
175 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW16mm | Coupler Fixing 16mm Dia | nos | 7000 | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 16 MM | nos | 7000 | 30 | 210000 | 0 | 0 | 0 | 0 | 0 | 0
176 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW20mm | Coupler Fixing 20mm Dia | nos | 4000 | Civil Raw Material-Coupler | Coupler 20 20 MM | nos | 4000 | 220 | 880000 | 1787 | 2330 | -543 | 393140 | 92035 | 301105
177 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW20mm | Coupler Fixing 20mm Dia | nos | 4000 | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 20 MM | nos | 4000 | 20 | 80000 | 1787 | 1809 | -22 | 35740 | 45225 | -9485
178 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW25mm | Coupler Fixing 25mm Dia | nos | 7000 | Civil Raw Material-Coupler | Coupler 25 25 MM | nos | 7000 | 220 | 1540000 | 3207 | 4256 | -1049 | 705540 | 260467.2 | 445072.8
179 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW25mm | Coupler Fixing 25mm Dia | nos | 7000 | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 25 MM | nos | 7000 | 30 | 210000 | 3207 | 3405 | -198 | 96210 | 85125 | 11085
180 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW25X20mm | Coupler Fixing 25mm X 20mm Dia | nos | 2500 | Civil Raw Material-Coupler | Coupler 25 20 MM | nos | 2500 | 220 | 550000 | 1453 | 2207 | -754 | 319660 | 176560 | 143100
181 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW25X20mm | Coupler Fixing 25mm X 20mm Dia | nos | 2500 | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 25mm X 20mm | nos | 2500 | 30 | 75000 | 1453 | 1453 | 0 | 43590 | 36325 | 7265
182 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW32mm | Coupler Fixing 32mm Dia | nos | 7000 | Civil Raw Material-Coupler | Coupler 32 32 MM | nos | 7000 | 220 | 1540000 | 4288 | 4885 | -597 | 943360 | 461144 | 482216
183 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW32mm | Coupler Fixing 32mm Dia | nos | 7000 | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 32 MM | nos | 7000 | 30 | 210000 | 4288 | 4288 | 0 | 128640 | 107200 | 21440
184 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW32X20mm | Coupler Fixing 32mm X 20mm Dia | nos | 500 | Civil Raw Material-Coupler | Coupler 32 20 MM | nos | 500 | 220 | 110000 | 26 | 6 | 20 | 5720 | 750 | 4970
185 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW32X20mm | Coupler Fixing 32mm X 20mm Dia | nos | 500 | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 32mm X 20mm | nos | 500 | 30 | 15000 | 26 | 26 | 0 | 780 | 650 | 130
186 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW32X25mm | Coupler Fixing 32mm X 25mm Dia | nos | 2000 | Civil Raw Material-Coupler | Coupler 32 25 MM | nos | 2000 | 220 | 440000 | 1202 | 1614 | -412 | 264440 | 201750 | 62690
187 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW32X25mm | Coupler Fixing 32mm X 25mm Dia | nos | 2000 | Labour-Civil-Coupler Fixing Work | Coupler Fixing work 32mm X 25mm | nos | 2000 | 30 | 60000 | 1202 | 1202 | 0 | 36060 | 30050 | 6010
188 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW40mm | Coupler Fixing 40mm Dia | nos | 2200 | Civil Raw Material-Coupler | Coupler 40 40 MM | nos | 2200 | 220 | 484000 | 1330 | 1366 | -36 | 292600 | 286860 | 5740
189 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW40mm | Coupler Fixing 40mm Dia | nos | 2200 | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 40 MM | nos | 2200 | 30 | 66000 | 1330 | 1330 | 0 | 39900 | 33250 | 6650
190 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW40X25mm | Coupler Fixing 40mm X 25mm Dia | nos | 500 | Civil Raw Material-Coupler | Coupler 40 25 MM | nos | 500 | 220 | 110000 | 40 | 40 | 0 | 8800 | 10480 | -1680
191 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW40X25mm | Coupler Fixing 40mm X 25mm Dia | nos | 500 | Labour-Civil-Coupler Fixing Work | Coupler Fixing Work 40mm X 25mm | nos | 500 | 30 | 15000 | 40 | 40 | 0 | 1200 | 1000 | 200
192 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW40X32mm | Coupler Fixing 40mm X 32mm Dia | nos | 1500 | Civil Raw Material-Coupler | Coupler 40 32 MM | nos | 1500 | 220 | 330000 | 636 | 851 | -215 | 139920 | 222962 | -83042
193 | WTC Commercial | WTC Commercial | MS COUPLER WORK | WTC-WTC Commercial--MSCFW40X32mm | Coupler Fixing 40mm X 32mm Dia | nos | 1500 | Labour-Civil-Coupler Fixing Work | Coupler fixing work 40mm X 32mm | nos | 1500 | 30 | 45000 | 636 | 636 | 0 | 19080 | 15900 | 3180
194 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial--RCCRW35 | RCC - Ramp - M-35 | cuft | 9646.94 | Civil Raw Material-RMC | RMC M-35 | cum | 270.114 | 4000 | 1080456 | 0 | 0 | 0 | 0 | 0 | 0
195 | WTC Commercial | WTC Commercial | REINFORCED CEMENT CONCRETE | WTC-WTC Commercial--RCCRW35 | RCC - Ramp - M-35 | cuft | 9646.94 | Labour-Civil-Concreting Work | Concreting Work With RMC M-35 | cuft | 9646.94 | 5 | 48234.7 | 0 | 0 | 0 | 0 | 0 | 0
196 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--RMC7.5IPCC | Infra - M7.5 PCC Work | cuft | 1000 | Civil Raw Material-RMC | RMC M-7.5 | cum | 28.31 | 86.38 | 2445.42 | 6.498 | 6.5 | -0.002 | 561.26 | 17221.2 | -16659.94
197 | WTC Commercial | WTC Commercial | SITE INFRA WORK | WTC-WTC Commercial--RMC7.5IPCC | Infra - M7.5 PCC Work | cuft | 1000 | Labour-Site Infra Work | Infra - PCC Work (RMC) | cuft | 1000 | 5 | 5000 | 229.515 | 229.52 | -0.005 | 1147.575 | 2608 | -1460.425
198 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SADS | Diesel | lumpsum | 180000 | Site Expenses | Diesel Expenses | lumpsum | 180000 | 1 | 180000 | 3157 | 155750 | -152593 | 3157 | 155750 | -152593
199 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SAELC | Electrical Charges | lumpsum | 12 | Site Expenses | Electricity Charges | lumpsum | 12 | 300000 | 3600000 | 1 | 7 | -6 | 300000 | 151105 | 148895
200 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SAIC | Installation Charges | lumpsum | 1500000 | Site Expenses | Installation Charges | lumpsum | 1500000 | 1 | 1500000 | 0 | 857298 | -857298 | 0 | 857298 | -857298
201 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SALBM | Lab Material | lumpsum | 500000 | Site Expenses | Lab Material | lumpsum | 500000 | 1 | 500000 | 304929 | 312309 | -7380 | 304929 | 312309 | -7380
202 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SAMVSC | Machine & Vehicle Service Charges | lumpsum | 240000 | Site Expenses | Machine & Vehicle Service Charges | lumpsum | 240000 | 1 | 240000 | 0 | 0 | 0 | 0 | 0 | 0
203 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SAOG | Office Goods | lumpsum | 500000 | Site Expenses | Office Goods | lumpsum | 500000 | 1 | 500000 | 157210 | 404211 | -247001 | 157210 | 404211 | -247001
204 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SAPRNT | Property Rent Charges | lumpsum | 12 | Site Expenses | Property Rent Charges | lumpsum | 12 | 100000 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0
205 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SAS | Stationary | lumpsum | 240000 | Site Expenses | STATIONARY | Rs. | 240000 | 1 | 240000 | 1017 | 18929 | -17912 | 1017 | 18929 | -17912
206 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SASG | Security Guard | lumpsum | 2160 | Site Expenses | Security Guard | lumpsum | 1440 | 500 | 720000 | 20 | 847 | -827 | 10000 | 444811 | -434811
207 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SASI | Safety Items | lumpsum | 500000 | Site Expenses | Safety Items | lumpsum | 500000 | 1 | 500000 | 26629 | 259259 | -232630 | 26629 | 259259 | -232630
208 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SASO | Site Office | lumpsum | 1 | Site Infra Items-Porta Cabin | Office Container Cabin | nos | 1 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0
209 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SASWM | Staff Welfare &medicne | lumpsum | 600000 | Site Expenses | Staff Welfare and Medicines | lumpsum | 600000 | 1 | 600000 | 0 | 52259 | -52259 | 0 | 52259 | -52259
210 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SATC | Travel & Conveyance | lumpsum | 240000 | Site Expenses | Travel & Conveyance | lumpsum | 240000 | 1 | 240000 | 0 | 9981 | -9981 | 0 | 9981 | -9981
211 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SATNC | Transportation & Courier Charges | lumpsum | 120000 | Site Expenses | Transportation and Courier Charges | lumpsum | 120000 | 1 | 120000 | 0 | 21240 | -21240 | 0 | 21240 | -21240
212 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SATOILT | Toilets | lumpsum | 1 | Site Infra Items-Porta Cabin | Container Portable Toilet | nos | 1 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0
213 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SATPM | Tools and Plant Material | lumpsum | 1500000 | Site Expenses | Tools and Plant Material | Rs. | 1500000 | 1 | 1500000 | 0 | 979995 | -979995 | 0 | 979995 | -979995
214 | WTC Commercial | WTC Commercial | SITE ADMINISTRATIVE EXPENSES | WTC-WTC Commercial--SAWC | Water Charges | lumpsum | 36000 | Site Expenses | Water Charges | lumpsum | 36000 | 1 | 36000 | 0 | 30120 | -30120 | 0 | 30120 | -30120